## Slide 1: Communications & Technology Goal 3.1 Communications and Technology Platform
Within 21 months, we will create and implement an enhanced communications process plan, Cathedral branding strategies and secure technology platform that will enable all parishioners to have 100% online access to our Parish services, ministries and other resources, information, tools and materials that will allow us to:
(a) have at least 70% of our stewards engaging and donating using our online engagement platform within 12 months thereafter;
(b) consistently achieve at least a 75% parishioner satisfaction level with this technology platform within 6 months thereafter; and
(c) develop and roll out a consistent and effective brand for the Cathedral and its ministries

## Slide 2: Communications & Technology Goal 3.1 Action Plan
Specific Key Actions Necessary To Achieve Goal 3.1 | Who Must Do Each Action | Timetable: How Many Months or Days To Finish Action From Previous Action | How Will We Know When This Action Has Been Completed
1. Form Communications & Technology Goal 3.1 Task Force (“C&T3.1TF”). | Strategic Planning Team and Goal Captain | 1 month from Start Date | C&T3.1TF members agree to serve
2. Research most effective church communications, branding strategies and technology resources, software, information, tools, and the best practices that churches and other non-profits use to connect with, and communicate to their parishioners and stakeholders. | C&T3.1TF | 4 months after step 1 | Report of most effective church communications and technology resources, information, tools and best practices is completed
3. Create, collect and determine metrics to measure parishioner use of and satisfaction with current website, online engagement and giving processes and communication channels, and other desirable ways to access our Parish and other services, information, processes and ministries. | C&T3.1TF | Simultaneous with step 2 | At least 20% of Parishioners respond to survey and report of survey results is summarized
4. (a) Analyze survey results from step 3; (b) begin developing branding materials; and (c) audit all current technology, communications process and all software capabilities (including, website, video broadcast, social media accounts, telephony, phone tree) compared against best practices established in step 2. | C&T3.1TF | 4 months after step 2 | Report summarizing status of capabilities of current resources and processes and preliminary branding materials is produced

## Slide 3: Communications & Technology Goal 3.1 Action Plan
Specific Key Actions Necessary To Achieve Goal 3.1 | Who Must Do Each Action | Timetable: How Many Months or Days To Finish Action From Previous Action | How Will We Know When This Action Has Been Completed
5. Interview stakeholders (clergy, office staff, ministry chairs and all demographics of parishioners) that produce or consume Parish services, communications and technology resources and work with our staff to research and identify the capabilities and gaps of our existing software and how our engagement and giving is processed. | C&T3.1TF | Simultaneous with step 4 | Report summarizing stakeholder interviews and giving processes and any underutilized software features and gap analysis is produced
6. Finalize (the “Communication & Technology Plan”) consisting of : (a) branding materials; (b) research and identification of potential alternative technology solutions enabling broadcast and dissemination of church services and creation of a communications hub to allow for content creators (clergy, office staff, ministry chairs) to create and target and deliver communications to parishioners through all channels; and (c) comprehensive recommendations, budget and implementation timeline in all areas of communications, online engagement and giving and technology, including appropriate metrics to evaluate and determine success. | C&T3.1TF | 4 months after step 5 | Communication & Technology Plan is finally developed (in cooperation with the Task Force working on Operational Excellence Strategic Goal 5.2)

## Slide 4: Communications & Technology Goal 3.1 Action Plan
Specific Key Actions Necessary To Achieve Goal 3.1 | Who Must Do Each Action | Timetable: How Many Months or Days To Finish Action From Previous Action | How Will We Know When This Action Has Been Completed
7. Obtain (a) any necessary budgetary, Parish Council, General Assembly or other approvals for Communication & Technology Plan recommendations; and (b) any necessary funding. | C&T3.1TF, Clergy and Parish Council | 6 months after step 6 | Necessary approvals and budgets are obtained
8. Establish governance, guidelines and monitoring processes for proper operation and use of all communications and engagement technology solutions. | C&T3.1TF, Clergy and Parish Council | Simultaneously with step 7 | Governance, guidelines and monitoring processes document is created and approved
9. Procure the products, systems, technical and facility resources, human resources necessary to implement the Communications & technology Plan. | C&T3.1TF, Clergy and Parish Council | 1 month after steps 7 and 8 | Procurement and pre-implementation checklist is fully acquired and complete
10. Begin implementation of Communication & Technology Plan based on implementation timeline, including enhanced online engagement and giving and access to other church services and self-service communications hub (“Communications Hub”) to allow parishioners to subscribe to the communications channels they wish to receive. | C&T3.1TF | 1 months after step 9 | Communication & Technology Plan and Communications Hub roll out begins

## Slide 5: Communications & Technology Goal 3.1 Action Plan
Specific Key Actions Necessary To Achieve Goal 3.1 | Who Must Do Each Action | Timetable: How Many Months or Days To Finish Action From Previous Action | How Will We Know When This Action Has Been Completed
11. Semi-annual parishioner survey and independent review, evaluation, update and changes in Communication & Technology Plan and Communications Hub to ensure that all elements are the most effective best practices available and ensure achievement of the targets of: (a) 70% of our stewards engaging and donating using our online engagement platform; and (b) at least a 75% parishioner satisfaction level with this engagement technology platform. | C&T3.1TF | Beginning 6 months after step 10 and every 6 months thereafter | Semi-Annual assessment of Communication & Technology Plan and Communications Hub is completed at least every 6 months and appropriate changes are implemented