## Slide 1: Campus Improvements Goal 1.1 Campus Improvements
(a) Within 15 month, we will determine the projected costs, timelines, obtain necessary approvals and prioritize a Master Plan for the most critical Cathedral Campus improvements, including improved: (i) facilities more accessible to individuals with disabilities; (ii) outdoor facilities; (iii) storage facilities; and (iv) signage.
(b) Within 2 years thereafter, we will raise the necessary funds and complete the prioritized improvements based on the established timelines.

## Slide 2: Campus Improvements Goal 1.1 Action Plan
Specific Key Actions Necessary To Achieve Goal 1.1 | Who Must Do Each Action | Timetable: How Many Months or Days To Finish Action From Previous Action | How Will We Know When This Action Has Been Completed
1. Form Campus Improvements Goal 1.1 Task Force (“CI1.1TF”). | Strategic Planning Team and Goal Captain | 1 month from Start Date | CI1.1TF team members agree to serve
2. Research and identify accessibility, athletic and storage facility projects (“Master Plan Projects”) needs throughout our campus by (a) conducting an on-site assessment with appropriate legal and facilities experts; (b) developing outreach tools (e.g., survey, focus groups, etc.) to receive feedback from community concerning Master Plan Projects needs; and (c) reviewing existing documentation on previous efforts to identify necessary improvements. | CI1.1TF | 4 months after step 1 | Completed on-site assessment, survey/focus group findings compiled in centralized format, existing documentation compiled a notebook of Master Plan Projects.
3. Establish criteria for prioritization and then prioritize Master Plan Projects list identified in step 2 (e.g., critical, necessary, desirable, etc.) and establish a proposed implementation timeline. | Parish Council and CI1.1TF | 1 month after step 2 | Proposed prioritization of Master Plan Projects completed
4. Create preliminary design drawings and research cost estimates for each prioritized Master Plan Project and compile comprehensive Master Plan Project Plan with all projects prioritized, costed and having proposed timelines. | CI1.1TF | 5 months after step 3 | Estimated costs and timelines determined and Master Plan Project Plan developed

## Slide 3: Campus Improvements Goal 1.1 Action Plan
Specific Key Actions Necessary To Achieve Goal 1.1 | Who Must Do Each Action | Timetable: How Many Months or Days To Finish Action From Previous Action | How Will We Know When This Action Has Been Completed
5. Obtain first Parish Council and then General Assembly (and any other required approvals (e.g., Metropolis, county, etc.)). | CI1.1TF and Parish Council and General Assembly | 4 months after step 4 | Required Parish Council, General Assembly and other approvals all obtained
6. Work collaboratively with Parish Council and Parish community to conduct feasibility study and procure necessary funding for approved prioritized Master Plan Projects. | CI1.1TF and Parish Council | 10 months after step 5 | Master Plan Project funds are raised
7. Work collaboratively with Parish Council and appropriate Parish authorities responsible for project management (e.g., finalize the design plans and design and construction bid process and permits, and the construction process, etc.) as necessary and appropriate to monitor progress and ensure timely and proper completion. | CI1.1TF and Parish Council | 6 months after step 6 | Periodic project reports and presented to Parish Council
8. Supervise completion of construction on identified Master Plan Projects. | CI1.1TF and Parish Council | 7 months after step 7 | Construction, including punch list items is complete and Parish accepts work
9. Conduct after completion review on all Master Plan Projects and processes and document lessons learned. | CI1.1TF and Parish Council | 1 month after step 7 | Master Plan Project final report submitted to Cathedral community