## Slide 1: Leadership Goal Sample 1

## Slide 2: Leadership, Outreach & Stewardship S.M.A.R.T. Goal 3
Measurably improve our stewardship and discipleship by developing and implementing an effective Leadership, Outreach, and Stewardship Programs (collectively, the “Discipleship Programs”) that will achieve the following “Discipleship Goals:”
(a) 100% of Parish Council members and candidates and ministry leaders will complete our Parish Leadership Program within 12 months and all PC members and Ministry leaders thereafter will do so before assuming their duties and responsibilities;
(b) a Welcoming Ministry Program which will actively engage 100% of visitors and invite them to participate in a comprehensive welcoming process within 10 months;
(c) a new Outreach Ministry Program will ensure at least 30 or more unaffiliated Orthodox or non-Orthodox join or re-join as stewards the parish each year beginning in 2024; and
(d) increase parish time, talents, and treasures stewardship by:
(i) within 34 months, increasing parish financial stewardship to consistently fund all operating expenses plus 10% or more of that parish approved budget to be expended on mission and community philanthropic outreach; and
(ii) Aggregate time and talent contributions by parishioners is increased by at least 10% over the starting baseline within 24 months.

## Slide 3: Leadership, Outreach & Stewardship Lags - Goal 3
LAG 1: Research the most effective leadership, outreach, and stewardship programs (the “Discipleship Programs”) within 4 months
LAG 2: Develop the most effective Discipleship Programs within 4 months
LAG 3: Recruit and train any needed parish training “Discipleship Ambassadors” within 2 months
LAG 4: Implement the Discipleship Programs to achieve all Discipleship Goals in not to exceed 24 months
LAG 5: Compile and assess the results of the Discipleship Programs and make necessary improvements within 2 months

## Slide 4: Leadership, Outreach & Stewardship Leads – Goal 3
LEAD 1:
  A: recruit team
  B: determine leadership , outreach, and stewardship key definitions, desired outcomes, and effectiveness metrics
  C: analyze the parish baseline on 1(B) key metrics and identify parish baselines and impediments to success
  D: identify at least 3 Leadership, 3 Outreach, and 3 Stewardship Programs to consider
LEAD 2:
  A: evaluate researched leadership , outreach, and stewardship for effectiveness against key definitions, performance metrics and parish baselines
  B: Modify all researched or existing leadership, outreach, and stewardship programs (the “Discipleship Programs”) for utilization at Holy Trinity to meet Discipleship Goals
  C: finalize parish Discipleship Programs and establish quarterly and/or monthly performance benchmarks to assess progress toward all respective Discipleship Goals
LEAD 3:
  A: identify numbers and names of Discipleship “Ambassadors” to help deliver Discipleship Programs
  B: develop Discipleship Ambassadors training programs
  C: train the Discipleship Ambassadors
LEAD 4:
  A: implement Discipleship Programs based on determined monthly and quarterly performance benchmarks to achieve all respective Discipleship Goals
  B: continue Ambassadors’ follow-up until all Discipleship Goals are achieved
LEAD 5:
  A: obtain qualitative and quantitative data from Discipleship Programs effectiveness
  B: analyze all data and finalize Discipleship Programs assessment and make all necessary improvements

## Slide 5
Key Actions Necessary To Achieve Strategic Goal 3 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 1: Research the most effective stewardship, and ministry and liturgical engagement programs (the “Discipleship Programs”) within 4 months |  |  | 
1. Form SMART Goal Team 3 (“Discipleship Ministry Team 3”). | Strategic Planning Team and Goal co-Captains | 1 month after Start Date | Discipleship Ministry Team 3 members agree to serve
2. Determine leadership, outreach, and stewardship engagement key definitions and effectiveness metrics. | Discipleship Ministry Team 3 | 2 month after step 1 | Discipleship definitions and metrics determined
3. Research and analyze the parish baselines on step 2 key metrics and survey or otherwise research and identify parish impediments to success on those key leadership, outreach, and stewardship effectiveness metrics success | Discipleship Ministry Team 3 | 1 months after step 2 | Parish baselines and parish impediments are finalized
4. Identify and research at least 3 Leadership, 3 Outreach, and 3 Stewardship Programs from both inside and outside the Orthodox ecosystem to evaluate and consider. | Discipleship Ministry Team 3 | Simultaneous with steps 2 & 3 | At least 3 Leadership, 3 Outreach, and 3 Stewardship Discipleship Programs examined
Leadership, Outreach & Stewardship
S.M.A.R.T. Goal 3

## Slide 6
Key Actions Necessary To Achieve Strategic Goal 3 | Responsible Party | Deadline Timetable |  | Completion Confirmation Test
LAG 2: Develop the most effective Discipleship Programs within 4 months |  |  |  | 
5. Evaluate researched leadership, outreach, and stewardship programs for effectiveness against key performance metrics and parish baselines based on criteria of effectiveness determined in step 2. | Discipleship Ministry Team 3 | 2 months after step 4 | Evaluation of alternative Leadership, Outreach, and Stewardship Discipleship programs is completed | Evaluation of alternative Stewardship, Outreach & Evangelism, and Leadership Discipleship programs is completed
6. Modify researched or existing Discipleship Programs for utilization at Holy Trinity and create and finalize parish Discipleship Programs and establish quarterly and/or monthly performance benchmarks to achieve all respective established Discipleship Goals. | Discipleship Ministry Team 3 | 2 months after step 5 | Discipleship Programs are finalized | Discipleship Programs are finalized
LAG 3: Recruit and train the parish Discipleship Ambassadors within 2 months |  |  |  | 
7. Identify and recruit the “Discipleship Ambassadors” who can implement the various Discipleship Programs. | Discipleship Ministry Team 3 | 1 month after step 6 | Discipleship Ambassadors are recruited | Discipleship Ambassadors are recruited
8. Develop Discipleship Ambassadors training program and train the Discipleship Ambassadors selected in step 7. | Discipleship Ministry Team 3 | 1 month after step 7 | Discipleship Ambassadors are trained | Discipleship Ambassadors are trained
Leadership, Outreach & Stewardship
S.M.A.R.T. Goal 3

## Slide 7
Key Actions Necessary To Achieve Strategic Goal 3 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 4: Implement the Engagement Programs to achieve the targeted goals within 24 months |  |  | 
9. Implement Discipleship Programs based on monthly and/or quarterly performance benchmarks determined in step 6 with continual Ambassador follow-up until all Discipleship Goals are achieved. | Discipleship Ambassadors | 24 months after step 8 | Established quarterly and/or monthly Discipleship Goals are achieved
LAG 5: Compile and assess the results of the Parish Discipleship Programs and make necessary improvements within 2 months |  |  | 
10. Obtain and compile qualitative and quantitative data from Discipleship Programs and compile as to the effectiveness and success (based on criteria established in step 2) and areas for improvement. | Discipleship Ambassadors and Discipleship Ministry Team 3 | 1 month after step 9 | Discipleship Programs assessments are completed
11. Finalize and deliver improvements to Discipleship Programs assessment analysis report, and make all refinements necessary to make those Ministries more effective based on information identified in step 10, and revise and improve them accordingly. | Discipleship Ambassadors and Discipleship Ministry Team 3 | 1 month after step 10 | Discipleship Programs implementation analysis is completed, and Discipleship Programs are refined accordingly
Leadership, Outreach & Stewardship
S.M.A.R.T. Goal 3

## Slide 8
Lead Measure Action | Deadline Date | Status: Percent Complete and Date
1. Form Discipleship Ministry Team 1 |  | 
2. Develop definitions and effectiveness metrics |  | 
3. Analyze parish baselines and success impediments |  | 
4. Research Discipleship Programs |  | 
5. Evaluate Discipleship Programs |  | 
6. Finalize Discipleship Programs |  | 
7. Identify and recruit Discipleship Ambassadors |  | 
8. Train Discipleship Ambassadors |  | 
9. Implement Discipleship Programs and manage to interim quarterly and monthly targets to achieve all Discipleship Goals |  | 
10. Obtain Data from Discipleship Programs Implementation |  | 
11. Improve Discipleship Programs based lessons learned in step 10 |  | 
Leadership, Outreach & Stewardship
Goal 3 Scoreboard

## Slide 9: Leadership Goal Sample 2

## Slide 10
Within 17 months, we will develop or customize a comprehensive and effective Orthodox Servant Leadership training program and implementation timeline that will be mandatory within 2 months thereafter for all new and current Parish Council Members and all Ministry Leaders and Educators, and voluntary for prospective leaders.
ADMINISTRATION, LEADERSHIP & FACILITIES 1.2 Leadership Development

## Slide 11: Administration, Leadership & Facilities Goal 1.2 Action Plan
Key Actions Necessary To Achieve Strategic Goal 1.2 | Responsible Party | Timetable | Completion Confirmation Test
1. Form Administration, Leadership & Facilities Goal 1.2 Team (Leadership Development Task Force (“AL&F1.2TF”) | Strategic Planning Team and Goal Captain | 1 month from Start Date | AL&F1.2TFmembers agree to serve
2. Conduct comprehensive research and identify: (a) best practices in Orthodox Servant Leadership Development using sources both inside and outside the Orthodox church; (b) key leadership skill elements and gaps which need to be filled for all three groups of Parish Council, Ministry Leaders and Educators (the “Three Constituents”); and (c) how to properly benchmark and measure the effectiveness of leadership training for all Three Constituents. | AL&F1.2TF | 5 months after step 1 | Research is completed and best practices summary report generated
3. Develop data collection methods, tools, metrics and targets that will effectively capture information from a diverse group of Orthodox and non-Orthodox to identify needed lay leadership skills and content for all Three Constituents (the “Data Collection Plan”). | AL&F1.2TF | Simultaneous with step 2 | Full Data Collection Plan is finalized

## Slide 12: Administration, Leadership & Facilities Goal 1.2 Action Plan
Key Actions Necessary To Achieve Strategic Goal 1.2 | Responsible Party | Timetable | Completion Confirmation Test
4. Implement Data Collection Plan among all targeted individuals identified in step 3. | AL&F1.2TF | 6 months after steps 2 and 3 | Data Collection Plan is completed consistent with guidelines set in step 3
Compile research and data from steps 2, 3, and 4 and review and analyze results to identify: (a) best practices in lay leadership training for all Three Constituents; (b) strengths, weaknesses, skills and gaps in current lay leadership programs for all Three Constituents; and (c) specific information on how to best reach and train all Three Constituents and measure effectiveness of such training. | AL&F1.2TF | 2 months after step 4 | Data analysis report is completed with all findings and recommendations
6. From all available resources, materials, and research (including the work done in steps 2-5), develop a best practices comprehensive “Lay Leadership Training Program” (including written materials, manuals and online resources) that addresses the specific lay leadership needs of all Three Constituents. | AL&F1.2TF | 2 months after step 5 | The Lay Leadership Training Program is finalized for all Three Constituents.

## Slide 13: Administration, Leadership & Facilities Goal 1.2 Action Plan
Key Actions Necessary To Achieve Strategic Goal 1.2 | Responsible Party | Timetable | Completion Confirmation Test
7. Recruit and train a team to help train and support the parish in the implementation of the Leadership Development Training Program (“the Training and Support Team”). Additionally, develop a training and support strategy, program, and schedule with a detailed rollout action plan and timeline that allows the stated target percentages to be achieved (the “Training and Support Program”). | AL&F1.2TF | Simultaneous with step 6 | At least four Training and Support Team members agree to serve and the Training and Support Program is finalized
Begin conducting and delivering: (a) Parish Council Leadership Development Training; (b) Ministry Leadership Development Training; and (c) Educator Training. | AL&F1.2TF Training and Support Team | 1 month after steps 6 & 7 | Training programs begin for Three Constituents are designed according to the Training and Support Program
9. After every Leadership Training Program, perform an assessment of its effectiveness and identify areas for improvement and make necessary course corrections. | AL&F1.2TF | Beginning after each program | Assessments are completed after every program and improvements implemented
10. At least annually, comprehensively survey and assess the Leadership Training Program for all Three Constituents and make necessary changes to ensure that all materials are the most effective best practices available and the targets of mandatory training are achieved. The acceptable target evaluation score is that at least 80% of participants rate the Training Programs in the top 2 rating categories. | AL&F1.2TF | Beginning annually after step 8 | At least annual assessment of Leadership Training Program is completed, improvements are implemented, and training targets are achieved

## Slide 14: Leadership Goal Sample 3

## Slide 15: Leadership, Management & Operations Goal 5.1 Orthodox Servant Leadership Program
Within 12 months, we will develop and implement a comprehensive and effective Orthodox Servant Leadership training and development program that will be mandatory for all Parish Council members, Ministry Leaders and youth leaders.

## Slide 16: Leadership, Management and Operations Goal 5.1 Action Plan
Specific Key Actions Necessary To Achieve Goal 5.1 | Who Must Do Each Action | Timetable: How Many Months or Days To Finish Action From Previous Action | How Will We Know When This Action Has Been Completed
1. Form Leadership, Management & Operations Goal 5.1 Task Force (“LMO5.1TF”). | Strategic Planning Team & Goal Captain | 1 month from Start Date | LMO5.1TF team members agree to serve
2. Research and identify best practices in: (a) Servant Leadership (both inside and outside the Orthodox church, including the Metropolis of Atlanta Orthodox Leadership Training program); (b) identify key leadership skill elements and gaps which need to be filled (shaped by the our values, mission, vision and goals); and (c) develop interview questions for participants in steps 3 and 4. | LMO5.1TF | 3 months after step 1 | Research is completed and best practices summary report generated, including elements of Metropolis Training Program that can be used
3. Identify and interview adults already in Parish leadership positions and discuss their skills, experiences and what they believe would help improve their performance and our Parish now and into the future. | LMO5.1TF | 3 months after step 2 | Summaries of adult leadership interviews are completed and compiled
4. Identify and interview youth, as well as other adults who show leadership potential, and assess what developmental areas that would help them or would be required by them in order to step into leadership positions in the near future. | LMO5.1TF | Simultaneous with step 3 | Interviews of youth and adult leaders are completed and compiled

## Slide 17: Leadership, Management and Operations Goal 5.1 Action Plan
Specific Key Actions Necessary To Achieve Goal 5.1 | Who Must Do Each Action | Timetable: How Many Months or Days To Finish Action From Previous Action | How Will We Know When This Action Has Been Completed
5. From all available research, resources and materials (including the work done in steps 2-4), develop Leadership Program training for all 4 tiers (the “4 Tiers”): (a) Parish Council members; (b) Ministry Leaders and Endowment members; (c) future leaders; and (d) youth leaders, that at least includes core management skills (planning, process, people, budgets, reporting, etc.), and leadership skills (team building, coaching and visioning, negotiation, conflict resolution, communication, etc.). | LMO5.1TF | 4 months after step 4 | Training program created for all 4 Tiers of Leadership Program
6. Establish a schedule for, and begin to regularly deliver, Leadership Program training to all 4 Tiers, with any candidate for Parish Council or Ministry Leadership being required to receive the training before they can serve in such capacities. | LMO5.1TF | 1 month after step 5 | Training for all 4 Tiers is conducted on set schedule
7. After every Leadership Training program perform an assessment of its effectiveness and identify areas for improvement and make necessary course corrections, | LMO5.1TF | After each program | Assessments are completed after every program and at least annually and improvements are implemented
8. At least annually, comprehensively assess the effectiveness of the entire Leadership Training Program for all 4 Tiers to ensure that all materials are the most effective best practices available and the target level of mandatory training is achieved. | LMO5.1TF | At least annual review | At least annual assessment of Leadership Training Program is completed, improvements are implemented and training targets are achieved