## Slide 1
Within 18 months, we will develop and implement a series of Life Stage Ministries to address the varied ministry needs of our singles, married couples, families, youth and seniors, that will include at least 50% of our parishioners within 3 years thereafter.
Life Stage Ministries
Goal 6.2 Life Stage Ministries

## Slide 2: Life Stage Ministry Goal 6.2 Action Plan
Specific Key Actions Necessary To Achieve Goal 6.2 | Who Must Do Each Action | Timetable: How Many Months or Days To Finish Action From Previous Action | How Will We Know When This Action Has Been Completed
1. Form Life Stage Ministry Goal 6.2 Task Force (“LSM6.2TF”) | Strategic Planning Team and Goal Captain | 1 month from Start Date | LCM6.2TF team members agree to serve.
2. Conduct comprehensive research from all available sources to determine how to properly measure the effectiveness of church singles, married couples, family, youth & seniors ministries and programs (“Life Stage Ministries”) and establish a “Ministry Effectiveness Measurement Methodology and Process” to test the effectiveness of our Life Stage Ministries. | LSM6.2TF | 6 months after step 1 | Life Stage Ministries Effectiveness Measurement Methodology and Process Report is completed
3. Conduct comprehensive research to determine best in class Orthodox and non-Orthodox Life Stage Ministry programs, materials, content, delivery options and best practices (“Best Practices”), including reviewing existing Metropolis of Atlanta strategic plan Life Stage Ministry materials, and specifically identify objective evidence of the effectiveness of each. | LSM6.2TF | simultaneous with step 2 | All materials are researched including objective evidence of effectiveness based on Life Stage Ministries Effectiveness Measurement Methodology and Process and Best Practices are defined
4. Together with existing Parish Life Stage Ministry leaders use Life Stage Ministries Effectiveness Measurement Methodology and Process and Best Practices to qualitatively analyze and assess all existing and researched Life Stage Ministry programs and materials (“Best Practices Report”) and identify gaps in existing our Life Stage Ministries (“GAP Analysis”). | LSM6.2TF and existing Parish Life Stage Ministry Leaders | 4 months after step 3 | Complete comprehensive Best Practices Report of all existing and researched Life Stage Ministries Measurement Methodology and Process and Gap Analysis

## Slide 3: Life Stage Ministry Goal 6.2 Action Plan
Specific Key Actions Necessary To Achieve Goal 6.2 | Who Must Do Each Action | Timetable: How Many Months or Days To Finish Action From Previous Action | How Will We Know When This Action Has Been Completed
5. Based on Best Practices Report and GAP Analysis revise existing Life Stage Ministries and develop new Life Stage Ministry programs that meet or exceed Best Practices and establish timetable and action plan to achieve engagement of at least (50%) of our parishioners within 3 years. | LSM6.2TF | 6 months after step 4 | Gap Analysis Workplan is executed and gaps are filled
6. Begin official roll out of new and revised Life Stage Ministry programs. | LSM6.2TF | 1 month after step 5 | New and revised Life Stage Ministry programs are officially rolled-out
7. Semi-annual review, evaluation and update of all Life Stage Ministries against Effectiveness Measurement Methodology and Process, Best Practices and progress toward achievement of goal of reaching at least (50%) of our parishioners within 3 years. | LSM6.2TF | Semi-annual review | Semi-Annual assessment of Life Stage Ministries is complete, improvements are implemented and 50% target is achieved