## Slide 1: Sample 1 Outreach & Evangelism

## Slide 2: Community Outreach & Evangelism S.M.A.R.T Goal 3
We will research, develop, and implement best practices, effective Community Outreach & Evangelism Programs (the “Discipleship Programs”) that will achieve the following “Discipleship Goals” within 36 months:
(a) a new Community Outreach Ministry will:
(i) participate in at least 6 significant community outreach, philanthropic, and service projects sponsored either by the parish alone or in partnership with another group, in which at least 40% of adults and youth parishioners will participate each calendar year (not counting food fest participation);
(ii) establish a new parish comprehensive Total Welcoming Ministry which engages 100% of visitors and lapsed parishioners; and
(b) a new Evangelism Ministry will:
(i) develop an evangelism training program in which at least 30% of parishioners participate;
(ii) at least semiannually the parish will have an evangelism presence at one of the community events or public gatherings beginning within 10 months; and
(iii) at least 8 new convert individuals (or 8 families) will join the Parish each calendar year due to the Discipleship Programs and remain active at least one year later.

## Slide 3: Prelim Lag Measures - Goal 3
LAG 1: Research the most effective community outreach & evangelism programs (the “Discipleship Programs”) within 4 months
LAG 2: Develop the most effective Discipleship Programs within 4 months
LAG 3: Recruit and train any needed parish “Discipleship Ambassadors” within 2 months
LAG 4: Implement the Discipleship Programs to achieve all Discipleship Goals in not to exceed 24 months
LAG 5: Compile and assess the results of the Discipleship Programs and make necessary improvements within 2 months

## Slide 4: Prelim Lead Measures Goal 3
LEAD 1:
  A: recruit team
  B: determine community outreach & evangelism key definitions, desired outcomes, and effectiveness metrics
  C: analyze the parish baseline on 1(B) key metrics and identify parish baselines and impediments to success
  D: identify at least 3 outreach and 3 evangelism programs to consider
LEAD 2:
  A: evaluate researched outreach and evangelism for effectiveness against key definitions, performance metrics and parish baselines
  B: modify all researched or existing community outreach & evangelism programs (the “Discipleship Programs”) for utilization at our parish to meet “Discipleship Goals”
  C: finalize parish Discipleship Programs and establish quarterly and/or monthly performance benchmarks to assess progress toward all respective Discipleship Goals
LEAD 3:
  A: identify numbers and names of Discipleship “Ambassadors” to help deliver Discipleship Programs
  B: develop Discipleship Ambassadors training programs
  C: train the Discipleship Ambassadors
LEAD 4:
  A: implement Discipleship Programs based on determined monthly and quarterly performance benchmarks to achieve all respective Discipleship Goals
  B: continue Ambassadors’ follow-up until all Discipleship Goals are achieved
LEAD 5:
  A: obtain qualitative and quantitative data from Discipleship Programs effectiveness
  B: analyze all data and finalize Discipleship Programs assessment and make all necessary improvements

## Slide 5: Community Outreach & Evangelism SMART Goal 3
Key Actions Necessary To Achieve SMART Goal 3 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 1: Research the most effective community outreach & evangelism programs (the “Discipleship Programs”) within 4 months |  |  | 
1. Form Parish SMART Goal Team 3 (“Discipleship Ministry Team 3”). | Strategic Planning Team and Goal co-Captains | 1 month after Start Date | Discipleship Ministry Team 3 members agree to serve
2. Determine community outreach & evangelism engagement key definitions and effectiveness metrics. | Discipleship Ministry Team 3 | 2 month after step 1 | Discipleship definitions and metrics determined
3. Research and analyze the parish baselines on step 2 key metrics, survey present and former parishioners, and research and identify parish impediments to success on those key community outreach & evangelism effectiveness metrics success | Discipleship Ministry Team 3 | 1 months after step 2 | Parish baselines and parish impediments are finalized
4. Identify and research at least 3 community outreach, and 3 evangelism programs to consider from both inside and outside the Orthodox ecosystem. | Discipleship Ministry Team 3 | Simultaneous with steps 2 & 3 | At least 3 community outreach, and 3 evangelism programs are examined

## Slide 6: Community Outreach & Evangelism SMART Goal 3
Key Actions Necessary To Achieve SMART Goal 3 | Responsible Party | Deadline Timetable |  | Completion Confirmation Test
LAG 2: Develop the most effective Discipleship Programs within 4 months |  |  |  | 
5. Evaluate researched community outreach & evangelism programs for effectiveness against key performance metrics and parish desires and baselines based on criteria of effectiveness determined in step 2. | Discipleship Ministry Team 3 | 2 months after step 4 | Evaluation of alternative outreach & evangelism programs is completed | Evaluation of alternative Stewardship, Outreach & Evangelism, and Leadership Discipleship programs is completed
6. Modify researched or existing Discipleship Programs for utilization at parish and create and finalize parish Discipleship Programs and establish quarterly and/or monthly performance benchmarks to achieve all respective established Discipleship Goals. | Discipleship Ministry Team 3 | 2 months after step 5 | Discipleship Programs are finalized | Discipleship Programs are finalized
LAG 3: Recruit and train the Parish Discipleship Ambassadors within 2 months |  |  |  | 
7. Identify and recruit the “Discipleship Ambassadors” who can implement the various Discipleship Programs. | Discipleship Ministry Team 3 | 1 month after step 6 | Discipleship Ambassadors are recruited | Discipleship Ambassadors are recruited
8. Train Discipleship Ambassadors selected in step 7 on how best to deliver Discipleship Programs. | Discipleship Ministry Team 3 | 1 month after step 7 | Discipleship Ambassadors are trained | Discipleship Ambassadors are trained

## Slide 7: Community Outreach & Evangelism SMART Goal 3
Key Actions Necessary To Achieve SMART Goal 3 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 4: Implement the Engagement Programs to achieve the targeted goals within 24 months |  |  | 
9. Implement Discipleship Programs based on monthly and/or quarterly performance benchmarks determined in step 6 with continual Discipleship Ambassador follow-up until all Discipleship Goals are achieved. | Discipleship Ambassadors and Discipleship Ministry Team 3 | 24 months after step 8 | Established quarterly and/or monthly Discipleship Goals are achieved
LAG 5: Compile and assess the results of the Parish Discipleship Programs and make necessary improvements within 2 months |  |  | 
10. Obtain and compile qualitative and quantitative data from Discipleship Programs and compile as to the effectiveness and success (based on criteria established in step 2) and areas for improvement. | Discipleship Ambassadors and Discipleship Ministry Team 3 | 1 month after step 9 | Discipleship Programs assessments are completed
11. Finalize and deliver improvements to Discipleship Programs assessment analysis report, and make all refinements necessary to make those Ministries more effective based on information identified in step 10, and revise and improve them accordingly. | Discipleship Ambassadors and Discipleship Ministry Team 3 | 1 month after step 10 | Discipleship Programs implementation analysis is completed, and Discipleship Programs are refined accordingly

## Slide 8
Lead Measure Action | Deadline Date | Status: Percent Complete and Date
1. Form Discipleship Ministry Team 1 |  | 
2. Develop definitions and effectiveness metrics |  | 
3. Analyze parish baselines and success impediments |  | 
4. Research Discipleship Programs |  | 
5. Evaluate Discipleship Programs |  | 
6. Finalize Discipleship Programs |  | 
7. Identify and recruit Discipleship Ambassadors |  | 
8. Train Discipleship Ambassadors |  | 
9. Implement Discipleship Programs and manage to interim quarterly and monthly targets to achieve all Discipleship Goals |  | 
10. Obtain Data from Discipleship Programs Implementation |  | 
11. Improve Discipleship Programs based lessons learned in step 10 |  | 
Community Outreach & Evangelism
SMART Goal 3

## Slide 9: Sample 2 Outreach & Evangelism

## Slide 10: External Service & Evangelism Wildly Important Goal 2
Develop and implement within 36 months the following effective “External Ministries” :
(a) External Service Ministry: that will achieve at least a:
(i) 33% increase in parishioner meaningful engagement within 24 months; and
(ii) 50% increase in parishioner meaningful engagement within 36 months; and
(b) Evangelism Ministry – that will have a meaningful interaction with:
(i) 100% of lapsed St. Nicholas parishioners; and
(ii) at least 700 non-Orthodox individuals who interact with the parish, including through specific external evangelism activities.

## Slide 11
LAG 1: Define and research the most effective External Service Ministry and Evangelism Ministry within 3 months
LAG 2: Develop the most effective External Service Ministry and Evangelism Ministry within 4 months
LAG 3: Identify the modalities, processes and procedures to achieve the following “Targets”: (a) at least a 33% increase in parishioner meaningful engagement within 24 months and 50% increase within 36 months; and (b) meaningful interaction with: (1) 100% of lapsed St. Nicholas parishioners; and (2) at least 700 non-Orthodox individuals, within 3 months
LAG 4: Implement the External Service Ministry & Evangelism Ministry to achieve the Targets within 24 months
LAG 5: Compile and assess the results of the External Service Ministry & Evangelism Ministry and make necessary improvements within 2 months.
WIG 2:
Develop and implement within 36 months an effective:
External Service Ministry – that will achieve at least a:
(i) 33% increase in parishioner meaningful engagement within 24 months; and
(ii) 50% increase in parishioner meaningful engagement within 36 months; and
(b) Evangelism Ministry – that will have a meaningful interaction with:
(i) 100% of lapsed St. Nicholas parishioners; and
(ii) at least 700 non-Orthodox individuals who interact with the parish, including through specific external evangelism activities.
External Service & Evangelism
Lag Measures WIG 2

## Slide 12
LEAD 1:
A: recruit team
B: define: (i) parishioner “engagement” in external service ministry; and (2) “meaningful engagement” with both lapsed Orthodox St. Nicholas parishioners and non-Orthodox individuals
C: research and identify metrics to determine effectiveness
  of External Service Ministry and Evangelism Ministry (collectively the “External Ministries”)
  D: Identify at least 5 external effective service ministries and 5 effective evangelism ministries to consider
LEAD 2:
  A: evaluate researched programs for effectiveness
  B: modify and/or develop External Ministries for utilization at St. Nicholas
  C: finalize External Ministries and effectiveness metrics
LEAD 3:
  A: identify External Ministries implementation modalities (technology and ministry participants)
  B: develop External Ministries ministry participant training program and ministry delivery modalities and materials
  C: recruit and train the parishioners who will implement the External Ministries (“External Ministries Disciples”)
LEAD 4:
  A: implement the External Ministries
  B: monthly track and report on the achievement of the External Ministries Targets and identify how to overcome impediments to success
LEAD 5:
  A: obtain qualitative and quantitative data from External Ministries effectiveness
  B: analyze all data and make all necessary improvements to External Ministries
LAG 1: Define and research the most effective External Service Ministry & Evangelism Ministry within 3 months
LAG 2: Develop the most effective External Service Ministry and Evangelism Ministry within 4 months
LAG 3: Identify the modalities, processes and procedures to achieve the following “Targets”: (a) at least a 33% increase in parishioner meaningful engagement within 24 months and 50% increase within 36 months; and (b) meaningful interaction with: (1) 100% of lapsed St. Nicholas parishioners; and (2) at least 700 non-Orthodox individuals, within 3 months
LAG 4: Implement the External Service Ministry & Evangelism Ministry to achieve the Targets within 24 months
LAG 5: Compile and assess the results of the External Service Ministry & Evangelism Ministry and make necessary improvements within 2 months.
External Service & Evangelism
Lead Measures WIG 2

## Slide 13
Key Actions Necessary To Achieve Strategic WIG 2 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 1: Define and research the most effective External Service Ministry & Evangelism Ministry within _3_ months |  |  | 
1. Form External Service Ministry & Evangelism Ministry (collectively, the “External Ministries” Wildly Important Goal Team 2 (“External Ministries Team 2”). | Strategic Planning Team and Goal co-Captains | 1 month after start date | External Ministries Team 2 members agree to serve
2. Identify definitions of “parishioner engagement” and “meaningful engagement” and levels of engagement with both lapsed St. Nicholas parishioners and non-Orthodox individuals. | External Ministries Team 2 | 1 month after step 1 | Engagement definitions determined
3. Research and identify metrics to determine effectiveness of External Ministries and how success will be determined based on the definitions in step 2. | External Ministries Team 2 | 1 month after step 2 | Effectiveness metrics determined
4. Identify at least 5 External Service Ministries and at least 5 Evangelism Ministries to evaluate and consider from both inside and outside the Orthodox ecosystem. | External Ministries Team 2 | Simultaneous with steps 2 and 3 | At least 5 External Service Ministries and 5 Evangelism Ministries are identified for study
LAG 2: Develop the most effective External Service Ministry & Evangelism Ministry within _4_ months |  |  | 
5. Research and analyze the St. Nicholas ministries’ baselines on those key engagement metrics identified in steps 2 and 3. | External Ministries Team 2 | 2 month after steps 3 & 4 | Analysis of St Nicholas baseline is completed
External Service & Evangelism Wildly Important Goal 2 Action Plan

## Slide 14
Key Actions Necessary To Achieve Strategic WIG 2 | Responsible Party | Deadline Timetable | Completion Confirmation Test
6. Evaluate the 5 External Service Ministries and 5 Evangelism Ministries identified in step 4 to determine their effectiveness and applicability to St. Nicholas based on definitions criteria of effectiveness and success determined in steps 2 and 3. | External Ministries Team 2 | Simultaneous with step 5 | Evaluation of alternative External Ministries is completed
7. Modify researched programs, or develop new elements, as necessary, to finalize the creation of official two St. Nicholas “External Ministries.” | External Ministries Team 2 | 2 months after steps 5 & 6 | St. Nicholas two External Ministries are finalized
LAG 3: Identify implementation modalities and processes and recruit External Ministry Teams within 3 months |  |  | 
8. Identify best implementation modalities (technology, ministries participants, etc.) to achieve the following “Targets”: (a) at least (i) 33% increase in parishioner meaningful engagement within 24 months; and (ii) 50% increase in parishioner meaningful engagement within 36 months; and (b) meaningful interaction with: (i) 100% of lapsed St. Nicholas parishioners; and (ii) at least 700 non-Orthodox individuals who interact with the parish, including through specific external evangelism activities. Recruit and train the parishioners who will implement the External Ministries (“External Ministries Disciples”). | External Ministries Team 2 | 1 month after step 7 | External Ministries Program delivery modalities determined, and External Ministries Disciples are recruited
External Service & Evangelism Wildly Important Goal 2 Action Plan

## Slide 15
Key Actions Necessary To Achieve Strategic WIG 2 | Responsible Party | Deadline Timetable | Completion Confirmation Test
9. Develop External Ministries implementation training programs, train External Ministries Disciples and prepare External Ministries delivery modalities and materials. | External Ministries Team 2 and External Ministries Disciples | 3 months after step 7 (and simultaneous with step 8) | External Ministries Disciples are trained, and all delivery modalities are set up and materials are prepared
LAG 4: Implement the External Ministries to achieve the Targets within 24 months |  |  | 
10. Implement the two External Ministries to achieve the Targets. | External Ministries Disciples | 24 months after step 9 | External Ministries are fully launched
11. Track and report on the achievement of the Targets on a monthly basis and implement improvements to External Ministries to overcome impediments to success. | External Ministries Team 2 and External Ministries Disciples | Concurrent with step 10 | Targets achievement are reported monthly and External Ministry improvements are implemented
LAG 5: Compile and assess the results of the External Ministries and make necessary improvements within _2_months |  |  | 
12. Obtain and compile qualitative and quantitative data from both External Ministries as to the effectiveness and success (based on criteria established in steps 2 and 3) and identify areas for improvement. | External Ministries Team 2 and External Ministries Disciples | 1 months after step 11 | Welcoming Ministry and Outreach & Evangelism Program assessments are compiled
13. Finalize and deliver both External Ministries assessment analysis report, make all refinements necessary to make those External Ministries more effective based on information identified in step 11, and revise and improve them accordingly. | External Ministries Team 2 and External Ministries Disciples | 1 months after step 12 | External Ministries implementation assessment analysis is completed, and External Ministries are refined accordingly
External Service & Evangelism Wildly Important Goal 2 Action Plan

## Slide 16
Lead Measure Action | Deadline Date | Status: Percent Complete and Date
1. Form External Ministries Team 2 | (1 month) _____-22 | 
2. Define meaningful engagement | (1 month) _____-22 | 
3. Research and identify metrics to determine effectiveness | (1 month) ____ -22 | 
4. Identify and evaluate alternative External Ministries | Simultaneous with steps 2 and 3) ___-22 | 
5. Research and analyze St. Nicholas External Ministries baseline | (2 months) ____-22 | 
6. Evaluate alternative External Ministries | Simultaneous with step 5) ___-22 | 
7. Finalize creation of both External Ministries | (2 months) ____-22 | 
8. Identify best implementation modalities | (1 month) ____-2 | 
9. Develop training programs and delivery modalities | (3 months from step 7) ____-23 | 
External Service & Evangelism Wildly Important Goal 2
Compelling Scoreboard

## Slide 17
Lead Measure Action | Deadline Date | Status: Percent Complete and Date
10. Implement the External Ministries | (24 months) ____-24 | 
11. Track and report on the achievement of the Targets and make necessary improvements | (simultaneous with step 11) ____-24 | 
12. Obtain and compile effectiveness data from External Ministries | (1 month) ____ -24 | 
13. Compile the results of the External Ministries effectiveness assessment and improve the External Ministries accordingly | (1 month) ____-24 | 
External Service & Evangelism Wildly Important Goal 2
Compelling Scoreboard

## Slide 18: Sample 3 Welcoming, Outreach & Evangelism

## Slide 19: Welcoming, Outreach & Evangelism Wildly Important Goal 3
Develop and implement within 23 months an effective:
(a) Welcoming Ministry in which 100% of visitors actively complete the parish comprehensive welcoming process; and
(b) Outreach & Evangelism Ministry that achieves a 20% increase in the number of engaged stewards from the prior year.

## Slide 20: Prelim Lag Measures WIG 3
LAG 1: Research the most effective Welcoming Ministry and Outreach & Evangelism Ministry within 3 months
LAG 2: Develop the most effective Welcoming Ministry and Outreach & Evangelism Ministry within 3 months
LAG 3: Identify the modalities, processes and procedures to welcome 100% of visitors and achieve the 20% engagement growth rate (collectively, the “Targets”) within 3 months
LAG 4: Implement the Welcoming Ministry and Outreach & Evangelism Ministry to achieve the Targets within 12 months
LAG 5: Compile and assess the results of the Welcoming and Outreach & Evangelism Ministry and make necessary improvements within 2 months
Ministries WIG 3:
“Develop and implement within 23 months an effective:
(a) Welcoming Ministry in which 100% of visitors complete the parish comprehensive welcoming process; and
(b) Outreach & Evangelism Ministry that achieves a 20% increase in the number of engaged stewards from the prior year.

## Slide 21: Prelim Lead Measures WIG 3
LEAD 1:
  A: recruit team
  B: research and identify metrics to determine effectiveness
  of welcoming and outreach and evangelism
  C: Identify at least 5 Welcoming Ministries and 5 Outreach & Evangelism Ministries to consider
LEAD 2:
  A: evaluate researched programs for effectiveness
  B: modify and/or develop Welcoming and Outreach & Evangelism Ministries for utilization at St. Demetrios
  C: finalize “Welcoming Ministry” and “Outreach & Evangelism Ministry” and effectiveness metrics
LEAD 3:
  A: identify implementation modalities (technology and ministry participants)
  B: develop ministry participant training program and ministry delivery modalities and materials
  C: recruit and train ministry participants
LEAD 4:
  A: implement the Welcoming Ministry and Outreach & Evangelism Ministry
  B: monthly track and report on the achievement of the Targets and identify how to overcome impediments to success
LEAD 5:
  A: obtain qualitative and quantitative data from Welcoming Ministry and Outreach & Evangelism Ministry effectiveness
  B: analyze all data and finalize Welcoming Ministry and Outreach & Evangelism Ministry assessment
  and make all necessary improvements
LAG 1: Research the most effective Welcoming Ministry and Outreach & Evangelism Ministry within 3 months
LAG 2: Develop the most effective Welcoming Ministry and Outreach & Evangelism Ministry within 3 months
LAG 3: Identify the processes and procedures to welcome 100% of visitors and achieve 20% increase in the number of engaged stewards (collectively, the “Targets”) from the prior year within 3 months
LAG 4: Implement the Welcoming Ministry and Outreach & Evangelism Ministry to achieve the Targets within 12 months
LAG 5: Compile and assess the results of the Welcoming and Outreach & Evangelism Ministries and make necessary improvements within 2 months

## Slide 22
Key Actions Necessary To Achieve Strategic WIG 3 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 1: Research the most effective Welcoming Ministry and Outreach & Evangelism Ministry within 3 months |  |  | 
1. Form Parish Wildly Important Goal Team 3 (W&OE Ministry Team 3). | Strategic Planning Team and Goal co-Captains | 1 month after start date | W&OE Ministry Team 3 members agree to serve
2. Research and identify definitions of engaged stewards, metrics to determine effectiveness and how success will be determined. | W&OE Ministry Team 3 | 2 months after start step 1 | Effectiveness metrics determined
3. Identify at least 5 Welcoming Ministries and at least 5 Outreach & Evangelism Ministries to evaluate and consider from both inside and outside the Orthodox ecosystem. | W&OE Ministry Team 3 | Simultaneous with step 2 | At least 5 Welcoming Ministries and Outreach & Evangelism Ministries are identified for study
LAG 2: Develop the most effective Welcoming and Outreach & Evangelism Ministries within 3 months |  |  | 
4. Analyze the parish baseline on those key welcoming and engagement effectiveness metrics and evaluate and study the Welcoming Ministries and Outreach & Evangelism Ministries identified in step 3 to determine their effectiveness and applicability to St. Demetrios based on criteria of effectiveness and success determined in step 2. | W&OE Ministry Team 3 | 1 month after step 3 | Evaluation of alternative Welcoming Ministries and Outreach & Evangelism Ministries is completed
5. Modify researched programs, or develop new elements, as necessary, to finalize the creation of official St. Demetrios Welcoming Ministry and Outreach & Evangelism Ministry. | W&OE Ministry Team 3 | 2 months after step 4 | Welcoming Ministry and Outreach & Evangelism Ministry is finalized

## Slide 23: Welcoming, Outreach & Evangelism Wildly Important Goal 3 Action Plan
Key Actions Necessary To Achieve Strategic WIG 3 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 3: Identify implementation modalities and processes and recruit Ministry Teams within 3 months |  |  | 
6. Identify best implementation modalities (technology, ministry participants, etc.) to achieve the 100% Welcoming Ministry and 20% Outreach & Evangelism Ministry “Targets” and recruit and train ministry participants (“W&OE Disciples”). | W&OE Ministry Team 3 | 1 months after step 5 | Welcoming Ministry and Outreach & Evangelism Ministry Program delivery modalities determined and W&OE Team are recruited
7. Develop Welcoming Ministry and Outreach & Evangelism Ministry implementation training programs and prepare ministry delivery modalities and materials. | W&OE Ministry Team 3 and W&OE Disciples | 3 months after step 5 (and concurrent with step 6) | W&OE Disciples are trained, and all delivery modalities are set up
LAG 4: Implement the Welcoming Ministry and Outreach & Evangelism Ministry Programs and Achieve the Targets within 12 months |  |  | 
8. Implement the Welcoming Ministry and Outreach & Evangelism Ministry to achieve the Welcoming and Outreach & Evangelism Targets. | W&OE Disciples | 12 months after step 7 | Achieve at least the Targets in welcoming and outreach & evangelism
9. Track and report on the achievement of the Targets on a monthly basis and implement improvements to Ministries to overcome impediments to success. | W&OE Ministry Team 3 and W&OE Disciples | Concurrent with step 8 | W&OE Target achievement is reported monthly and Ministry improvements are implemented

## Slide 24
Key Actions Necessary To Achieve Strategic WIG 3 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 5: Compile and assess the results of the Parish Welcoming Ministry and Outreach & Evangelism Ministry and make necessary improvements within 2 months |  |  | 
10. Obtain and compile qualitative and quantitative data from Welcoming Ministry and Outreach & Evangelism Ministry implementation as to the effectiveness and success (based on criteria established in step 2) and areas for improvement. | W&OE Ministry Team 3 and W&OE Disciples | 1 months after step 9 | Welcoming Ministry and Outreach & Evangelism Program assessments are compiled
11. Finalize and deliver Welcoming Ministry and Outreach & Evangelism Ministry assessment analysis report, make all refinements necessary to make those Ministries more effective based on information identified in step 10, and revise and improve them accordingly. | W&OE Ministry Team 3 and W&OE Disciples | 1 months after step 10 | Parish Welcoming Ministry and Outreach & Evangelism Ministry implementation assessment analysis is completed, and Ministries are refined accordingly
Welcoming, Outreach & Evangelism Wildly Important Goal 3 Action Plan

## Slide 25: Welcoming, Outreach & Evangelism Wildly Important Goal 3 Compelling Scoreboard
Lead Measure Action | Deadline Date | Status: Percent Complete and Date
1. Form W&OE Ministry Team 3 | (1 month) _____-21 | 
2. Research and Identify metrics to determine effectiveness | (2 months) ____ -21 | 
3. Research Welcoming Ministry and Outreach & Evangelism Ministry | Simultaneous with step 2) ______-21 | 
4. Evaluate Welcoming Ministry and Outreach & Evangelism Ministry Programs | (1 month) _____-21 | 
5. Finalize Welcoming Ministry and Outreach & Evangelism Ministry Programs | (2 months) ____-21 | 
6. Identify Delivery Best Implementation Modalities | (1 month) ____-22 | 
7. Train W&OE Team and Implement Delivery Modalities | (3 months from step 5) ____-22 | 
8. Implement the Welcoming Ministry and Outreach & Evangelism Ministry | (12 months) ____-22 | 

## Slide 26: Welcoming, Outreach & Evangelism Wildly Important Goal 3 Compelling Scoreboard
Lead Measure Action | Deadline Date | Status: Percent Complete and Date
9. Track and report on the achievement of the Targets on a monthly basis and make necessary improvements | (12 months) ____-22 | 
10. Obtain and compile effectiveness data from Welcoming Ministry and Outreach & Evangelism Ministry implementation | (1 month) ____ -22 | 
11. Compile the results of the Welcoming Ministry and Outreach & Evangelism Ministry effectiveness assessment and improve the Welcoming Ministry and Outreach & Evangelism Ministry accordingly | (1 month) ____-22 | 

## Slide 27: Sample 4 Welcoming, Outreach & Evangelism

## Slide 28: Welcoming, Outreach, In-reach, & Evangelism Wildly Important Goal 2
Develop and implement an effective youth and adult Welcoming, Outreach, In-reach, & Evangelism Ministries (the “WOI&E Ministries”) that within 36 months will achieve the following “Target Goals”:
(a) Welcoming Ministry in which 100% of visitors actively complete a comprehensive welcoming process;
(b) 52 or more unaffiliated Orthodox or non-Orthodox are welcomed in the parish each year; and
(c) In-reach Ministries will achieve a 20% or more increase in the number of youth and adults engaged in parish activities or ministries from the prior year.

## Slide 29: Welcoming, Outreach, In-reach, & Evangelism WIG 2 Lag Measures
LAG 1: Research the most effective youth and adult Welcoming, Outreach, In-reach, & Evangelism Ministries within 3 months
LAG 2: Develop the most effective Holy Trinity Welcoming, Outreach, In-reach, & Evangelism Ministries (the “WOI&E Ministries”) within 3 months
LAG 3: Identify the modalities, processes and procedures to achieve “Target Goals” in the WOI&E Ministries within 3 months
LAG 4: Implement the WOI&E Ministries to achieve the Target Goals within 24 months
LAG 5: Compile and assess the results of the WOI&E Ministries and make necessary improvements within 2 months
Ministries WIG 2:
Develop and implement an effective youth and adult Welcoming, Outreach, In-reach, & Evangelism Ministries (the “WOI&E Ministries”) that within 36 months will achieve the following “Target Goals”:
(a) Welcoming Ministry in which 100% of visitors actively complete a comprehensive welcoming process;
(b) 52 or more unaffiliated Orthodox or non-Orthodox are welcomed in the parish each year; and
(c) In-reach Ministries will achieve a 20% or more increase in the number of youth and adults engaged in parish activities or ministries from the prior year.

## Slide 30: Welcoming, Outreach, In-reach, & Evangelism WIG 2 Lead Measures
LEAD 1:
  A: Recruit team
  B: Research and identify definitions and metrics to determine effectiveness of youth and adult Welcoming, Outreach, In-reach, & Evangelism Ministries
  C: Identify 5 or more Welcoming Ministries and 5 or more ministries for each of the following: Outreach, In- Reach, & Evangelism Ministries to consider
LEAD 2:
  A: Evaluate researched programs for effectiveness
  B: Modify and/or develop final Welcoming, Outreach, In- reach, & Evangelism Ministries (the “WOI&E Ministries”) for utilization at Holy Trinity
  C: Finalize WOI&E Ministries effectiveness metrics
LEAD 3:
  A: Identify WOI&E Ministries implementation modalities and ministry participants (“WOI&E Disciples”).
  B: Develop WOI&E Disciples training program and delivery modalities and materials
  C: Recruit and train WOI&E Disciples
LEAD 4:
  A: Implement the WOI&E Ministries
  B: Track and report monthly, on the achievement of the Target Goals” and identify how to overcome impediments to success
LEAD 5:
A: Obtain qualitative and quantitative data from WOI&E Ministries effectiveness
B: Analyze all data and finalize WOI&E Ministries and make all necessary improvements
LAG 1: Research the most effective youth and adult Welcoming, Outreach, In-reach, & Evangelism Ministries within 3 months
LAG 2: Develop the most effective Holy Trinity Welcoming, Outreach, In-reach, & Evangelism Ministries (the “WOI&E Ministries”) within 4 months
LAG 3: Identify the modalities, processes and procedures to achieve “Target Goals” in the WOI&E Ministries within 3 months
LAG 4: Implement the WOI&E Ministries to achieve the Target Goals within 24 months
LAG 5: Compile and assess the results of the WOI&E Ministries and make necessary improvements within 2 months

## Slide 31: Welcoming Ministry and Outreach, In-Reach, and Evangelism WIG 2 Action Plan
Key Actions Necessary To Achieve Strategic WIG 2 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 1: Research the most effective Welcoming Ministry and Outreach, In-Reach, and Evangelism Ministries (the “WOI&E Ministries”) within 3 months |  |  | 
1. Form Welcoming, Outreach, In-reach, & Evangelism Ministries Team 2 (WOI&E Team 2). | Strategic Planning Team and Goal co-Captains | 1 month after start date | WOI&E Team 2 members agree to serve
2. Research and identify definitions of youth and adult welcoming, outreach, in-reach and evangelism and metrics to determine effectiveness and how success will be determined. | WOI&E Team 2 | 2 months after step one starts | Definitions and effectiveness metrics determined
3. Identify 5 or more Welcoming Ministries and 5 or more Outreach, In-Reach & Evangelism Ministries for both youth and adults to evaluate and consider from both inside and outside the Orthodox ecosystem. | WOI&E Team 2 | Simultaneous with step 2 | 5 or more Welcoming, Outreach, In-reach, & Evangelism Ministries are identified for study

## Slide 32: Welcoming Ministry and Outreach, In-Reach, and Evangelism WIG 2 Action Plan
Key Actions Necessary To Achieve Strategic WIG 2 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 2: Develop the most effective Welcoming ,Ministry and Outreach, In-Reach, and Evangelism Ministries within 4 months |  |  | 
4. Analyze the Holy Trinity baseline on key Welcoming, Outreach, In-reach, & Evangelism Ministries effectiveness metrics. Evaluate and study the Welcoming, Outreach, In-reach, & Evangelism Ministries identified in step 3 to determine their effectiveness and applicability to the Holy Trinity based on definitions and criteria of effectiveness and success determined in step 2. | WOI&E Team 2 | 1 month after step 3 | Evaluation of alternative Welcoming, Outreach, In-reach, & Evangelism Ministries are completed
5. Modify researched programs, or develop new programs or elements, as necessary, to finalize the creation of official Holy Trinity youth and adult Welcoming, Outreach, In-reach, & Evangelism Ministries (the “WOI&E Ministries”) | WOI&E Team 2 | 3 months after step 4 | Welcoming, Outreach, In-reach, & Evangelism Ministries are finalized

## Slide 33: Welcoming Ministry and Outreach, In-Reach, and Evangelism WIG 2 Action Plan
Key Actions Necessary To Achieve Strategic WIG 2 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 3: Identify implementation modalities and processes and recruit Welcoming, Outreach, In-reach, & Evangelism Ministries Teams within 3 months |  |  | 
6. Identify best implementation modalities (technology, ministry participants, etc.) to achieve the Target Goals and recruit and train Welcoming, Outreach, In-reach, & Evangelism Ministries participants (“WOI&E Disciples”). | WOI&E Team 2 | 1 month after step 5 | WOI&E Ministries Welcoming Ministry and Outreach, In-Reach & Evangelism Ministries Program, delivery modalities are determined, and WOI&E Disciples are recruited
7. Develop WOI&E Ministries implementation training programs and delivery modalities and materials and train WOI&E Disciples. | WOI&E Team 2 and WOI&E Disciples | 3 months after step 5 (and concurrent with step 6) | WOI&E Disciples are trained, and all delivery modalities are set up

## Slide 34: Welcoming Ministry and Outreach, In-Reach, and Evangelism WIG 2 Action Plan
Key Actions Necessary To Achieve Strategic WIG 2 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 4: Implement the Welcoming Ministry and Outreach, In-Reach & Evangelism Ministries Programs and Achieve the ”Intended” within 24 months |  |  | 
8. Implement the WOI&E Ministries to achieve the Target Goals | WOI&E Disciples | 24 months after step 7 | Achieve or exceed the Target Goals in welcoming and outreach & evangelism
9. Track and report on the achievement of the Target Goals on a monthly basis and implement improvements to WOI&E Ministries to overcome impediments to success. | WOI&E Team 2 and WOI&E Disciples | Concurrent with step 8 | WOI&E Target Goals achievement is reported monthly and WOI&E Ministries improvements are implemented

## Slide 35: Welcoming Ministry and Outreach, In-Reach, and Evangelism WIG 2 Action Plan
Key Actions Necessary To Achieve Strategic WIG 2 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 5: Compile and assess the results of the Holy Trinity WOI&E Ministries and make necessary improvements within 2 months |  |  | 
10. Obtain and compile qualitative and quantitative data from WOI&E Ministries implementation as to the effectiveness and success (based on criteria established in step 2) and areas for improvement. | WOI&E Team 2 and WOI&E Disciples | 1 month after step 9 | WOI&E Ministries assessments are compiled
11. Finalize and deliver WOI&E Ministries assessment analysis report, make all refinements necessary to make the WOI&E Ministries more effective based on information identified in step 10, and revise/improve them accordingly. | WOI&E Team 2 and WOI&E Disciples | 1 month after step 10 | WOI&E Ministries implementation assessment analysis is completed, and WOI&E Ministries are refined accordingly

## Slide 36: Welcoming, Outreach, In-Reach, & Evangelism WIG2 Compelling Scoreboard
Lead Measure Action | Deadline Date | Status: Percent Complete and Date
1. Form WOI&E Team 2 | 1 month _____-21 | 
2. Research and identify metrics to determine effectiveness | 2 months ____ -22 | 
3. Research Welcoming, Outreach, In-reach, & Evangelism Ministries | Simultaneous with step 2 ______-22 | 
4. Evaluate Welcoming, Outreach, In-reach, & Evangelism Ministries Programs | 1 month _____-22 | 
5. Finalize Welcoming, Outreach, In-reach, & Evangelism Ministries Programs | 3 months ____-22 | 
6. Identify Delivery Best Implementation Modalities | 1 month ____-22 | 
7. Train WOI&E Disciples and Implement Delivery Modalities | 3 months from step 5 ____-22 | 
8. Implement the WOI&E Ministries | 24 months ____-24 | 

## Slide 37: Welcoming, Outreach, In-Reach, & Evangelism WIG2 Compelling Scoreboard
Lead Measure Action | Deadline Date | Status: Percent Complete and Date
9. Track and report on the achievement of the “Target Goals” on a monthly basis and make necessary improvements | 12 months ____-24 | 
10. Obtain and compile effectiveness data from WOI&E Ministries implementation | 1 month ____ -24 | 
11. Compile the results of the WOI&E effectiveness assessment and improve accordingly | 1 month ____-24 | 

## Slide 38: Sample 5 Welcoming, Outreach & Evangelism

## Slide 39: Philanthropy, Outreach & Evangelism Goal 7.2 Outreach & Evangelism Ministry
Within 16 months, we will establish a vibrant Outreach and Evangelism Ministry, that within 8 months from formation will:
(a) recruit at least 100 parishioners to participate in Parish Outreach, and Evangelism ministries and partnerships;
(b) plan and execute at least one specific Parish Outreach and Evangelism Ministry event every four months, either alone or in partnership with another non-profit entity;
(c) define and successfully implement at least one re-occurring signature Outreach or Evangelism Ministry program or event.

## Slide 40: Outreach & Evangelism Ministry Goal 7.2 Action Plan
Specific Key Actions Necessary To Achieve Goal 7.2 | Who Must Do Each Action | Timetable: How Many Months or Days To Finish Action From Previous Action | How Will We Know When This Action Has Been Completed
1. Form Philanthropy, Outreach and Evangelism (“POE”) Goal 7.2 Task Force (“POE7.2TF”) . | Strategic Planning Team and Goal Captain | 1 month from Start Date | POE7.2TF team members agree to serve
2. Conduct comprehensive research to determine best-in-class Outreach and Evangelism methods, programs, activities, structure, success factors, volunteer recruitment strategies and effectiveness assessment tools from Orthodox, non-Orthodox and other non-profit organizations. | POE7.2TF | 4 months after step 1 | Outreach and Evangelism best practices report is completed
3. Develop a baseline inventory to identify: (a) all current and past Parish Outreach and Evangelism programs (and their perceived success); (b) other signature Outreach and Evangelism ministries and programs from other Christian or non-profit organizations which can either be copied or adapted or with whom partnerships can be established to pursue that ministry or program; and (c) outreach and evangelism-minded parishioners to help coordinate Outreach and Evangelism ministries and activities. | POE7.2TF | 4 months after step 2 | Outreach and Evangelism baseline inventory is completed

## Slide 41: Outreach & Evangelism Ministry Goal 7.2 Action Plan
Specific Key Actions Necessary To Achieve Goal 7.2 | Who Must Do Each Action | Timetable: How Many Months or Days To Finish Action From Previous Action | How Will We Know When This Action Has Been Completed
4. From among the many ideas generated from the research in steps 2-3, survey the community and conduct some interviews in order to determine what areas of Outreach and Evangelism programs, ministries, activities and partnerships are most important to the Parish and will obtain the greatest participation and positive results. | POE7.2TF | 4 months after step 3 | Parish Outreach and Evangelism survey information and interviews are collected
5. From all available resources, materials, research, surveys and interviews, identify, plan and obtain any necessary approvals for: (a) a quarterly schedule of Outreach and Evangelism events to be implemented by the Parish either alone or in partnership with another entity (the “Quarterly Outreach and Evangelism Events”); and (b) the most attractive Parish re-occurring signature Outreach and Evangelism program (the “Signature Outreach and Evangelism Program”); and develop strategy, budget, fundraising, mechanism, communications and implementation plan for all such Outreach and Evangelism programs, including dates, time and goals. . | POE7.2TF | 3 months after step 4 | Planning of recommended Quarterly Outreach and Evangelism Events and Signature Outreach and Evangelism Program is completed and ready for implementation

## Slide 42: Outreach & Evangelism Ministry Goal 7.2 Action Plan
Specific Key Actions Necessary To Achieve Goal 7.2 | Who Must Do Each Action | Timetable: How Many Months or Days To Finish Action From Previous Action | How Will We Know When This Action Has Been Completed
6. Present Quarterly Outreach and Evangelism Events and Signature Outreach and Evangelism Program to the Parish and continuously recruit until at least 100 parishioners participate in at least one of the Quarterly Outreach and Evangelism Events or Signature Outreach and Evangelism Program. | POE7.2TF | 8 months after step 5 | At least 100 Outreach and Evangelism volunteers are recruited and participate in at least one of the Quarterly Outreach and Evangelism Events or Signature Outreach and Evangelism Program
Successfully implement: (a) at least one Quarterly Outreach and Evangelism Event every 3 months; (b) the Signature Outreach and Evangelism Program annually; and (c) publicize successes and results of events every 3 months. | POE7.2TF | Concurrent with step 6 | Quarterly Outreach and Evangelism Events and Signature Outreach and Evangelism Program are executed on schedule
8. Implement the Outreach and Evangelism effectiveness assessment tool to manage on-going effectiveness of the all Quarterly Outreach and Evangelism Events and the Signature Outreach and Evangelism Program, ensure alignment with overall Parish vision, and make necessary adjustments and improvements. | POE7.2TF | After every Quarterly Outreach and Evangelism Event and Signature Outreach and Evangelism Program and at least annually continuously thereafter. | Signature Outreach and Evangelism Program is evaluated and revised as needed, and success is determined