## Slide 1: Philanthropy, Outreach & Evangelism Goal 7.1 Philanthropy Ministry
Within 16 months, we will establish a vibrant Philanthropy Ministry, that within 8 months from formation will:
(a) recruit at least 100 parishioners to participate in Parish Philanthropy Ministries and partnerships;
(b) plan and execute at least one specific Parish Philanthropy Ministry event every four months, either alone or in partnership with another non-profit entity;
(c) define and successfully implement at least one re-occurring signature Philanthropy Ministry program or event.

## Slide 2: Philanthropy Ministry Goal 7.1 Action Plan
Specific Key Actions Necessary To Achieve Goal 7.1 | Who Must Do Each Action | Timetable: How Many Months or Days To Finish Action From Previous Action | How Will We Know When This Action Has Been Completed
1. Form Philanthropy, Outreach and Evangelism (“POE”) Goal 7.1 Task Force (“POE7.1TF”) . | Strategic Planning Team and Goal Captain | 1 month from Start Date | POE7.1TF team members agree to serve
2. Conduct comprehensive research to determine best-in-class Philanthropy methods, programs, activities, structure, success factors, volunteer recruitment strategies and effectiveness assessment tools from Orthodox, non-Orthodox and other non-profit organizations. | POE7.1TF | 4 months after step 1 | Philanthropy best practices report is completed
3. Develop a baseline inventory to identify: (a) all current and past Parish Philanthropy programs (and their perceived success); (b) other signature Philanthropy ministries and programs from other Christian or non-profit organizations which can either be copied or adapted or with whom partnerships can be established to pursue that ministry or program; and (c) philanthropy-minded parishioners to help coordinate Philanthropy ministries and activities. | POE7.1TF | 4 months after step 2 | Philanthropy baseline inventory is completed

## Slide 3: Philanthropy Ministries Goal 7.1 Action Plan
Specific Key Actions Necessary To Achieve Goal 7.1 | Who Must Do Each Action | Timetable: How Many Months or Days To Finish Action From Previous Action | How Will We Know When This Action Has Been Completed
4. From among the many ideas generated from the research in steps 2-3, survey the community and conduct some interviews in order to determine what areas of Philanthropy programs, ministries, activities and partnerships are most important to the Parish and will obtain the greatest participation and positive results. | POE7.1TF | 4 months after step 3 | Parish Philanthropy survey information and interviews are collected
5. From all available resources, materials, research, surveys and interviews, identify, plan and obtain any necessary approvals for : (a) a quarterly schedule of Philanthropy events to be implemented by the Parish either alone or in partnership with another entity (the “Quarterly Philanthropy Events”); and (b) the most attractive Parish re-occurring signature Philanthropy program (the “Signature Philanthropy Program”); and develop strategy, budget, fundraising, mechanism, communications and implementation plan for all such Philanthropy programs, including dates, time and goals. . | POE7.1TF | 3 months after step 4 | Planning of recommended Quarterly Philanthropy Events and Signature Philanthropy Program is completed and ready for implementation

## Slide 4: Philanthropy Ministry Goal 7.1 Action Plan
Specific Key Actions Necessary To Achieve Goal 7.1 | Who Must Do Each Action | Timetable: How Many Months or Days To Finish Action From Previous Action | How Will We Know When This Action Has Been Completed
6. Present Quarterly Philanthropy Events and Signature Philanthropy Program to the Parish and continuously recruit until at least 100 parishioners participate in at least one of the Quarterly Philanthropy Events or Signature Philanthropy Program. | POE7.1TF | 8 months after step 5 | At least 100 Philanthropy volunteers are recruited and participate in at least one of the Quarterly Philanthropy Events or Signature Philanthropy Program
Successfully implement: (a) at least one Quarterly Philanthropy Event every 3 months; (b) the Signature Philanthropy Program annually; and (c) publicize successes and results of events every 3 months. | POE7.1TF | Concurrent with step 6 | Quarterly Philanthropy Events and Signature Philanthropy Program are executed on schedule
8. Implement the Philanthropy effectiveness assessment tool to manage on-going effectiveness of the all Quarterly Philanthropy Events and the Signature Philanthropy Program, ensure alignment with overall Parish vision, and make necessary adjustments and improvements. | POE7.1TF | After every Quarterly Philanthropy Event and Signature Philanthropy Program and at least annually continuously thereafter. | Signature Philanthropy, Program is evaluated and revised as needed, and success is determined