## Slide 1
Within 21 months, we will develop and implement an effective Small Group Program that within 3 years thereafter will include at least 100 of our families.
Life Stage Ministries
Goal 6.1 Small Groups

## Slide 2: Life Stage Ministries Goal 6.1 Action Plan
Specific Key Actions Necessary To Achieve Goal 6.1 | Who Must Do Each Action | Timetable: How Many Months or Days To Finish Action From Previous Action | How Will We Know When This Action Has Been Completed
Form Life Stage Ministries Goal 6.1 Task Force (“LSM6.1TF”). | LSM6.1TF | 1 month from start date | LSM6.1TF team members agree to serve
2. Conduct comprehensive research to find best practices in Small Group programs (including making site visits and interviews of those who have successfully implemented this program), and closely examine and investigate what has worked, what has not, what lessons have been learned and what resources are available to facilitate a Small Group Program, and specifically identify objective evidence of effectiveness. | LSM6.1TF | 3 months after steps 1 | All materials are researched including objective evidence of effectiveness
3. Qualitatively analyze and assess all researched Small Group program materials and resources, results of personal site visits and objective evidence of their effectiveness, and create a comprehensive list of topics and best in class content and best alternative methods for delivery and logistics. | LSM6.1TF | 2 months after step 3 | Complete comprehensive report of Small Group research and site visits analysis
4. Compile, distribute and process survey, interviews and data collection techniques to our community for input on willingness to participate in a Small Group, and obtain feedback on logistics, methodology to maximize attendance and participation, including desired topics, frequency, information and curriculum. | LSM6.1TF | 4 months after step 3 | Surveys returned and responses are compiled
5. Using all of the research compiled in steps 2 through 4, create a comprehensive “Small Group Program” and delivery schedule and methods and identify materials and curriculum gaps and the process and timeline for specifically filling such gaps, including who is responsible for achieving each step within the established timeline (“Gap Analysis Workplan”). | LSM6.1TF | 3 months after step 4 | Small Group Program Gap Analysis Workplan is complete

## Slide 3: Life Stage Ministries Goal 6.1 Action Plan
Specific Key Actions Necessary To Achieve Goal 6.1 | Who Must Do Each Action | Timetable: How Many Months or Days To Finish Action From Previous Action | How Will We Know When This Action Has Been Completed
6. Research, gather, revise, develop, and/or solicit the development of additional materials needed for missing areas, or areas that do not meet best practices or most effective standard as determined through Gap Analysis Workplan, and complete Small Group Program curriculum and process. | LSM6.1TF | 2 months after step 5 | Gap Analysis Workplan is executed and gaps are filled and Small Group Program curriculum and process is finalized
7. Recruit and train at least 5 Small Group leaders on how to most effectively lead small groups based on the Small Group Program. | LSM6.1TF | 3 month after step 6 | At least 5 Small Group Leaders agree to serve and are trained
8. Recruit sufficient parishioners to participate in at least 5 Small Groups to be formed by leaders trained in step 7 and provide them training on how the Small Group Program will be implemented. | LSM6.1TF | 2 months after step 7 | At least 5 Small Groups are formed and parishioners ate recruited and trained
9. Conduct pilot test of at least 5 Small Groups and conduct at least quarterly assessments of lessons learned and changes needed to ensure the greatest effectiveness and make appropriate improvements in Small Group Program. | LSM6.1TF and Small Group Program Leaders | Beginning 1 month after step 8 | Pilot test assessment is completed continued on at least a quarterly basis
10. Recruit and train additional Small Group leaders and expand recruitment of additional parishioners to participate in Small Group Program and continue to grow to achieve the target of at least 100 participating families. | LSM6.1TF and Small Group Program Leaders | Continuously occurring after step 9 | Additional Small Group Leaders and groups are formed until at least 100 families participate
11. Implement a regularly scheduled evaluation plan for reviewing the performance of all Small Groups and materials at least quarterly and make improvements based on results of evaluation to ensure that all materials are the most effective best practices available and the target of at least 100 participating families is achieved. | LSM6.1TF and Small Group Program Leaders | At least quarterly assessment | Evaluations occur and improvements are made in each element of Small Group Program