## Slide 1: Sample 1 Religious Education

## Slide 2: Religious Education S.M.A.R.T. Goal
Develop, distribute, and publish on extensive media outlets a wide variety of religious educational materials that achieve designated interaction metrics growing at least 10% per quarter (the “Online Program”);
(b) at least 90% of parish youth will complete a revamped full academic year “Youth Religious Formation and Education School Program” each year and achieve measurable outcomes identified in step 2 of the Action Plan;
(c) at least 50% of parish adults will complete a new “Adult Religious Formation and Education Program” each year and achieve measurable outcomes identified in step 2 of the Action Plan; and
(d) establish a quarterly dinner “Parish Life Education Program” with dynamic presenters in which at least an average of 25% of parishioners participate in each quarterly program during complete implementation year 1, and at least and average of 40% of parishioners participate in each quarterly program during complete implementation year 2.
We will research, develop, and implement best practices and effective adult and youth “Religious Education Programs” with a comprehensive communications plan that will achieve the following “Religious Education Targets ” within 36 months:

## Slide 3
Religious Education Action Plan
Actions Steps | Responsible Party | Deadline | Completion Test
Interim Goal 1: Research the most effective religious education programs within 4 months |  |  | 
1. Form Religious Education Team (RET) to develop and implement the “Religious Education Programs” consisting of the Online Program, Youth Sunday School Program, Adult Sunday School Program, and Parish Life Education Program. | SPT and RET Co-Captains | 1 month after Start Date | RET members agree to serve
2. Determine religious education key definitions and effectiveness metrics (to include specific deliver/open, view/read, completion/engagement metrics) that grow for adults and youth for each of the four Religious Education Programs. | RET | 2 months after step 1 | Religious Education Programs key Definitions and metrics determined
3. Analyze the parish baseline on those key religious education effectiveness metrics and survey parishioners to determine what religious education content they need and what delivery modalities they will use regularly. | RET | 1 month after step 2 | Parish baselines, and content delivery vehicle and frequency of religious education content is finalized
4. Identify several Online Programs, Youth Sunday School Programs, Adult Sunday School Programs, and Parish Life Education Programs to consider from both inside and outside the Orthodox ecosystem. | RET | Simultaneous with steps 2 & 3 | Multiple Religious Education Programs are researched and examined

## Slide 4
Actions Steps | Responsible Party | Deadline | Completion Test
Interim Goal 2: Develop the most effective Religious Education Programs within 4 months |  |  | 
5. Evaluate researched Religious Education Programs for effectiveness against key performance metrics and parish baselines based on criteria of effectiveness determined in step 2 and determine topics and modalities. | RET | 2 months after step 4 | Evaluation of alternative Religious Education Programs is completed
6. Modify or develop new Online Program, Youth Sunday School Program, Adult Sunday School Program, and Parish Life Education Program (the “Religious Education Programs”) and establish monthly performance benchmarks to achieve Religious Education Targets. | RET | 2 months after step 5 | Religious Education Programs are finalized, and monthly performance benchmarks are determined
Interim Goal 3: Recruit and train Educators within 2 months |  |  | 
7. Identify and recruit Religious Education Programs “Educators” who can implement the Religious Education Programs. | RET | 1 month after step 6 | Educators are recruited
8. Train Educators to implement the Religious Education Programs. | RET | 1 month after step 7 | Educators are trained
Religious Education Action Plan

## Slide 5
Actions Steps | Responsible Party | Deadline | Completion Test
Interim Goal 4: Implement the Religious Education Programs to achieve the Religious Education Targets within 24 months |  |  | 
9. Implement Religious Education Programs to achieve the Religious Education Targets. | Educators | 24 months after step 8 | Religious Education Programs are fully launched
10. Track and report on monthly performance benchmarks determined in step 6 and continue Educators follow-up with parishioners until Religious Education Targets are achieved. | Educators | Contemporaneous with step 9 | Established monthly Religious Education Targets are achieved
Religious Education Action Plan

## Slide 6
Actions Steps | Responsible Party | Deadline | Completion Test
Interim Goal 5: Compile and assess the results of the Religious Education Program and make necessary improvements within 2 months |  |  | 
11. Obtain and compile qualitative and quantitative data from Religious Education Programs and determine effectiveness and success (based on criteria established in step 2) and identify areas for improvement. | Educators and RET | 1 month after step 10 | Religious Education Program assessments are completed
12. Finalize and deliver Religious Education Programs assessment analysis report, and make all refinements necessary to make the Religious Education Programs more effective based on information identified in step 11. | Educators and RET | 1 month after step 11 | Analysis is completed, and Religious Education Programs is refined accordingly
Religious Education Action Plan

## Slide 7
Lead Measure Action | Deadline Date | % Complete and Date
1. Form Religious Education Programs Team |  | 
2. Develop definitions and effectiveness metrics |  | 
3. Analyze parish baselines and engagement success impediments |  | 
4. Research Religious Education Programs |  | 
5. Evaluate Religious Education Programs |  | 
6. Finalize Religious Education Programs |  | 
7. Identify and recruit Educators |  | 
8. Train Educators |  | 
9. Implement Religious Education Programs and manage to interim monthly targets |  | 
10. Track performance Data from Religious Education Programs Implementation |  | 
11. Obtain qualitative and quantitative assessment data from Religious Education Programs |  | 
12. Improve Religious Education Programs based lessons learned in step 11 |  | 
Religious Education Action Plan

## Slide 8: Sample 2 Religious Education

## Slide 9: Religious Education S.M.A.R.T. Goal
(a) At least 50% of parish youth in year 1, and at least 75% of parish youth in year 2, will complete a revamped full academic year “Youth Sunday School Ministry” and achieve measurable outcomes identified in step 2 of the Action Plan;
(b) At least an average of 15% of parishioners in year one, and at least 25% of parishioners in year 2, will participate in at least two new quarterly “Parish Life Education Ministry” dinner series with dynamic presenters and discussion groups (the “Parish Life Ministry”);
(c) A new “Small Group Ministry” will actively engage at least 3 small groups of parishioners meeting at least monthly in year 1, and at least 10 small groups of parishioners meeting at least monthly in year 2, where they will discuss spiritual growth, religious education, and personal growth topics;
(d) A bi-weekly adult “Bible Study Ministry” will be offered each year over four distinct modules of sessions live, via Zoom, and recorded with at least 15% of parishioners completing at least half of the four modules in year one, and at least 25% of parishioners completing at least three of the four modules in year two;
(e) A parish “Religious Education Media Center” will be created that engages at least 50% of parishioners at least weekly by providing on the parish website, email, text messaging and social media and other platforms at least 90 items of religious education and spiritual growth content over the course of each year with specific metrics of delivery, opening, viewing, reading, and engaging to be determined in step 2 of the Action Plan; and
(f) Within 12 months, the parish will implement a “Congregational Singing Ministry” to more fully engage parishioners in liturgical life by singing during the Divine Liturgy.
2. In addition to the above Religious Education Ministries, within 26 months, we will research and begin to implement some form of “Parochial School Ministry” which can include either creating a more engaging interactive partnership with the Holy Trinity Academy in Warren, Ohio, St. Constantine School in Houston, TX, some other Orthodox parochial school, or developing a separate parish plan for its own parochial school.
Within 36 months we will research, develop, and implement best practices and effective adult and youth “Religious Education Ministries” in each of the following six areas with a comprehensive communications plan where:
1. We will achieve the following “Religious Education Targets” for the Religious Education Ministries:

## Slide 10
Religious Education Action Plan – Part 1
Actions Steps | Responsible Party | Deadline | Completion Test
Interim Goal 1: Research the most effective Religious Education Ministries within 4 months |  |  | 
1. Form Religious Education Ministries Team (REMT). | SPT and REMT Co-Captains | 1 month after Start Date | REMT members agree to serve
2. Determine religious education key definitions and effectiveness metrics for adults and youth for each of the six SMART Goal religious education and spiritual growth objectives (collectively the “Religious Education Ministries”). | REMT | 2 months after step 1 | Religious Education Ministries key definitions and metrics determined for all six elements
3. Analyze the parish baseline on those key religious education effectiveness metrics and survey parishioners to determine what religious education content they need and what delivery modalities they will use regularly. | REMT | 1 month after step 2 | Parish baselines, and content delivery vehicle and frequency of religious education content is finalized
4. Identify at 2-3 of each of adult religious education, youth religious education, small group ministry, Bible study, media ministry, and congregational singing programs to consider from both inside and outside the Orthodox ecosystem. | REMT | Simultaneous with steps 2 & 3 | At least 2-3 alternatives of each of the six elements of the Religious Education Ministry are examined

## Slide 11
Actions Steps | Responsible Party | Deadline | Completion Test
Interim Goal 2: Develop the most effective Religious Education Ministries within 4 months |  |  | 
5. Evaluate all the researched Religious Education Ministries items from step 4 for effectiveness against key performance metrics and parish baselines based and criteria of effectiveness determined in step 2 and determine religious education topics, programs, and modalities. | REMT | 2 months after step 4 | Evaluation of alternative Religious Education Ministries is completed
6. Develop new Youth Sunday School Ministry, Parish Life Ministry, Small Group Ministry, Bible Study Ministry, Religious Education Media Center, and Congregational Singing Ministry, (collectively, the “Religious Education Ministries”) and establish monthly performance benchmarks to achieve each of the Religious Education Targets. | REMT | 2 months after step 5 | Religious Education Ministries are finalized, and monthly performance benchmarks are determined
Interim Goal 3: Recruit and train Religious Educators Leaders within 2 months |  |  | 
7. Identify and recruit Religious Education Ministries “Educators” who can teach and implement each of the Religious Education Ministries | REMT | 1 month after step 6 | Educators are recruited
8. Train Educators to implement the Religious Education Ministries. | REMT | 1 month after step 7 | Educators are trained
Religious Education Action Plan – Part 1

## Slide 12
Actions Steps | Responsible Party | Deadline | Completion Test
Interim Goal 4: Implement the Religious Education Ministry to achieve the Religious Education Targets within 24 months |  |  | 
9. Implement Religious Education Ministries to achieve the Religious Education Targets. | Educators | 24 months after step 8 | Religious Education Ministries are fully launched
10. Track and report on monthly performance benchmarks determined in step 6 and continue Educators follow-up with parishioners until Religious Education Targets are achieved. | Educators | Contemporaneous with step 9 | Established monthly Religious Education Targets are achieved
Religious Education Action Plan – Part 1

## Slide 13
Actions Steps | Responsible Party | Deadline | Completion Test
Interim Goal 5: Compile and assess the results of the Religious Education Ministry and make necessary improvements within 2 months |  |  | 
11. Obtain and compile qualitative and quantitative data from Religious Education Ministries and determine effectiveness and success (based on criteria established in step 2) and identify areas for improvement. | Educators and REMT | 1 month after step 10 | Religious Education Ministry assessments are completed
12. Finalize and deliver Religious Education Ministries assessment analysis report, and make all refinements necessary to make the Religious Education Ministries more effective based on information identified in step 11. | Educators and REMT | 1 month after step 11 | Analysis is completed, and Religious Education Ministry is refined accordingly
Religious Education Action Plan – Part 1

## Slide 14
Parochial School Action Plan – Part 2
Actions Steps | Responsible Party | Deadline | Completion Test
Interim Goal 1: Research interest in Parochial School and alternatives within 9 months |  |  | 
1. Form Parochial School Team (PST). | SPT and PST Co-Captains | 1 month after Start Date | PST members agree to serve
2. Determine Parochial School (PS) desired outcomes and effectiveness metrics. | PST | 2 months after step 1 | PS metrics determined
3. Survey and analyze parish interest in developing some form of PS solution and optimum alternative approaches. | PST | 2 months after step 2 | Parish interest in PS and alternatives are determined
4. Assuming sufficient interest in step 3, identify at least 3-5 existing parochial schools to examine, including Holy Trinity Academy in Warren, Ohio, and St. Constantine School in Houston, TX. Conduct site visits and interviews with all such schools, their administration and Boards and conduct due diligence. Research specific action plan to develop a parish PS strategy. | PST | 4 months after step 3 | Several alternative PS models are diligenced along with the necessary steps to develop the parish’s PS strategy.

## Slide 15
Actions Steps | Responsible Party | Deadline | Completion Test
Interim Goal 2: Develop the most effective PS alternative within 9 months |  |  | 
5. Evaluate all the researched parochial school alternatives and develop a specific proposal and submit it to the parish for approval. | PST | 3 months after step 4 | Evaluation of alternative PS alternatives and proposal submitted to the parish for approval
6. If a separate PS is approved by the parish, select initial Board of Directors (Board) and Headmaster and crate a strategic, operational and financial plan for the preferred PS alternative. | PST | 6 months after step 5 | PS Board and Headmaster selected, and strategic, operational and financial plan developed
Interim Goal 3: Implement Plan to be prepared for opening within 6 months |  |  | 
7. Implement strategic, operational, and financial plan to prepare for opening of preferred PS alternative in time for the next available academic year opportunity. | Board and Headmaster | 6 months after step 6 | PS alternative opened
8. Track and report on monthly performance benchmarks determined in strategic, operational, and financial plan. | Board and Headmaster | Each month during PS operation | Monthly reports of progress released
Interim Goal 4: Compile and assess the results of the PS and make necessary improvements within 2 months |  |  | 
9. Obtain and compile qualitative and quantitative data of PS effectiveness, identify areas for improvement, and make all refinements necessary. | Board and Headmaster | At least annually | Assessment and remediation plans created and implemented
Parochial School Action Plan – Part 2

## Slide 16
Lead Measure Action | Deadline Date | % Complete and Date
1. Form Religious Education Ministry Team |  | 
2. Develop definitions and effectiveness metrics |  | 
3. Analyze parish baselines and engagement success impediments |  | 
4. Research Religious Education Ministries |  | 
5. Evaluate Religious Education Ministries |  | 
6. Finalize Religious Education Ministries |  | 
7. Identify and recruit Educators |  | 
8. Train Educators |  | 
9. Implement Religious Education Ministries and manage to interim monthly targets |  | 
10. Track performance Data from Religious Education Ministries Implementation |  | 
11. Obtain qualitative and quantitative assessment data from Religious Education Ministries |  | 
12. Improve Religious Education Ministries based lessons learned in step 11 |  | 
Religious Education Action Plan

## Slide 17: Sample 3 Religious Education

## Slide 18: Adult, Young Adult & Youth Religious Education & Liturgical Engagement SMART Goal 1
We will research, develop, and implement a best-practices, effective Adult and Youth “Religious Education, Prayer Life & Church Services Engagement” that will achieve the following “Education & Engagement Targets” within 24 months:
(a) Education
at least 25% of adult parishioners complete a new four-part series of Orthodoxy Education 6-8-week programs;
at least 25% of young adult parishioners (aged 18-30) complete new Orthodoxy Education programs;
(iii) at least 90% of youth parishioners complete a revamped full academic year Sunday School program starting 2023 academic year;
(b) Liturgical Engagement
(i)at least 50% of all parishioners will participate in an age- appropriate “Prayer Life Initiative” and achieve at least a 50% improvement in their prayer life practice; and
(ii) engagement of all parishioners in church services is increased by at least 75%.

## Slide 19: SMART Goal Lags 1
LAG 1: Research the most effective Adult, Young Adult & Youth Religious Education, Prayer Life & Church Services Engagement Programs within 4 months
LAG 2: Develop the most effective “Education & Engagement Program” for adults, young adults, and youth within 4 months
LAG 3: Identify delivery modalities and recruit and train the Education & Engagement Program “Educators” within 2 months
LAG 4: Deliver the Education & Engagement Program to at least achieve the outlined Education & Engagement Targets within 12 months
LAG 5: Compile and assess the results of the Education & Engagement Program and make necessary improvements within 2 months

## Slide 20: SMART Goal Leads 1
LEAD 1:
  A: recruit team
  B: research, define and identify metrics to determine effectiveness, baselines, parishioner desires and what constitutes measurable improvement success
  C: identify at least 3 adult, young adult, and youth religious education, (including prayer life enhancement) & church services engagement programs to consider
LEAD 2:
  A: evaluate researched education & engagement programs, and benchmark existing parish education & engagement programs, for effectiveness against Lead 1B definitions and standards
  B: modify and/or develop new education & engagement programs for utilization and create parish Education & Engagement Program to achieve Education & Engagement Targets
  C: finalize parish “Education & Engagement Program” and effectiveness measurement metrics
LEAD 3:
  A: identify delivery modalities, technology, and “Educators”
  B: develop Educator training program, delivery modalities, and interim effectiveness assessment process
  C: recruit and train Educators
LEAD 4:
  A: identify, recruit and educate Parish adults, young adults, and youth into the Education & Engagement Program B: assign Educators to respective adults, young adults and youth, as necessary
  B: schedule and complete a parish implementation of the Education & Engagement Program to achieve the Education & Engagement Targets
LEAD 5:
  A: obtain qualitative and quantitative data from Education & Engagement Program effectiveness
  B: analyze all data and finalize and deliver Education & Engagement Program assessment and make all necessary improvements to Education & Engagement Program

## Slide 21
Key Actions Necessary To Achieve SMART Goal 1 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 1: Research the most effective Education & Engagement Programs within 4 months |  |  | 
1. Form Parish SMART Goal Team 1 (“Education & Engagement Ministry Team 1”). | Strategic Planning Team and Goal co-Captains | 1 month after start date | Education & Engagement Ministry Team 1 members agree to serve
2. Research, define and identify metrics to determine effectiveness and what constitutes “measurable improvement” success for each targeted demographic of youth and adults in each “Education & Engagement Programs.” Survey parishioners’ religious education, prayer life & church services engagement needs and desires. Identify specific curriculum to help parishioners better make personal transitions through their lives. | Education & Engagement Ministry Team 1 | 3 months after step 1 | Success and effectiveness metrics are finalized
3. Identify at least 3 Adult/Young Adult and 3 Youth Education & Engagement programs to evaluate and consider from both inside and outside the Orthodox ecosystem. | Education & Engagement Ministry Team 1 | Simultaneous with step 2 | At least 3 Education & Engagement training programs are identified for study for each demographic
Adult, Young Adult & Youth Education & Engagement SMART Goal 1 Action Plan

## Slide 22
Key Actions Necessary To Achieve SMART Goal 1 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 2: Develop the most effective Education & Engagement Program within 4 months |  |  | 
4. Using the step 2 criteria of effectiveness and measurable improvement success: (a) evaluate and study the education & engagement programs identified in step 3: (b) baseline the effectiveness of the existing parish adult and youth education & engagement programs; (c) assess parishioner program desires. |  | 1 month after step 3 | Evaluation of alternative religious education & liturgical engagement Programs and parish existing programs is completed
5. Modify researched or existing programs, or develop new curriculum, as necessary, to finalize the creation of official parish Adult and Youth “Education & Engagement Program” for use. Identify potential “Educators” who can teach the Education & Engagement Program. And establish quarterly evaluation of success performance benchmarks. | Education & Engagement Ministry Team 1 | 3 months after step 4 | Adult and Youth Education & Engagement Program is finalized, and Educators are identified
Adult, Young Adult & Youth Education & Engagement SMART Goal 1 Action Plan

## Slide 23: Adult, Young Adult & Youth Education & Engagement SMART Goal 1 Action Plan
Key Actions Necessary To Achieve SMART Goal 1 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 3: Identify delivery modalities and recruit and train the Education & Engagement Program Educators within 2 months |  |  | 
6. (a) identify the best ways to deliver the Adult Education & Engagement Programs; (b) identify delivery modalities and materials (small groups, technology, live education, etc.); (c) recruit potential Educators; and (d) schedule training for Educators. | Education & Engagement Ministry Team 1 | 1 month after step 5 | Education & Engagement Program delivery modalities determined, and Educators are recruited and trained
7. (a) Develop training program for Educators; (b) determine interim quarterly effectiveness assessment measurement process to ultimately achieve Education & Engagement Targets; (c) train the Educators selected in step 6; and (d) implement and establish all delivery modalities and materials. | Education & Engagement Ministry Team 1 | 2 months after step 5 (concurrent with step 6) | Educators are trained in training program, interim assessment process determined, and all delivery modalities are set up
LAG 4: Deliver the Education & Engagement Program to at least Education & Engagement Targets of adults and youth over 12 months |  |  | 
8. Identify, recruit, and educate “Education & Engagement Target” numbers of Parish adult and youth parishioners in each Education & Engagement Program. | Educators and Education & Engagement Ministry Team 1 | Concurrent with step 7 | At least the Education & Engagement Target numbers of Adult and Youth Parishioners participate in the Education & Engagement Program

## Slide 24
Key Actions Necessary To Achieve SMART Goal 1 | Responsible Party | Deadline Timetable | Completion Confirmation Test
9. Over 12 months, at least the Education & Engagement Target numbers of (a) Adult and Young Adult Parishioners complete the Orthodoxy Education Programs, Prayer Life Program; (b) report the liturgical engagement target and (c) youth complete the new Sunday School Program. | Educators | 12 months after steps 7 & 8 | Education & Engagement Program is implemented to at least the Target number of Parishioners
LAG 5: Compile and assess the results of the Parish Education & Engagement Program and make improvements within 2 months |  |  | 
10. Obtain and compile qualitative and quantitative data from Parish Education & Engagement Program implementations as to the effectiveness and success of the Education & Engagement Program (based on criteria established in step 2) and identify areas for improvement. | Educators and Education & Engagement Ministry Team 1 | 1 month after step 9 | Parish Education & Engagement Program implementation assessments are compiled
11. Finalize and deliver Education & Engagement Program effectiveness assessment analysis and make all refinements necessary to make the Education & Engagement Program more effective based on information identified in step 10, and revise and improve the Education & Engagement Program accordingly. | Educators and Education & Engagement Ministry Team 1 | 1 month after step 10 | Education & Engagement Program implementation assessment analysis are completed Programs are refined accordingly
Adult, Young Adult & Youth Education & Engagement SMART Goal 1 Action Plan

## Slide 25: Adult, Young Adult & Youth Education & Engagement Goal 1 Scoreboard
Lead Measure Action | Deadline Date | Status: Percent Complete and Date
1. Form Education & Engagement Ministry Team 1 |  | 
2. Research and Identify metrics to determine effectiveness and success |  | 
3. Research Education & Engagement Programs |  | 
4. Evaluate Education & Engagement Programs |  | 
5. Finalize Parish Education & Engagement Program |  | 
6. Identify delivery modalities and Educators |  | 
7. Train Educators and implement delivery modalities |  | 
8. Recruit Adults, Young Adult and Youth to participate in Education & Engagement Program |  | 
9. Implement Education & Engagement Program to Education & Engagement Target numbers or adults, young adults, and youth |  | 
10. Obtain and compile effectiveness data from Education & Engagement Program implementation |  | 
11. Compile the results of the Education & Engagement Program effectiveness assessment and improve the Education & Engagement Program accordingly |  | 

## Slide 26: Sample 4 Religious Education

## Slide 27: Adult & Youth Education S.M.A.R.T. Goal 1
Measurably improve parishioner understanding of the Orthodox Faith over the next 24 months by researching, developing, implementing and evaluating a best-practices Adult and Youth Orthodox education program (the “Education Programs”) that will achieve the following “Education Targets:”
at least 75% of adult parishioners are aware of the new Education Programs;
at least 33% of all adult parishioners complete at least one of the variety of Orthodoxy introduction, intermediate, or advanced multiple session Educational Programs series;
a quarterly religious Education Program with external speakers is provided beginning after Pascha 2023; and
over the course of a youth education program year, at least 50% of youth parishioners will consistently attend and complete a new or revised “Youth Education Program” including Youth Sunday School.

## Slide 28: Adult & Youth Education Lags – Goal 1
LAG 1: Research the most effective adult & youth education programs within 4 months
LAG 2: Develop the most effective adult and youth Orthodox “Education Programs” within 4 months
LAG 3: Identify delivery modalities and recruit and train the Education Programs “Educators” within 2 months
LAG 4: Deliver the Education Programs to at least achieve the outlined Education Targets within 12 months
LAG 5: Compile and assess the results of the Education Programs and make necessary improvements within 2 months

## Slide 29: Adult & Youth Education Leads – Goal 1
LEAD 1:
  A: recruit team
  B: research, define and identify metrics to determine effectiveness and what constitutes measurable improvement success
  C: identify at least 3 adult and youth education programs to consider and establish current baselines
LEAD 2:
  A: evaluate researched education programs, and benchmark existing Holy Trinity education programs, for effectiveness against Lead 1B definitions and standards
  B: modify and/or develop new education programs for utilization and create Holy Trinity “Education Programs” to achieve Education Targets
  C: finalize Holy Trinity Education Programs and effectiveness measurement metrics
LEAD 3:
  A: identify delivery modalities (technology and “Educators”)
  B: develop Educator training program, delivery modalities and interim effectiveness assessment process
  C: recruit and train Educators
LEAD 4:
  A: identify, recruit and educate Parish adults and youth in the Education Programs to achieve the Education Targets
  B: assign Educators to respective adults and youth, as necessary
  C: schedule and complete a parish implementation of the Education Programs to all Education Target number of adults and youth
LEAD 5:
  A: obtain qualitative and quantitative data from Education Programs effectiveness
  B: analyze all data and finalize and deliver Education Program assessment and make all necessary improvements to Education Programs

## Slide 30
Key Actions Necessary To Achieve Strategic Goal 1 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 1: Research the most effective Education Programs within 4 months |  |  | 
1. Form Parish Youth and Adult SMART Goal Team 1 (“Education Ministry Team 1”). | Strategic Planning Team and Goal co-Captains | 1 month after start date | Education Ministry Team 1 members agree to serve
2. Research, define and identify metrics to determine effectiveness and what constitutes “measurable improvement” success for each targeted demographic of youth and adults and the different Orthodoxy 101, 201, 301, and quarterly, adult educational programs. Survey parishioners’ religious education needs and identify dynamic presenters. | Education Ministry Team 1 | 3 months after step 1 | Success and effectiveness metrics are finalized
3. Identify at least 3 Adult and 3 Youth Education programs from both inside and outside the Orthodox ecosystem to evaluate and consider. | Education Ministry Team 1 | Concurrent with step 2 | At least 3 education training programs are identified for study
Adult & Youth Education S.M.A.R.T. Goal 1 Action Plan

## Slide 31
Key Actions Necessary To Achieve Strategic Goal 1 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 2: Develop the most effective Education Programs within 4 months |  |  | 
4. Using the step 2 criteria of effectiveness and measurable improvement success: (a) evaluate and study the education programs identified in step 3: (b) baseline the effectiveness of the existing Holy Trinity adult and youth education programs; (c) assess parishioner program desires; and (d) develop communications plan regarding all Education Program(s). |  | 4 months after step 3 | Evaluation of alternative education programs and Holy Trinity existing programs are completed
5. Modify researched or existing programs, or develop new curriculum, as necessary, to finalize the creation of official Holy Trinity Adult and Youth “Education Programs” for use. Identify potential “Educators” who can teach the Education Programs. | Education Ministry Team 1 | Concurrent with step 4 | Adult and Youth Education Programs are finalized, and Educators are identified
Adult & Youth Education S.M.A.R.T. Goal 1 Action Plan

## Slide 32
Key Actions Necessary To Achieve Strategic Goal 1 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 3: Identify delivery modalities and recruit and train the Education Programs Educators within 2 months |  |  | 
6. (a) identify the best ways to deliver the Adult Education Programs; (b) identify delivery modalities and materials (technology, live education, etc.); (c) recruit potential Educators; and (d) schedule training for Educators; (e) begin communications about the launch of the specific Adult Education Programs. | Education Ministry Team 1 | 1 month after step 5 | Education Programs delivery modalities determined, and Educators are recruited and trained
7. (a) Develop training program for Educators; (b) determine interim quarterly effectiveness assessment measurement process to ultimately achieve Education Targets; (c) train the Educators selected in step 6; and (d) implement and establish all delivery modalities and materials. | Education Ministry Team 1 | 2 months after step 5 (concurrent with step 6) | Educators are trained in Education Programs, interim assessment process determined, and all delivery modalities are set up
LAG 4: Deliver the Education Programs to at least Education Targets of adults and youth over 12 months |  |  | 
8. Identify, recruit, and educate “Education Target” numbers of Parish adult and youth parishioners to participate in each of the Adult Education Programs. | Educators and Education Ministry Team 1 | Concurrent with step 7 | At least the Education Target numbers of Adult and Youth Parishioners participate in the Education Programs
Adult & Youth Education S.M.A.R.T. Goal 1 Action Plan

## Slide 33
Key Actions Necessary To Achieve Strategic Goal 1 | Responsible Party | Deadline Timetable | Completion Confirmation Test
9. At least the Education Target numbers of: (a) Adult Education Programs and quarterly Education Programs; and (b) youth complete at least one full year of new youth Education Programs. | Educators | 12 months after steps 7 & 8 | Education Programs is implemented to at least the Target number of Parishioners within the 12 months
LAG 5: Compile and assess the results of the Parish Education Programs and make necessary improvements within 2 months |  |  | 
10. Obtain and compile qualitative and quantitative data from Parish Education Programs implementations as to the effectiveness and success of the Education Programs (based on criteria established in step 2) and identify areas for improvement. | Educators and Education Ministry Team 1 | 1 months after step 9 | Parish Education Programs implementation assessments are compiled
11. Finalize and deliver Education Programs effectiveness assessment analysis and make all refinements necessary to make the Education Programs more effective based on information identified in step 10, and revise and improve the Education Programs accordingly. | Educators and Education Ministry Team 1 | 1 months after step 10 | Education Programs implementation assessment analysis are completed Programs are refined accordingly
Adult & Youth Education S.M.A.R.T. Goal 1 Action Plan

## Slide 34: Adult & Youth Education Goal 1 Scoreboard
Lead Measure Action | Deadline Date | Status: Percent Complete and Date
1. Form Education Ministry Team 1 |  | 
2. Research and Identify metrics to determine effectiveness and success |  | 
3. Research adult and youth education programs |  | 
4. Evaluate adult and youth education programs |  | 
5. Finalize Parish Education Programs |  | 
6. Identify delivery modalities and Educators |  | 
7. Train Educators and implement delivery modalities |  | 
8. Recruit Adults and Youth to participate in Education Programs |  | 
9. Implement Education Programs to Education Target numbers or adults and youth |  | 
10. Obtain and compile effectiveness data from Education Programs implementation |  | 
11. Compile the results of the Education Program effectiveness assessment and improve the Education Program accordingly |  | 

## Slide 35: Sample 5 Religious Education

## Slide 36: Adult & Youth Religious Education and Liturgical Engagement Wildly Important Goal 3
Develop and implement an effective Religious Education and Liturgical Engagement (“RELE”) Program for youth and adults that will be completed within 20 months by the following “Education Targets”:
  25% or more of parish adults; and
  75% or more of parish youth;
  50% or more of unaffiliated Orthodox or non-Orthodox are fully welcomed by the parish.

## Slide 37: Adult & Youth RELE Lag Measures WIG 3
LAG 1: Research the most effective adult and youth Religious Education and Liturgical Engagement (“RELE Program”) within 3 months
LAG 2: Develop the most effective RELE Program for Holy Trinity adults and youth (the “RELE Program ”) within 3 months
LAG 3: Identify delivery modalities and recruit and train the RELE Program “Educators” within 3 months
LAG 4: Deliver the RELE Program to the Education Targets within 9 months
LAG 5: Compile and assess the results of the RELE Program and make necessary improvements within 2 months
Adult & Youth RELE WIG 3:
Develop and implement an effective Religious Education and Liturgical Engagement (“RELE”) Program for youth and adults that will be completed within 20 months by the following “Education Targets”:
  25% or more of parish adults; and
  75% or more of parish youth.
  50% or more of unaffiliated Orthodox or non-Orthodox are fully welcomed by the parish.

## Slide 38: Adult & Youth RELE Lead Measures WIG 3
LEAD 1:
  A: recruit team
  B: define how RELE success will be determined research and identify metrics to determine effectiveness and success for both adults and youth
  C: Identify 5 or more Religious Education and 5 or more Liturgical Engagement Programs to consider
LEAD 2:
  A: evaluate all RELE Programs for effectiveness
  B: modify and/or develop RELE Programs for utilization at Holy Trinity
  C: finalize “RELE Programs” and effectiveness measurement metrics
LEAD 3:
  A: identify RELE delivery modalities technology and “Educators”
  B: develop RELE Educator training program, delivery modalities and interim effectiveness assessment process
  C: recruit and train Educators
LEAD 4:
  A: identify, recruit and educate the “Education Targets ” of parish adults and youth in the RELE Programs
  B: assign Educators to respective adults and youth
  C: schedule and complete a parish implementation of the RELE Programs to all Education Targets of adults and youth
LEAD 5:
  A: obtain qualitative and quantitative data from RELE Programs effectiveness
  B: analyze all data and finalize and deliver RELE Programs assessment and make all necessary improvements
LAG 1: Research the most effective youth and adult Religious Education and Liturgical Engagement (“RELE Program”) within 3 months
LAG 2: Develop the most effective RELE Program for Holy Trinity youth and adults (the “RELE Program”) within 3 months
LAG 3: Identify delivery modalities and recruit and train the RELE Program “Educators” within 3 months
LAG 4: Deliver the RELE Program to the Education Targets or more of adult stewards and youth within 9 months
LAG 5: Compile and assess the results of the RELE Program and make necessary improvements within 2 months

## Slide 39: Adult & Youth RELE WIG 3 Action Plan
Key Actions Necessary To Achieve Strategic WIG 3 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 1: Research the most effective RELE Program within 3 months |  |  | 
1. Form parish Religious Education and Liturgical Engagement (“RELE”) Team 3 (“RELE Team 3”). | Strategic Planning Team and Goal co-Captains | 1 month after start date | RELE Team 3 members agree to serve
2. Research and define how RELE success will be determined for each targeted demographic of adults and youth and identify metrics to determine effectiveness. | RELE Team 3 | 2 months after step 1 | Success and effectiveness metrics are finalized
3. Identify 5 or more Religious Education and 5 or more Liturgical Engagement Programs for both adults and youth to evaluate and consider from both inside and outside the Orthodox ecosystem. | RELE Team 3 | Simultaneous with step 2 | 5 or more Religious Education and 5or more Liturgical Engagement training programs are identified for study

## Slide 40: Adult & Youth RELE WIG 3 Action Plan
Key Actions Necessary To Achieve Strategic WIG 3 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 2: Develop the most effective RELE Program within 3 months |  |  | 
4. Evaluate and study the RELE Programs identified in step 3 to determine their effectiveness and applicability to Holy Trinity based on criteria of effectiveness and success determined in step 2. | RELE Team 3 | 1 month after step 3 | Evaluation of alternative RELE Programs is completed
5. Modify researched RELE programs, or develop new curriculum or programs, as necessary, to finalize the creation of official Holy Trinity adult and youth RELE Program for use. Identify potential “Educators” who can teach the RELE Program to each age demographic. | RELE Team 3 | 2 months after step 4 | Adult and Youth RELE Program is finalized

## Slide 41: Adult & Youth RELE WIG 3 Action Plan
Key Actions Necessary To Achieve Strategic WIG 3 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 3: Identify delivery modalities and recruit and train the RELE Program Educators within 3 months |  |  | 
6. (a) identify the best ways to deliver the RELE Program for both adults and youth; (b) identify delivery modalities and materials (technology, live education, etc.); (c) recruit potential Educators for each age demographic; and (d) schedule training for Educators. | RELE Team 3 | 1 months after step 5 | RELE Program delivery modalities determined, and Educators are recruited and trained
7. (a) Develop RELE training program for Educators; (b) determine interim effectiveness assessment measurement process; (c) train the Educators selected in step 6; and (d) implement and establish all delivery modalities and materials. | RELE Team 3 | 3 months after step 5 (concurrent with step 6) | Educators are trained in RELE training program, interim assessment process determined, and all delivery modalities are set up

## Slide 42: Adult & Youth RELE WIG 3 Action Plan
Key Actions Necessary To Achieve Strategic WIG 3 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 4: Deliver the RELE Program to the Education Targets or more of adults and youth within 9 months |  |  | 
8. Identify, recruit and educate the “Education Targets” or more of parish adults and youth in each targeted demographic in the RELE Program. | Educators and RELE Team 3 | Concurrent with step 7 | The Education Targets of Adult and Youth Parishioners or more participate in the RELE Program
9. The Education Target numbers or more of adults and youth in each targeted demographic will complete the RELE Program. | Educators | 9 months after steps 7 & 8 | RELE Program is implemented to achieve or exceed the Education Targets of Parishioners
LAG 5: Compile and assess the results of the parish RELE Program and make necessary improvements within 2 months |  |  | 
10. Obtain and compile qualitative and quantitative data from RELE Program implementations as to the effectiveness and success (based on criteria established in step 2) and identify areas for improvement. | Educators and RELE Team 3 | 1 months after step 9 | RELE Program implementation assessments are compiled
11. Finalize and deliver RELE Program effectiveness assessment analysis and make all refinements necessary to make the RELE Program more effective based on information identified in step 10. | Educators and RELE Team 3 | 1 months after step 10 | RELE Program is refined accordingly based on results of implementation

## Slide 43: Adult & Youth RELE WIG 3 Compelling Scoreboard
Lead Measure Action | Deadline Date | Status: Percent Complete and Date
1. Form RELE Team 3 | 1 month ____-22 | 
2. Research and Identify metrics to determine effectiveness and success | 2 months ____ -22 | 
3. Research RELE Programs | Simultaneous with step 2 _____-22 | 
4. Evaluate RELE Programs | 1 month ____-22 | 
5. Finalize RELE Program | 2 months ____-22 | 
6. Identify delivery modalities and Educators | 1 month ____-22 | 
7. Train Educators and implement delivery modalities | 3 months ____-22 | 
8. Recruit Target Numbers of adults and youth to participate in RELE Program | Concurrent with step 7 ____-21 | 
9. Implement RELE Program to the Education Targets | 9 months ____-23 | 
10. Obtain and compile effectiveness data from RELE Program implementation | 1 month ____ -23 | 
11. Compile the results of the RELE Program effectiveness assessment and improve the RELE Program accordingly | 1 month ____-23 | 

## Slide 44: Sample 6 Religious Education

## Slide 45: Adult & Youth Education Wildly Important Goal 2
Develop and implement an effective Adult and Youth Education Ministry Program for ALL adults and youth
that will be completed within 20 months by:
at least 33% of adults; and
at least 66% of youth.

## Slide 46: Prelim Lag Measures WIG 2
LAG 1: Research the most effective Adult & Youth Education Programs within 3 months
LAG 2: Develop the most effective Education Ministry Program for St. Demetrios adults and youth (the “Education Program ”) within 3 months
LAG 3: Identify delivery modalities and recruit and train the Education Program Educators within 3 months
LAG 4: Deliver the Education Program to at least 33% of adult stewards and 66% of youth within 9 months
LAG 5: Compile and assess the results of the Education Program and make necessary improvements within 2 months
Ministries WIG 2:
Develop and implement an effective Adult and Youth Education Ministry Program that at least 33% of adult stewards and 66% of youth complete within 20 months.

## Slide 47: Prelim Lead Measures WIG 2
LEAD 1:
  A: recruit team
  B: research and identify metrics to determine effectiveness and success
  C: Identify at least 5 Education Programs to consider
LEAD 2:
  A: evaluate Education Programs for effectiveness
  B: modify and/or develop Education Programs for utilization at St. Demetrios
  C: finalize “Education Program” and effectiveness measurement metrics
LEAD 3:
  A: identify delivery modalities (technology and “Educators”)
  B: develop Educator training program, delivery modalities and interim effectiveness assessment process
  C: recruit and train Educators
LEAD 4:
  A: identify, recruit and educate at least the “Target Number” of 33% of Parish adults and 66% of Parish youth in the Education Program
  B: assign Educators to respective adults and youth
  C: schedule and complete a parish implementation of the Education Program to all Target Number of adults and youth
LEAD 5:
  A: obtain qualitative and quantitative data from Education Program effectiveness
  B: analyze all data and finalize and deliver Education Program assessment and make all necessary improvements
LAG 1: Research the most effective Adult & Youth Education Programs within 3 months
LAG 2: Develop the most effective Education Program for St. Demetrios adults and youth (the “Education Program”) within 3 months
LAG 3: Identify delivery modalities and recruit and train the Education Program Educators within 3 months
LAG 4: Deliver the Education Program to at least 33% of adult stewards and 66% of youth within 9 months
LAG 5: Compile and assess the results of the Education Program and make necessary improvements within 2 months

## Slide 48: Adult & Youth Education Wildly Important Goal 2 Action Plan
Key Actions Necessary To Achieve Strategic WIG 2 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 1: Research the most effective Education Program within 3 months |  |  | 
1. Form Parish Wildly Important Goal Team 2 (Education Ministry Team 2). | Strategic Planning Team and Goal co-Captains | 1 month after start date | Education Ministry Team 2 members agree to serve
2. Research and identify metrics to determine effectiveness and how success will be determined for each targeted demographic of youth and adults. | Education Ministry Team 2 | 2 months after step 1 | Success and effectiveness metrics are finalized
3. Identify at least 5 Adult and 5 Youth Education programs to evaluate and consider from both inside and outside the Orthodox ecosystem. | Education Ministry Team 2 | Simultaneous with step 2 | At least 5 Education training programs are identified for study
LAG 2: Develop the most effective Education Program within 3 months |  |  | 
4. Evaluate and study the Parish Education Programs identified in step 3 to determine their effectiveness and applicability to St. Demetrios based on criteria of effectiveness and success determined in step 2. | Education Ministry Team 2 | 1 month after step 3 | Evaluation of alternative Education Programs is completed
5. Modify researched programs, or develop new curriculum, as necessary, to finalize the creation of official St. Demetrios Adult and Youth “Education Program” for use. Identify potential “Educators” who can teach the Education Program. | Education Ministry Team 2 | 2 months after step 4 | Adult and Youth Education Program is finalized

## Slide 49: Adult & Youth Education Wildly Important Goal 2 Action Plan
Key Actions Necessary To Achieve Strategic WIG 2 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 3: Identify delivery modalities and recruit and train the Education Program Educators within 3 months |  |  | 
6. (a) identify the best ways to deliver the Education Program; (b) identify delivery modalities and materials (technology, live education, etc.); (c) recruit potential Educators; and (d) schedule training for Educators. | Education Ministry Team 2 | 1 months after step 5 | Education Program delivery modalities determined and Educators are recruited and trained
7. (a) Develop training program for Educators; (b) determine interim effectiveness assessment measurement process; (c) train the Educators selected in step 6; and (d) implement and establish all delivery modalities and materials. | Education Ministry Team 2 | 3 months after step 5 (concurrent with step 6) | Educators are trained in training program, interim assessment process determined and all delivery modalities are set up
LAG 4: Deliver the Education Program to at least 33% of adults and 66% of youth within 9 months |  |  | 
8. Identify, recruit and educate at least 33% of Parish adult stewards and 66% of Parish youth in each targeted demographic of adults and youth (the “Target Numbers”) in the Education Program. | Educators and Education Ministry Team 2 | Concurrent with step 7 | At least the Target Numbers of Adult and Youth Parishioners agree to participate in the Education Program
9. At least the Target Number of Adult and Youth Parishioners will complete the Education Program. | Educators | 9 months after steps 7 & 8 | Education Program is implemented to at least the Target number of Parishioners

## Slide 50
Key Actions Necessary To Achieve Strategic WIG 2 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 5: Compile and assess the results of the Parish Education Program and make necessary improvements within 2 months |  |  | 
10. Obtain and compile qualitative and quantitative data from Parish Education Program implementations as to the effectiveness and success of the Education Program (based on criteria established in step 2) and identify areas for improvement. | Educators and Education Ministry Team 2 | 1 months after step 9 | Parish Education Program implementation assessments are compiled
11. Finalize and deliver Education Program effectiveness assessment analysis and make all refinements necessary to make the Education Program more effective based on information identified in step 10, and revise and improve the Education Program accordingly. | Educators and Education Ministry Team 2 | 1 months after step 10 | Parish Education Program implementation assessment analysis is completed and Education Program is refined accordingly
Adult & Youth Education Wildly Important Goal 2 Action Plan

## Slide 51: Adult & Youth Education Goal 2 Compelling Scoreboard
Lead Measure Action | Deadline Date | Status: Percent Complete and Date
1. Form Education Ministry Team 2 | (1 month) ____-21 | 
2. Research and Identify metrics to determine effectiveness and success | (2 months ____ -21 | 
3. Research Education Programs | Simultaneous with step 2) _____-21 | 
4. Evaluate Education Programs | (1 month) ____-21 | 
5. Finalize Parish Education Program | (2 months) ____-21 | 
6. Identify delivery modalities and Educators | (1 month) ____-22 | 
7. Train Educators and implement delivery modalities | (3 months) ____-22 | 
8. Recruit 33% Adults + 66% Youth | Concurrent with step 7) ____-21 | 
9. Implement Education Program to Target Numbers | (9 months) ____-22 | 
10. Obtain and compile effectiveness data from Education Program implementation | (1 month) ____ -22 | 
11. Compile the results of the Education Program effectiveness assessment and improve the Education Program accordingly | (1 month) ____-22 | 

## Slide 52: Sample 7 Religious Education

## Slide 53
Within 20 months, we will fully research, develop, improve and implement a best practices religious and spiritual education program that will drive a measurably more proficient level of knowledge of the Orthodox Faith and its practices to better live a Christ-centered life for all parish:
  (a) youth under 18
  (b) college-and and emerging adults; and
  (c) adults.
EDUCATION & SPIRITUAL GROWTH Strategic Goal 2.1
Religious & Spiritual Education

## Slide 54: Education & Spiritual Growth Strategic Goal 2.1 Action Plan
Key Actions Necessary To Achieve Strategic Goal 2.1 | Responsible Party | Timetable | Completion Confirmation Test
1. Form Educational and Spiritual Growth Goal 2.1 Task Force (“ESG2.1TF”) | Strategic Planning Team, Goal Captain and Clergy | 1 month from Start Date | ESG2.1TF team members agree to serve
2. Conduct comprehensive research from all available sources (Orthodox and non-Orthodox) to collect best in class religious and spiritual education programs and materials (learning standards, content, curricula, delivery methods, teacher development programs, etc.) for all age groups and specifically identify objective evidence of the effectiveness of each. | ESG2.1TF | 4 months after step 1 | Research report complied from all sources including objective evidence of effectiveness
3. Develop and conduct survey/polling to gain parish input as to what religious education and spirituality topics and delivery methods are desired by parishioners. | ESG2.1TF | Simultaneous with step 2 | Surveys are returned from statistically significant sampling and responses are compiled
4. Qualitatively analyze and assess: (a) all researched and collected educational and spiritual materials and objective evidence of their success and applicable target goals; (b) parishioner survey data of needed content and programs and desired delivery options; (c) all existing parish content; and (d) best methods for delivery of religious education materials for each age group. | ESG2.1TF | 4 months after steps 2 and 3 | Comprehensive report of qualitative analysis and best practices is completed

## Slide 55: Education & Spiritual Growth Strategic Goal 2.1 Action Plan
Key Actions Necessary To Achieve Strategic Goal 2.1 | Responsible Party | Timetable | Completion Confirmation Test
5. Develop an outline of a comprehensive “Religious and Spiritual Education Program” tailored to the needs of the parish with a delivery schedule and proposed methods of delivery. | ESG2.1TF | 3 months after step 4 | Outline of elements of comprehensive Religious and Spiritual Education Program is finalized
6. Develop, improve or eliminate materials needed to create a best practices comprehensive new Religious and Spiritual Education Program. | ESG2.1TF | 4 months after step 5 | Religious and Spiritual Education Program is completed and developed
7. Recruit and train all the required teachers of the new Religious and Spiritual Education Program (“Teachers”) and establish the various delivery methods for the Program as determined in step 4. | ESG2.1TF | 3 months after step 6 | Teachers are recruited and trained, and delivery methods are established
8. Begin implementation of the comprehensive Religious and Spiritual Education Program. | ESG2.1TF and Teachers | 1 month after step 7 | Religious and Spiritual Education Program delivery begins
9. At least annually review, evaluate, eliminate or improve materials, Teachers and the entire Religious and Spiritual Education Program to ensure that all materials represent the most effective best practices available and the Teachers are most effective so that the target goals are achieved. Necessary adjustments are made in the Program or Teachers. | ESG2.1TF and Teachers | At least annually after step 8 and continuously thereafter | Annual review takes place and improvements are implemented

## Slide 56: Sample 8 Religious Education

## Slide 57
Within 20 months, we will fully research, develop or improve and implement a Christ-centered Youth and Emerging Adult Ministry and programs that focus on measurably increasing and improving the spiritual and intellectual engagement, fellowship, service and Orthodox Christian way of life for the Youth and Emerging Adults in the parish.
EDUCATION & SPIRITUAL GROWTH Strategic Goal 2.2
Youth and Emerging Adult Ministries

## Slide 58: Education & Spiritual Growth Strategic Goal 2.2 Action Plan
Key Actions Necessary To Achieve Strategic Goal 2.2 | Responsible Party | Timetable | Completion Confirmation Test
1. Form Educational and Spiritual Growth Goal 2.1 Task Force (“ESG2.2TF”) | Strategic Planning Team and Goal Captain | 1 month from Start Date | ESG2.2TF team members agree to serve
2. Conduct comprehensive research from all available sources (Orthodox and non-Orthodox) to collect best in class youth and emerging adult ministry programs and activities and identify methods to assess and measurably increase and improve the spiritual and intellectual engagement, fellowship, service and Orthodox Christian way of life of youth and emerging adults. | ESG2.2TF | 5 months after step 1 | Research report complied from all sources including objective evidence of effectiveness
3. Develop and conduct survey/polling from present and past youth and emerging adults to gain input as to what programs and activities they desire and would be most effective and what are the most effective delivery options. | ESG2.2TF | Simultaneous with step 2 | Surveys are returned from statistically significant sampling of present and past youth and emerging adults and responses are compiled
4. Qualitatively analyze and assess: (a) all researched and collected youth and emerging adult ministry programs and activities, objective metrics and evidence of their success, and the methods to assess and measurably increase and improve the spiritual and intellectual engagement, fellowship and service; (b) Youth and emerging adult survey data of needed content and programs and desired delivery options; (c) all existing parish youth and emerging adult ministry programs and activities; and (d) best methods for implementing and delivering the programs and activities for each age group. | ESG2.2TF | 4 months after steps 2 and 3 | Comprehensive report of qualitative analysis and best practices is completed

## Slide 59: Education & Spiritual Growth Strategic Goal 2.2 Action Plan
Key Actions Necessary To Achieve Strategic Goal 2.2 | Responsible Party | Timetable | Completion Confirmation Test
5. Develop an outline of a comprehensive Youth and Emerging Adult Ministry Program tailored to the needs of the youth and emerging adults with delivery schedule and proposed methods of delivery. | ESG2.2TF and Clergy | 3 months after step 4 | Outline of elements of comprehensive Youth and Emerging Adult Ministry Program is finalized
6. Develop, improve or eliminate materials needed to create a best practices comprehensive new Youth and Emerging Adult Ministry Program that is also in full compliance with the applicable youth protection policies and standards. | ESG2.2TF | 3 months after step 5 | Youth and Emerging Adult Ministry Program is completed and developed
Recruit and train the Y&EA Ministry Team to implement the new Youth and Emerging Adult Ministry Program and establish the various delivery methods for the Program as determined in step 4. | ESG2.2TF | 3 months after step 6 | Y&EA Ministry Team are recruited and trained and delivery methods are established
8. Begin implementation of the comprehensive new Youth and Emerging Adult Ministry Program. | ESG2.2TF and Y&EA Ministry Team | 1 month after step 7 | Youth and Emerging Adult Ministry Program delivery begins
9. At least annually review, evaluate, eliminate or improve, materials, Y&EA Ministry Team and the entire Youth and Emerging Adult Ministry Program to ensure that all materials and the program represents the most effective best practices and metrics available and the Y&EA Ministry Team are most effective so that the target goals are achieved. Necessary adjustments are made in the Program or Y&EA Ministry Team. | ESG2.2TF and Y&EA Ministry Team | At least annually after step 8 and continuously thereafter | Annual review takes place and improvements are implemented

## Slide 60: Sample 9 Religious Education

## Slide 61
Within 21 months, we will develop and implement an effective, comprehensive and interactive full-year Adult Religious Education Program that will be successfully delivered to a minimum of 30% of adult parishioners over the next 2 years thereafter.
Education
Goal 4.1 Adult Religious Education

## Slide 62: Education Goal 4.1 Action Plan
Specific Key Actions Necessary To Achieve Goal 4.1 | Who Must Do Each Action | Timetable: How Many Months or Days To Finish Action From Previous Action | How Will We Know When This Action Has Been Completed
Form Education Goal 4.1 Task Force (E4.1TF). | E4.1TF | 1 month from start date | E4.1TF team members agree to serve
2. Compile and send survey to community for input on most needed and desired adult religious education and spirituality topics, information and curriculum. | E4.1TF | 4 months after step 1 | Surveys returned and responses are compiled
3. Conduct comprehensive research to determine best in class adult religious and spiritual education materials, content, programs, delivery options and best practices from both Orthodox and non-Orthodox sources (including reviewing existing Metropolis of Atlanta strategic plan religious education materials and other offerings from Orthodox Parish Priests and Religious Education Directors) and specifically identify objective evidence of the effectiveness of each. | E4.1TF | Simultaneous with step 2 | All materials are researched including objective evidence of effectiveness
4. Qualitatively analyze and assess: (a) all researched and submitted educational materials and categorize them according to topics and objective evidence of their effectiveness and create a comprehensive list of topics and best in class content; (b) assess community survey data of needed and desired adult religious education and spirituality topics and information; and (c) best alternative methods for delivery of adult religious education content. | E4.1TF | 4 months after step 3 | Comprehensive report completed of qualitive analysis of all content / materials, community survey and alternative delivery systems
5. Finalize outline of comprehensive “Adult Religious Education Program” and delivery schedule and methods to identify gaps in the Program and the process and timeline for specifically filling such gaps, including who is responsible for achieving each step within the established timeline (“Gap Analysis Workplan”). | E4.1TF | 3 months after step 4 | Adult Religious Education Program and Gap Analysis Workplan is complete

## Slide 63: Education Goal 4.1 Action Plan
Specific Key Actions Necessary To Achieve Goal 4.1 | Who Must Do Each Action | Timetable: How Many Months or Days To Finish Action From Previous Action | How Will We Know When This Action Has Been Completed
6. Research, gather, revise, develop, and/or solicit the development of additional materials needed for missing areas, or areas that do not meet best practices, or most effective standard as determined through Gap Analysis Workplan, including replacing those materials that are deemed ineffective. | E4.1TF | 4 months after step 5 | Gap Analysis Workplan is executed and gaps are filled
7. Recruit and train any additional appropriate persons needed to most effectively deliver the content for the Adult Religious Education Program. | E4.1TF | 4 months after step 6 | Additional educators agree to serve and are trained
8. In conjunction with Communications and Technology Task Force, establish online, video and/or alternative platform for delivery of Adult Religious Education Program, including a format for peer review and commentary, as well as a process to submit newer and more effective materials, and load best practices education materials onto Metropolis of Atlanta Portal Spiritual Growth Resources. | E4.1TF | Simultaneous with steps 6 and 7 | Online and video delivery options established and best practice materials for the various topics are loaded on the Metropolis Portal
9. Begin promotion of Adult Religious Education Program and establish process to sign up as many adults as possible with the goal of participation from 30% of our adults. | E4.1TF | Simultaneous with step 7 | Communication and sign-up of participants occurs
10. Begin official roll out of Adult Religious Education Program. | E4.1TF | 1 month after step 9 | Program is officially rolled-out
11. Create and implement a regularly scheduled evaluation plan for reviewing the performance and effectiveness of all Adult Religious Education Program materials after each delivery and make improvements based on results of evaluation. | E4.1TF | Beginning after each Program is delivered | Evaluations reviewed and improvements made in each element of Adult Religious Education Program
12. Semi-annual review, evaluation and update of all materials, presenters, and entire Adult Religious Education Program to ensure that all materials and presenters are the most effective best practices available and the target of 30% of adults having completed the program is achieved. | E4.1TF | Semi-annual review | Semi-Annual assessment is complete, improvements implemented and 30% adult target is achieved

## Slide 64
Within 21 months, we will determine the applicable metrics to ensure that our Sunday School curriculum is effective, and design and implement such an effective K-12 curriculum that reaches and engages at least 60% of our youth.
Education
Goal 4.2 Youth Religious Education

## Slide 65: Education Goal 4.2 Action Plan
Specific Key Actions Necessary To Achieve Goal 4.2 | Who Must Do Each Action | Timetable: How Many Months or Days To Finish Action From Previous Action | How Will We Know When This Action Has Been Completed
1. Form Education Goal 4.2 Task Force (E4.2TF). | E4.2TF | 1 month from start date | E4.2TF team members agree to serve
2. Conduct comprehensive research from all available sources to determine how to measure properly the effectiveness of church religious education programs and materials for youth and establish an “Effectiveness Measurement Methodology and Process” to test the effectiveness of our youth religious education programs. | E4.2TF | 4 months after step1 | Effectiveness Measurement Methodology and Process Report is completed
3. Conduct comprehensive research to determine best in class religious and spiritual education materials, content, programs, delivery options and best practices from both Orthodox and non-Orthodox sources (including site visits to successful churches and reviewing existing Metropolis of Atlanta strategic plan religious education materials and other offerings from Orthodox Parish Priests and Religious Education Directors) and specifically identify objective evidence of the effectiveness of each. | E4.2TF | simultaneous with step 2 | All materials are researched including objective evidence of effectiveness based on Effectiveness Measurement Methodology and Process
4. Qualitatively analyze and assess: (a) all researched and submitted educational materials and categorize them according to topics and objective evidence of their effectiveness and create a comprehensive list of topics and best in class content; (b) all content against the Effectiveness Measurement Methodology and Process to determine the most effective content; and (c) best alternative methods for delivery of most effective youth religious education content. | E4.2TF | 4 months after step 3 | Comprehensive report completed of qualitive analysis of all content/materials, and alternative delivery systems
5. Finalize outline of comprehensive “Youth Religious Education Program” and delivery schedule and methods to identify gaps in the Program and the process and timeline for specifically filling such gaps, including who is responsible for achieving each step within the established timeline (“Gap Analysis Workplan”). | E4.2TF | 3 months after step 4 | Youth Religious Education Program and Gap Analysis Workplan is complete

## Slide 66: Education Goal 4.2 Action Plan
Specific Key Actions Necessary To Achieve Goal 4.2 | Who Must Do Each Action | Timetable: How Many Months or Days To Finish Action From Previous Action | How Will We Know When This Action Has Been Completed
6. Research, gather, revise, develop, and/or solicit the development of additional materials needed for missing areas that do not meet best practices, or most effective standard as determined through Gap Analysis Workplan, including replacing those materials that are deemed ineffective. | E4.2TF | 4 months after step 5 | Gap Analysis Workplan is executed and gaps are filled
7. Recruit and train appropriate teachers needed for the most effective delivery of the Youth Religious Education Program. | E4.2TF | 4 months after step 6 | Additional teachers agree to serve and are trained
8. Begin official roll out of Youth Religious Education Program. | E4.2TF | 1 month after step 7 | Youth Religious Education Program is officially rolled-out
9. In conjunction with the Communications and Technology Committee, establish and implement alternative online, video and/or other platform for delivery of Youth Religious Education Program, including a format for peer review and commentary, as well as a process to submit newer and more effective materials,. | E4.2TF | Simultaneous with steps 7 and 8 | Online, video or alterative delivery options established and implemented
10. Semi-annual review, evaluation and update of all materials, teachers, and entire Youth Religious Education Program to ensure that all materials are the most effective best practices available and the target of 60% of Youth having effectively completed the Youth Religious Education Program is achieved. | E4.2TF | Semi-annual review | Semi-Annual assessment of Youth Religious Education Program is complete, improvements are implemented and 60% Youth target is achieved

## Slide 67: Sample 10 Religious Education

## Slide 68: Parishioner Engagement & Spiritual Growth Wildly Important Goal 3
Develop and implement within 36 months effective Parishioner Engagement & Spiritual Growth Programs (collectively, the “Engagement Programs”) that will achieve the following “Engagement Targets”:
Increase ministries engagement by at least 50%;
Increase the parishioner financial stewardship so that:
all parish operating expenses (plus increases in funding for parish-chosen external charities and philanthropies that equal at least 10% of the other operating expenses) are paid through parishioner stewardship; and
the median annual stewardship contribution from parishioners increases by at least 75%;
(c) Actively engage at least 50% of parishioners in a religious education and spiritual engagement program.

## Slide 69
LAG 1: Research the most effective stewardship and ministry engagement, and spiritual growth programs (the “Engagement Programs”) within 4 months
LAG 2: Develop the most effective Engagement Programs within 4 months
LAG 3: Recruit and train the parish “Engagement Ambassadors” within 2 months
LAG 4: Implement the Engagement Programs to achieve the Engagement Targets within 24 months
LAG 5: Compile and assess the results of the Engagement Programs and make necessary improvements within 2 months
WIG 3:
Develop and implement within 36 months effective Parishioner Engagement & Spiritual Growth Programs (collectively, the “Engagement Programs”) that will achieve the following “Engagement Targets”:
Increase ministries engagement by at least 50%;
Increase the parishioner financial stewardship so that:
all parish operating expenses (plus increases in funding for parish-chosen external charities and philanthropies to equal at least 10% of the other operating expenses) are paid through parishioner stewardship; and
the median annual stewardship contribution from parishioners will increase by at least 75%;
(c) Actively engage at least 50% of parishioners in a religious education and spiritual engagement program.
Parishioner Engagement & Spiritual Growth Lag Measures WIG 3

## Slide 70
LEAD 1:
  A: recruit team
  B: determine stewardship, ministry engagement, and spiritual engagement key definitions and effectiveness metrics
  C: analyze the parish baseline on those key effectiveness metrics and identify parish impediments to success
  D: identify at least 5 stewardship/ministry engagement and 5 spiritual growth programs to consider
LEAD 2:
  A: evaluate researched stewardship, ministry engagement, and spiritual engagement programs for effectiveness against key performance metrics and parish baselines
  B: modify stewardship, ministry engagement and spiritual engagement programs (collectively, the ”Engagement Programs”) for utilization at St Nicholas
  C: finalize parish Engagement Programs and establish quarterly and/or monthly performance benchmarks
LEAD 3:
  A: identify numbers and names of Engagement Programs and Engagement Ambassadors to deliver Engagement Programs
  B: develop Engagement Ambassadors training programs
  C: train the Engagement Ambassadors
LEAD 4:
  A: implement Engagement Programs based on determined monthly and quarterly performance benchmarks
  B: continue Engagement Ambassadors’ follow-up with parishioners until Engagement Targets are achieved
LEAD 5:
  A: obtain qualitative and quantitative data from Engagement Programs effectiveness
  B: analyze all data and finalize Engagement Programs assessment and make all necessary improvements
LAG 1: Research the most effective stewardship and ministry engagement, and spiritual growth programs (the “Engagement Programs”) within 4 months
LAG 2: Develop the most effective Engagement Programs within 4 months
LAG 3: Recruit and train the parish “Engagement Ambassadors” within 2 months
LAG 4: Implement the Engagement Programs to achieve the Engagement Targets within 24 months
LAG 5: Compile and assess the results of the Engagement Programs and make necessary improvements within 2 months
Parishioner Engagement & Spiritual Growth Lead Measures WIG 3

## Slide 71: Parishioner Engagement & Spiritual Growth Wildly Important Goal 3 Action Plan
Key Actions Necessary To Achieve Strategic WIG 3 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 1: Research the most effective stewardship, and ministry and spiritual engagement programs (the “Engagement Programs”) within 4 months |  |  | 
1. Form Parishioner Engagement & Spiritual Growth Wildly Important Goal Team 3 (“Engagement Programs Team 3”). | Strategic Planning Team and Goal co-Captains | 1 month after Start Date | Engagement Programs Ministry Team 3 members agree to serve
2. Determine stewardship and ministry and spiritual engagement key definitions and effectiveness metrics. | Engagement Programs Ministry Team 3 | 2 month after step 1 | Engagement definitions and metrics determined
3. Analyze the parish baseline on those key stewardship, ministry and spiritual engagement effectiveness metrics and survey/research parish impediments to achieving increased stewardship and ministry and spiritual engagement success. | Engagement Programs Ministry Team 3 | 1 months after step 2 | Parish baselines and parish impediments determination are finalized
4. Identify at least 5 stewardship/ ministry engagement, and 5 spiritual growth programs, to consider from both inside and outside the Orthodox ecosystem. | Engagement Programs Ministry Team 3 | Simultaneous with steps 2 & 3 | At least 5 stewardship /ministry engagement, and 5 spiritual growth programs are examined

## Slide 72: Parishioner Engagement & Spiritual Growth Wildly Important Goal 3 Action Plan
Key Actions Necessary To Achieve Strategic WIG 3 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 2: Develop the most effective Engagement Programs within 4 months |  |  | 
5. Evaluate researched stewardship/ ministry engagement and spiritual growth programs for effectiveness against key performance metrics and parish baselines based on criteria of effectiveness determined in step 2. | Engagement Programs Ministry Team 3 | 2 months after step 4 | Evaluation of alternative stewardship, ministry engagement, and spiritual engagement programs is completed
6. Modify or develop stewardship / ministry engagement and spiritual growth programs (collectively, the “Engagement Programs”) for utilization at St. Nicholas and finalize Engagement Programs and establish monthly performance benchmarks. | Engagement Programs Ministry Team 3 | 2 months after step 5 | Engagement Programs are finalized, and monthly performance benchmarks are determined
LAG 3: Recruit and train the parish Engagement Ambassadors within 2 months |  |  | 
7. Identify and recruit the “Engagement Ambassadors” who can implement the Engagement Programs. | Engagement Programs Ministry Team 3 | 1 month after step 6 | Engagement Ambassadors are recruited
8. Develop Engagement Ambassadors training program and train the Engagement Ambassadors selected in step 7. | Engagement Programs Ministry Team 3 | 1 month after step 7 | Engagement Ambassadors are trained

## Slide 73: Parishioner Engagement & Spiritual Growth Wildly Important Goal 3 Action Plan
Key Actions Necessary To Achieve Strategic WIG 3 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 4: Implement the Engagement Programs to achieve the Engagement Targets within 24 months |  |  | 
9. Implement Engagement Programs to achieve the Engagement Targets. | Engagement Ambassadors | 24 months after step 8 | Engagement Programs are fully launched
10. Track and report on monthly performance benchmarks determined in step 6 and continue Engagement Ambassadors’ follow-up with parishioners until Engagement Targets are achieved | Engagement Ambassadors | Contemporaneous with step 9 | Established monthly Engagement Targets are achieved
LAG 5: Compile and assess the results of the Parish Engagement Programs and make necessary improvements within 2 months |  |  | 
11. Obtain and compile qualitative and quantitative data from Engagement Programs and compile as to the effectiveness and success (based on criteria established in step 2) and identify areas for improvement. | Engagement Ambassadors and Engagement Ministry Team 3 | 1 month after step 10 | Engagement Programs assessments are completed
12. Finalize and deliver Engagement Programs assessment analysis report, and make all refinements necessary to make the Engagement Ministries more effective based on information identified in step 11. | Engagement Ambassadors and Engagement Ministry Team 3 | 1 month after step 11 | Engagement Programs analysis is completed, and Engagement Programs are refined accordingly

## Slide 74
Lead Measure Action | Deadline Date | Status: Percent Complete and Date
1. Form Engagement Ministry Team 3 | 1 month ___-22 | 
2. Develop definitions and effectiveness metrics | 2 months ___-22 | 
3. Analyze parish baselines and engagement success impediments | 1 month ___-22 | 
4. Research Engagement Programs | together with 2 and 3 month ____-22 | 
5. Evaluate Engagement Programs | 2 months ____-22 | 
6. Finalize Engagement Programs | 2 months ____-22 | 
7. Identify and recruit Engagement Ambassadors | 1 month _____-22 | 
8. Train Engagement Ambassadors | 1 month _____-22 | 
9. Implement Engagement Programs and manage to interim monthly targets | 24 months ___-24 | 
10. Track performance Data from Engagement Programs Implementation | Simultaneous with step 9 | 
11. Obtain qualitative and quantitative assessment data from Engagement Programs | 1 month_____-24 | 
12. Improve Engagement Programs based lessons learned in step 11 | 1 month ____-24 | 
Parishioner Engagement & Spiritual Growth Wildly Important Goal 3
Compelling Scoreboard