## Slide 1: Church Building & Capital Campaign Program S.M.A.R.T. Goal
Within six months we will research and present for General Assembly and Metropolis approval at least the following four options:
  Plan A: A revised construction plan, budget, and capital campaign and debt plan to fully finance and build on the current site a modified version of the currently approved plan;
  Plan B: A completely modified construction plan, budget, and capital campaign and debt plan to fully finance and build on the current site a new Sanctuary only;
  Plan C: A new construction plan, budget, and capital campaign and debt plan to fully finance and build an expanded sanctuary and other buildings on an entirely new site assuming sale of the current site; and
  Plan D: A budget, capital campaign and debt plan to fully finance and buy an existing building to be developed into a sanctuary and other supportive buildings on an entirely new site assuming sale of the current site.
(b) Within twelve months after (a), we will:
  Reach consensus and obtain all necessary parish and Metropolis approvals for the final desired Building Program;
  Retain the real estate professionals, architects, and general contractors necessary to complete the Building Program;
  (iii) Develop and begin to execute a “Capital Campaign” process plan and methodology to obtain pledges to cover at least 80% of the aggregate Building Program budget (“Contributed Portion”); and
  (iv) Negotiate funding commitments for a construction loan and mortgage loan (the “Borrowed Portion”) and develop repayment plan approved by the parish.
(c) We will complete the Capital Campaign and raise at least the Contributed Portion by the deadline established in the Capital Campaign decided above.
We will research, develop, and implement a best practices “Church Building Program” that within 54 months will achieve the following “Church Building & Capital Campaign Targets” for a new church.

## Slide 2
Actions Steps | Responsible Party | Deadline | Completion Test
Interim Goal 1: Research the most effective Church Building & Capital Campaign Program within 6 months |  |  | 
1. Form Church Building & Capital Campaign Team (CB&CCT). | SPT and CB&CCT Goal Co-Captains | 1 month after Start Date | CB&CCT members agree to serve
2. Research the alternative options and finalize the parish consensus list, prioritization, and timeline for building and capital improvement projects in the Church Building & Capital Campaign Program. | CB&CCT | 2 months after step 1 | Finalize Church Building & Capital Campaign Program projects and prioritization
3. Finalize a proposed construction budget for the Church Building & Capital Campaign Program and seek necessary approvals for total budget, Contributed Portion and Borrowed Portion. | CB&CCT | 3 month after step 2 | Church Building Project budget and Contributed and Borrowed Portions determined
4. Identify at least 3 capital campaign processes (and/or consultants if needed) to consider from both inside and outside the Orthodox ecosystem. | CB&CCT | Simultaneous with steps 2 & 3 | At least 3 capital campaign programs and/or consultants are examined
Church Building & Capital Campaign Action Plan

## Slide 3
Actions Steps | Responsible Party | Deadline | Completion Test
Interim Goal 2: Develop the most effective Church Building & Capital Campaign Program within 10 months |  |  | 
5. Obtain all necessary parish, Metropolis and city approvals for Church Building & Capital Campaign Program, including Capital Campaign and Borrowings budgets. | CB&CCT | 10 months after step 4 | Approvals obtained and Capital Campaign ad Borrowing levels finalized
6. Develop effective Capital Campaign to reach 100% of parishioners to solicit sufficient 2-3-year pledges to provide at least the Contributed Portion of the Church Building & Capital Campaign Program and negotiate with lenders the construction and mortgage loans. Develop monthly performance benchmarks. | CB&CCT | Simultaneous with step 5 | Capital Campaign and construction and mortgage programs and loans are finalized and negotiated
Interim Goal 3: Recruit and train Ambassadors within 2 months |  |  | 
7. Identify and recruit personal visitation capital campaign ambassadors (“Ambassadors”) who can implement the Capital Campaign. | CB&CCT | 1 month after step 6 | Ambassadors are recruited
8. Train Ambassadors to implement the Capital Campaign. | CB&CCT | 1 month after step 7 | Ambassadors are trained
Church Building & Capital Campaign Action Plan

## Slide 4
Actions Steps | Responsible Party | Deadline | Completion Test
Interim Goal 4: Implement the Church Building & Capital Campaign Program to achieve the Church Building & Capital Campaign Targets within 24 months |  |  | 
9. Implement Church Building & Capital Campaign Program to achieve the Church Building & Capital Campaign Targets. | Ambassadors | 24 months after step 8 | Church Building & Capital Campaign is fully launched
10. Track and report on monthly performance benchmarks determined in step 6 and continue Ambassadors follow-up with parishioners until Church Building & Capital Campaign Targets are achieved | Ambassadors | Contemporaneous with step 9 | Established monthly Church Building & Capital Campaign Targets are achieved
Interim Goal 5: Complete Church Building & Capital Campaign Program |  |  | 
11. Identify and fill any gaps in Building & Capital Campaign Program to achieve Church Building & Capital Campaign Targets | Ambassadors and CB&CCT | 12 months after step 10 | Church Building & Capital Campaign Program is completed
Church Building & Capital Campaign Action Plan

## Slide 5
Action | Deadline Date | % Complete and Date
1. Form Church Building & Capital Campaign Program Team |  | 
2. Develop Church Building & Capital Campaign Program projects and prioritization |  | 
3. Church Building Project budget and Contributed and Borrowed Portions determined |  | 
4. Capital campaign programs and/or consultants researched |  | 
5. Approvals obtained and Capital Campaign ad Borrowing levels finalized |  | 
6. Capital Campaign and construction and mortgage loans are finalized and negotiated |  | 
7. Identify and recruit Capital Campaign Ambassadors |  | 
8. Train Ambassadors |  | 
9. Implement Church Building & Capital Campaign Program manage to interim monthly targets |  | 
10. Track performance of Church Building & Capital Campaign Program |  | 
11. Identify and fill gaps in results of Church Building & Capital Campaign Program |  | 
Church Building & Capital Campaign Action Plan

## Slide 6
Within 39 months we will research, develop, and implement best practices and effective Parish Facilities Ministry with a comprehensive communications plan that will achieve the following “Parish Facilities Targets”:
(d) A new and comprehensive “Parish and Facilities Ministry” will:
  Within 4 months, finalize developing a detailed plan “Consensus Parish Facilities Plan” that addresses all present and future building and facilities needs and desires of the parish in one campus location, including
    facilities improvements and additions priorities list,
    plans for sales of superfluous property, and
    creation of development budget (including use of the Endowment) for the Consensus Parish Facilities Plan;
  within 5 months after (d)(i),
    A. obtain all necessary parish approvals for the Consensus Parish Facilities Plan;
    B. obtain Metropolis and other governmental approvals for the Consensus Parish Facilities Plan approved by the parish;
  within 6 months after (d)(ii),
    A. identify and contract with architects, general contractors. and other service providers necessary to execute the Consensus Parish Facilities Plan;
    B. develop and begin executing a “Capital Campaign” process plan and methodology that includes using the parish Endowment (to the extent approved by the parish) plus three-year pledges to cover at least 80% of the aggregate budget for the Consensus Parish Facilities Plan (“Contributed Portion”);
    C. obtain funding commitments for a construction loan and, if necessary, mortgage loan and repayment plan (the “Borrowed Portion”) for the Consensus Facilities Plan; and
  within 24 months after (d)(iii) complete the Consensus Parish Facilities Plan, including completion of the Capital Campaign by raising at least the Contributed Portion.
Parish Facilities Ministry S.M.A.R.T. Goal (Part 2)
Page 2 of 2

## Slide 7
Actions Steps | Responsible Party |  | Deadline | Completion Test | 
Interim Goal 1: Research parish buildings and facilities options to determine optimum solution within 4 months |  |  |  |  | 
1. Form Parish Facilities Ministry Team (PFMT). | PFT and Goal Co-Captains | SPT and Goal Co-Captains | 1 month after Start Date | PFT members agree to serve | PFMT members agree to serve
2. Comprehensively research the alternative options and analyze optimal alterative(s) for a proposal for Goal items D (i) (A), (B), (C) and (D) (the “Consensus Parish Facilities Plan”). | PFT | PFMT | 3 months after step 1 |  | Comprehensive research of optimal building and facilities options is competed
Interim Goal 2: Obtain consensus consents and approvals from parishioners and Metropolis in support of the Consensus Facilities Plan within 5 months |  |  |  |  | 
3. Finish development of Consensus Parish Facilities Plan and obtain all necessary parish and Metropolis approvals to whatever final version of the Consensus Parish Facilities Plan is approved by the parish general assembly. | LPCFT | PFMT | 5 months after step 2 |  | Obtain parishioner and Metropolis approval of Consensus Parish Facilities Plan
Parish Facilities Ministry – Part 2

## Slide 8
Actions Steps | Responsible Party | Deadline | Completion Test
Interim Goal 3: Obtain all necessary professionals and capital campaign program and debt borrowings to implement Consensus Parish Facilities Plan and Capital Campaign within 6 months |  |  | 
4. Implement steps (d) (iii) to achieve Consensus Parish Facilities Plan by: (A) identifying architects, general contractors, and other service providers: (B) identify how much of the Endowment will be used as part of the Consensus Parish Facilities Plan and receive approval from the parish general assembly; (C) develop and begin executing a “Capital Campaign” to obtain at least the Contributed Portion of the Consensus Parish Facilities Plan; and (D) obtain funding commitments for the “Borrowed Portion” | PFMT | 6 months after step 3 | Finalize retention of necessary professionals, any borrowings and capital campaign and debt program to fully implement the Consensus Parish Facilities Plan
5. Develop tracking and reporting monthly performance benchmarks for all activities associated with Consensus Parish Facilities Plan and Capital Campaign (the “Parish Facilities & Capital Campaign Targets”). | PFMT | Simultaneous with step 4 | Report on monthly progress of Parish Facilities Building & Capital Campaign Targets
Parish Facilities Ministry – Part 2

## Slide 9
Actions Steps | Responsible Party | Deadline | Completion Test
Interim Goal 5: Implement the Facilities and all other programs to achieve the LPC&F Targets within 24 months |  |  | 
6. Successfully implement Consensus Parish Facilities Plan and Capital Campaign Ministry. | PFMT | 24 months after step 5 | Consensus Parish Facilities Plan and Capital Campaign Ministry are completed
7. Track and report on monthly performance benchmarks determined previously regarding Consensus Parish Facilities Plan, Parish Facilities & Capital Campaign Targets, and Consensus Parish Facilities Ministry. | PFMT | Simultaneous with step 6 | Monthly performance benchmark reports are released
8. Identify and fill any gaps in Parish Facilities & Capital Campaign Targets until Consensus Parish Facilities Plan is fully completed and achieved. | PFMT | Simultaneous with step 6 | Consensus Parish Facilities Ministry and Capital Campaign are successfully achieved
Parish Facilities Ministry – Part 2

## Slide 10
Lead Measure Action | Deadline Date | % Complete and Date
1. Form Parish Facilities Religious Ministry Team |  | 
2. Research Consensus Parish Facilities Plan options |  | 
3. Develop Consensus Parish Facilities Plan and obtain all necessary parish and Metropolis approvals |  | 
4. Identifying professionals, and obtain approval for use of Endowment, develop and begin executing a Capital Campaign and obtain funding commitments for the Borrowed Portion |  | 
5. Develop tracking and reporting monthly performance benchmarks for all activities associated with Consensus Parish Facilities Plan and Capital Campaign (the “Parish Facilities & Capital Campaign Targets |  | 
6. Successfully implement Consensus Parish Facilities Plan and Capital Campaign Ministry |  | 
7. Track and report on Consensus Parish Facilities Ministry monthly performance benchmarks, Capital Campaign Targets. |  | 
8. Identify and fill any gaps in Parish Facilities & Capital Campaign Targets until Consensus Parish Facilities Plan is fully completed and achieved. |  | 
Parish Facilities

## Slide 11: Campus Improvements Goal 1.1 Campus Improvements
(a) Within 15 month, we will determine the projected costs, timelines, obtain necessary approvals and prioritize a Master Plan for the most critical Cathedral Campus improvements, including improved: (i) facilities more accessible to individuals with disabilities; (ii) outdoor facilities; (iii) storage facilities; and (iv) signage.
(b) Within 2 years thereafter, we will raise the necessary funds and complete the prioritized improvements based on the established timelines.

## Slide 12: Campus Improvements Goal 1.1 Action Plan
Specific Key Actions Necessary To Achieve Goal 1.1 | Who Must Do Each Action | Timetable: How Many Months or Days To Finish Action From Previous Action | How Will We Know When This Action Has Been Completed
1. Form Campus Improvements Goal 1.1 Task Force (“CI1.1TF”). | Strategic Planning Team and Goal Captain | 1 month from Start Date | CI1.1TF team members agree to serve
2. Research and identify accessibility, athletic and storage facility projects (“Master Plan Projects”) needs throughout our campus by (a) conducting an on-site assessment with appropriate legal and facilities experts; (b) developing outreach tools (e.g., survey, focus groups, etc.) to receive feedback from community concerning Master Plan Projects needs; and (c) reviewing existing documentation on previous efforts to identify necessary improvements. | CI1.1TF | 4 months after step 1 | Completed on-site assessment, survey/focus group findings compiled in centralized format, existing documentation compiled a notebook of Master Plan Projects.
3. Establish criteria for prioritization and then prioritize Master Plan Projects list identified in step 2 (e.g., critical, necessary, desirable, etc.) and establish a proposed implementation timeline. | Parish Council and CI1.1TF | 1 month after step 2 | Proposed prioritization of Master Plan Projects completed
4. Create preliminary design drawings and research cost estimates for each prioritized Master Plan Project and compile comprehensive Master Plan Project Plan with all projects prioritized, costed and having proposed timelines. | CI1.1TF | 5 months after step 3 | Estimated costs and timelines determined and Master Plan Project Plan developed

## Slide 13: Campus Improvements Goal 1.1 Action Plan
Specific Key Actions Necessary To Achieve Goal 1.1 | Who Must Do Each Action | Timetable: How Many Months or Days To Finish Action From Previous Action | How Will We Know When This Action Has Been Completed
5. Obtain first Parish Council and then General Assembly (and any other required approvals (e.g., Metropolis, county, etc.)). | CI1.1TF and Parish Council and General Assembly | 4 months after step 4 | Required Parish Council, General Assembly and other approvals all obtained
6. Work collaboratively with Parish Council and Parish community to conduct feasibility study and procure necessary funding for approved prioritized Master Plan Projects. | CI1.1TF and Parish Council | 10 months after step 5 | Master Plan Project funds are raised
7. Work collaboratively with Parish Council and appropriate Parish authorities responsible for project management (e.g., finalize the design plans and design and construction bid process and permits, and the construction process, etc.) as necessary and appropriate to monitor progress and ensure timely and proper completion. | CI1.1TF and Parish Council | 6 months after step 6 | Periodic project reports and presented to Parish Council
8. Supervise completion of construction on identified Master Plan Projects. | CI1.1TF and Parish Council | 7 months after step 7 | Construction, including punch list items is complete and Parish accepts work
9. Conduct after completion review on all Master Plan Projects and processes and document lessons learned. | CI1.1TF and Parish Council | 1 month after step 7 | Master Plan Project final report submitted to Cathedral community