## Slide 1: Sample 1 Stewardship & Engagement

## Slide 2: Stewardship & Engagement S.M.A.R.T. Goal
Transition the adult and youth parishioners to becoming percentage givers on their way to becoming tithers;
Increase the adult and youth ministry engagement so that at least 70% of parishioners are actively engaged in ministry through implementing pathways for parishioners to use their time and talents on our way to becoming a full participation parish;
Cover at least 70% of parish operating expenses solely through financial stewardship contributions; and
(d) Implement a planned giving campaign in which at least 15% of parishioners participate.
We will research, develop, and implement a best practices and effective adult and youth Stewardship & Engagement Ministry (the “Stewardship & Engagement Ministry”) with a comprehensive communications plan that will achieve the following “Stewardship & Engagement Targets” within 36 months:

## Slide 3
Stewardship & Engagement Action Plan
Actions Steps | Responsible Party | Deadline | Completion Test
Interim Goal 1: Research the most effective stewardship and ministry engagement programs within 4 months |  |  | 
1. Form Stewardship & Engagement Ministry Team (S&EMT). | SPT and S&EMT Goal Co-Captains | 1 month after Start Date | S&EMT members agree to serve
2. Determine adult and youth stewardship, tithing, ministry engagement, and planned giving key definitions, data, and effectiveness metrics. | S&EMT | 1 month after step 1 | Definitions and metrics determined
3. Analyze the adult and youth parish baselines on those key stewardship, tithing, ministry engagement, and planned giving metrics, survey/research parish impediments to achieving increased stewardship, tithing, ministry engagement, and planned giving success. | S&EMT | 2 months after step 2 | Parish baselines and parish impediments determination are finalized
4. Identify at least 2-3 ministry engagement, 2-3 stewardship, percentage giving/tithing, and 2-3 planned giving programs to consider from both inside and outside the Orthodox ecosystem. | S&EMT | Simultaneous with steps 2 & 3 | At least 2-3 of each of stewardship, ministry engagement & planned giving programs are examined

## Slide 4
Actions Steps | Responsible Party | Deadline | Completion Test
Interim Goal 2: Develop the most effective Stewardship, Ministry Engagement & Planned Giving Ministry within 3 months |  |  | 
5. Evaluate researched adult and youth stewardship, tithing, ministry engagement, and planned giving programs for effectiveness against key parish performance metrics and baselines based on criteria of effectiveness determined in step 2. | S&EMT | 1 month after step 4 | Evaluation of alternative stewardship & ministry engagement, tithing, and planned giving programs is completed
6. Modify or develop new adult and youth stewardship, tithing, ministry engagement, and planned giving ministry programs for utilization at the parish (the “SMEPG Ministry”) and establish monthly performance benchmarks and comprehensive communications strategy and plan. | S&EMT | 2 months after step 5 | SMEPG Ministry is finalized, and monthly performance benchmarks are determined
Interim Goal 3: Recruit and train Ambassadors within 3 months |  |  | 
7. Identify and recruit stewardship personal visitation (“Ambassadors”) who can implement the SMEPG Ministry. | S&EMT | 1 month after step 6 | Ambassadors are recruited
8. Train Ambassadors to implement all aspects of the SMEPG Ministry. | S&EMT | 2 months after step 7 | Ambassadors are trained
Stewardship & Engagement Action Plan

## Slide 5
Actions Steps | Responsible Party | Deadline | Completion Test
Interim Goal 4: Implement the Stewardship, Engagement & Tithing Ministry to achieve the Stewardship & Engagement Targets within 24 months |  |  | 
9. Fully implement the SMEPG Ministry to achieve the Stewardship & Engagement Targets. | Ambassadors | 24 months after step 8 | SMEPG Ministry is fully launched
10. Track and report on monthly performance benchmarks determined in step 6 and continue Ambassadors follow-up with parishioners until Stewardship & Engagement Targets are achieved | Ambassadors | Contemporaneous with step 9 | Established monthly Stewardship & Engagement Targets are achieved
Interim Goal 5: Compile and assess the results of the Stewardship, Engagement & Tithing Ministry and make necessary improvements within 2 months |  |  | 
11. Obtain and compile qualitative and quantitative data from SMEPG Ministry and determine effectiveness and success (based on criteria established in step 2) and identify areas for improvement. | Ambassadors and S&EMT | 1 month after step 10 | SMEPG Ministry assessments are completed
12. Finalize and deliver SMEPG Ministry assessment analysis report and make all refinements necessary to make the SMEPG Ministry more effective. | Ambassadors and S&EMT | 1 month after step 11 | Analysis is completed, and SMEPG Ministry is refined accordingly
Stewardship & Engagement Action Plan

## Slide 6
Lead Measure Action | Deadline Date | % Complete and Date
1. Form Stewardship, Engagement & Planned Giving Ministry Team |  | 
2. Develop definitions and effectiveness metrics |  | 
3. Analyze parish baselines and engagement success impediments |  | 
4. Research Stewardship, Engagement & Planned Giving Ministry |  | 
5. Evaluate Stewardship, Engagement & Planned Giving Ministry |  | 
6. Finalize Stewardship, Engagement & Planned Giving Ministry |  | 
7. Identify and recruit Stewardship Ambassadors |  | 
8. Train Stewardship Ambassadors |  | 
9. Implement Stewardship, Engagement & Planned Giving Ministry and manage to interim monthly targets |  | 
10. Track performance Data from Stewardship, Engagement & Planned Giving Ministry Implementation |  | 
11. Obtain qualitative and quantitative assessment data from Stewardship, Engagement & Planned Giving |  | 
12. Improve Stewardship, Engagement & Planned Giving Ministry based lessons learned in step 11 |  | 
Stewardship & Engagement Action Plan

## Slide 7: Sample 2 Stewardship & Engagement

## Slide 8: Stewardship & Engagement S.M.A.R.T. Goal
Transition all adult and youth parishioners to intentionally give a percentage of their income on their way to becoming at least tithers (10%);
Increase the adult and youth ministry engagement so that at least 90% of parishioners use their time and talents in ministry so that we can become a full participation parish; and
Cover solely through financial stewardship all parish operating expenses plus at least an additional 10% of operating expenses to be given to parish-chosen external charities without negatively impacting the capital campaign.
(d) Implement a planned giving campaign in which at least 25% of parishioners participate
We will research, develop, and implement a best practices and effective adult and youth Stewardship & Ministry Engagement Program (the “Stewardship & Engagement Program”) with a comprehensive communications plan that will achieve the following “Stewardship & Engagement Targets” within 34 months:

## Slide 9
Stewardship & Engagement Action Plan
Actions Steps | Responsible Party | Deadline | Completion Test
Interim Goal 1: Research the most effective stewardship and ministry engagement programs within 3 months |  |  | 
1. Form Stewardship & Engagement Program Team (S&EPT). | SPT and S&EPT Goal Co-Captains | 1 month after Start Date | S&EPT members agree to serve
2. Determine adult and youth stewardship, tithing, ministry engagement, and planned giving key definitions and effectiveness metrics. | S&EPT | 1 month after step 1 | Definitions and metrics determined
3. Analyze the adult and youth parish baseline on those key stewardship, tithing, ministry engagement, and planned giving metrics, survey/research parish impediments to achieving increased stewardship, tithing, ministry engagement, and planned giving success. | S&EPT | 1 month after step 2 | Parish baselines and parish impediments determination are finalized
4. Identify at least 3 engagement, 3 percentage giving/tithing, and 3 planned giving programs to consider from both inside and outside the Orthodox ecosystem. | S&EPT | Simultaneous with steps 2 & 3 | At least 3 stewardship & engagement, 3 percentage giving/ tithing, and 3 planned giving programs are examined

## Slide 10
Actions Steps | Responsible Party | Deadline | Completion Test
Interim Goal 2: Develop the most effective Stewardship & Engagement Program within 3 months |  |  | 
5. Evaluate researched adult and youth stewardship, tithing, ministry engagement, and planned giving for effectiveness against key performance metrics and parish baselines based on criteria of effectiveness determined in step 2. | S&EPT | 1 months after step 4 | Evaluation of alternative stewardship & ministry engagement, tithing, and planned giving programs is completed
6. Modify or develop new adult and youth stewardship, tithing, ministry engagement, and planned giving for utilization at the parish the Stewardship, Tithing, Ministry Engagement and Planned Giving Program (collectively the “Stewardship & Engagement Program”) and establish monthly performance benchmarks and comprehensive communications strategy and plan. | S&EPT | 2 months after step 5 | Stewardship & Engagement Program is finalized, and monthly performance benchmarks are determined
Interim Goal 3: Recruit and train Ambassadors within 2 months |  |  | 
7. Identify and recruit personal visitation ambassadors/small group leaders (“Ambassadors”) who can implement the Stewardship & Engagement Program. | S&EPT | 1 month after step 6 | Ambassadors are recruited
8. Train Ambassadors to implement the Stewardship & Engagement Program. | S&EPT | 1 month after step 7 | Ambassadors are trained
Stewardship & Engagement Action Plan

## Slide 11
Actions Steps | Responsible Party | Deadline | Completion Test
Interim Goal 4: Implement the Stewardship & Engagement Program to achieve the Stewardship & Engagement Targets within 24 months |  |  | 
9. Implement Stewardship & Engagement Program to achieve the Stewardship & Engagement Targets. | Ambassadors | 24 months after step 8 | Stewardship & Engagement Program is fully launched
10. Track and report on monthly performance benchmarks determined in step 6 and continue Ambassadors follow-up with parishioners until Stewardship & Engagement Targets are achieved | Ambassadors | Contemporaneous with step 9 | Established monthly Stewardship & Engagement Targets are achieved
Stewardship & Engagement Action Plan

## Slide 12
Actions Steps | Responsible Party | Deadline | Completion Test
Interim Goal 5: Compile and assess the results of the Stewardship Program and make necessary improvements within 2 months |  |  | 
11. Obtain and compile qualitative and quantitative data from Stewardship & Engagement Program and determine effectiveness and success (based on criteria established in step 2) and identify areas for improvement. | Ambassadors and S&EPT | 1 month after step 10 | Stewardship & Engagement Program assessments are completed
12. Finalize and deliver Stewardship & Engagement Program assessment analysis report, and make all refinements necessary to make the Stewardship & Engagement Program more effective based on information identified in step 11. | Ambassadors and S&EPT | 1 month after step 11 | Analysis is completed, and Stewardship & Engagement Program is refined accordingly
Stewardship & Engagement Action Plan

## Slide 13
Lead Measure Action | Deadline Date | % Complete and Date
1. Form Stewardship & Engagement Giving Program Team |  | 
2. Develop definitions and effectiveness metrics |  | 
3. Analyze parish baselines and engagement success impediments |  | 
4. Research Stewardship &.Engagement Program |  | 
5. Evaluate Stewardship & Engagement Program |  | 
6. Finalize Stewardship & Engagement Program |  | 
7. Identify and recruit Stewardship Ambassadors |  | 
8. Train Stewardship Ambassadors |  | 
9. Implement Stewardship & Engagement Program and manage to interim monthly targets |  | 
10. Track performance Data from Stewardship & Engagement Program Implementation |  | 
11. Obtain qualitative and quantitative assessment data from Stewardship & Engagement Program |  | 
12. Improve Stewardship & Engagement Program based lessons learned in step 11 |  | 
Stewardship & Engagement Action Plan

## Slide 14: Sample 3 Stewardship & Engagement

## Slide 15: Stewardship & Engagement SMART Goal 2
We will research, develop, and implement a best practices, effective youth and adult Stewardship Ministry Engagement Program (the “Stewardship & Engagement Program”) that will achieve the following “Stewardship & Engagement Targets” within 35 months:
create a stewardship ministry that uses effective communications strategies and full transparency to personally reach and engage all youth and adult parishioners to contribute their time, talents, and treasures;
increase ministry engagement of parishioners by at least 33% though identifying and engaging the diverse talents of all parishioners;
increase the parishioner financial stewardship so that all parish operating expenses (including at least 10% of expenses given to parish-chosen external charities and philanthropies) are paid solely through parishioner stewardship;
(d) establish a parish benevolence fund to help parishioners in need with at least $15,000 available;
(e) establish a planned giving program and endowment in which at least 5% of parishioners participate (in addition to their annual stewardship);
(f) Will transition to having parishioners become percentage financial givers on their way to becoming at least 10% tithers.

## Slide 16: Stewardship & Engagement SMART Goal 2
LAG 1: Research the most effective stewardship and engagement programs within 3 months
LAG 2: Develop the most effective parish stewardship and engagement program the “Stewardship & Engagement Program” within 4 months
LAG 3: Recruit and train the parish Stewardship & Engagement “Ambassadors” within 2 months
LAG 4: Implement the Stewardship & Engagement Program to achieve the Stewardship & Engagement Targets within 24 months
LAG 5: Compile and assess the results of the Stewardship & Engagement Program and make necessary improvements within 2 months

## Slide 17: Stewardship & Engagement SMART Goal 2
LEAD 1:
  A: recruit team
  B: determine stewardship and engagement key definitions and effectiveness metrics and timelines
  C: analyze the parish baseline on those key effectiveness metrics and identify parish impediments to success
  D: identify at least 3 stewardship and engagement, 3 endowment and 3 benevolence fund programs to consider
LEAD 2:
  A: evaluate researched programs for effectiveness against key performance metrics and parish baselines
  B: modify or develop new stewardship and engagement programs for utilization at the parish (the “Stewardship & Engagement Program”)
  C: finalize parish Stewardship & Engagement Program and establish quarterly and/or monthly performance benchmarks
LEAD 3:
  A: identify Stewardship & Engagement Program "Ambassadors" to deliver Stewardship & Engagement Program
  B: develop Ambassadors training programs
  C: train the Ambassadors
LEAD 4:
  A: implement Stewardship & Engagement Program based on determined monthly and quarterly performance benchmarks
  B: continue Ambassadors’ follow-up with parishioners until Stewardship & Engagement Targets are achieved
LEAD 5:
  A: obtain qualitative and quantitative data from Stewardship & Engagement Program effectiveness
  B: analyze all data and finalize Stewardship & Engagement Program assessment and make all necessary improvements

## Slide 18
Key Actions Necessary To Achieve SMART Goal 2 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 1: Research the most effective stewardship and ministry engagement programs within 3 months |  |  | 
1. Form Parishioner SMART Goal Team 2 (“Stewardship & Engagement Program Team 2”). | Strategic Planning Team and Goal co-Captains | 1 month after Start Date | Stewardship & Engagement Program Team 2 members agree to serve
2. Determine stewardship and ministry engagement key definitions and effectiveness metrics. | Stewardship & Engagement Program Team 2 | 1 month after step 1 | Stewardship definitions and metrics determined
3. Analyze the parish baseline on those key stewardship and ministry engagement effectiveness metrics and survey/research parish impediments to achieving increased stewardship and ministry engagement success. | Stewardship & Engagement Program Team 2 | 1 months after step 2 | Parish baselines and parish impediments determination are finalized
4. Identify at 3 stewardship and engagement, 3 endowment, and 3 benevolence fund programs to consider from both inside and outside the Orthodox ecosystem. | Stewardship & Engagement Program Team 2 | Simultaneous with steps 2 & 3 | At least 3 stewardship and engagement, 3 endowment and 3 benevolence fund programs are examined
Stewardship & Engagement SMART Goal 2 Action Plan

## Slide 19: Stewardship & Engagement SMART Goal 2 Action Plan
Key Actions Necessary To Achieve SMART Goal 2 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 2: Develop the most effective Stewardship Program within 4 months |  |  | 
5. Evaluate researched stewardship and engagement, endowment, and benevolence fund programs for effectiveness against key performance metrics and parish baselines based on criteria of effectiveness determined in step 2. | Stewardship & Engagement Program Team 2 | 2 months after step 4 | Evaluation of alternative stewardship and ministry engagement, endowment and benevolence fund programs is completed
6. Modify or develop new stewardship and engagement, endowment, and benevolence fund program for utilization at the parish (the “Stewardship & Engagement Program”) and finalize Stewardship & Engagement Program and establish monthly performance benchmarks. | Stewardship & Engagement Program Team 2 | 2 months after step 5 | Stewardship & Engagement Program is finalized, and monthly performance benchmarks are determined
LAG 3: Recruit and train Ambassadors within 2 months |  |  | 
7. Identify and recruit the Stewardship & Engagement “Ambassadors” who can implement the Stewardship & Engagement Program. | Stewardship & Engagement Program Team 2 | 1 month after step 6 | Ambassadors are recruited
8. Train Ambassadors to implement the Stewardship & Engagement Program. | Stewardship & Engagement Program Team 2 | 1 month after step 7 | Ambassadors are trained

## Slide 20: Stewardship & Engagement SMART Goal 2 Action Plan
Key Actions Necessary To Achieve SMART Goal 2 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 4: Implement the Stewardship & Engagement Program to achieve the Stewardship & Engagement Targets within 24 months |  |  | 
9. Implement Stewardship & Engagement Program to achieve the Stewardship % Engagement Targets. | Ambassadors | 24 months after step 8 | Stewardship & Engagement Program is fully launched
10. Track and report on monthly performance benchmarks determined in step 6 and continue Ambassadors follow-up with parishioners until Stewardship & Engagement Targets are achieved | Ambassadors | Contemporaneous with step 9 | Established monthly Stewardship & Engagement Targets are achieved
LAG 5: Compile and assess the results of the Stewardship Program and make necessary improvements within 2 months |  |  | 
11. Obtain and compile qualitative and quantitative data from Stewardship & Engagement Program and compile as to the effectiveness and success (based on criteria established in step 2) and identify areas for improvement. | Ambassadors and Stewardship & Engagement Program Team 2 | 1 month after step 10 | Stewardship & Engagement Program assessments are completed
12. Finalize and deliver Stewardship & Engagement Program assessment analysis report, and make all refinements necessary to make the Stewardship & Engagement Program more effective based on information identified in step 11. | Ambassadors and Stewardship & Engagement Program Team 2 | 1 month after step 11 | Stewardship & Engagement Program analysis is completed, and Stewardship & Engagement Program are refined accordingly

## Slide 21
Lead Measure Action | Deadline Date | Status: Percent Complete and Date
1. Form Stewardship Ministry Team 2 |  | 
2. Develop definitions and effectiveness metrics |  | 
3. Analyze parish baselines and engagement success impediments |  | 
4. Research Stewardship Program |  | 
5. Evaluate Stewardship Program |  | 
6. Finalize Stewardship Program |  | 
7. Identify and recruit Stewardship Ambassadors |  | 
8. Train Stewardship Ambassadors |  | 
9. Implement Stewardship & Engagement Program and manage to interim monthly targets |  | 
10. Track performance Data from Stewardship & Engagement Program Implementation |  | 
11. Obtain qualitative and quantitative assessment data from Stewardship & Engagement Program |  | 
12. Improve Stewardship & Engagement Program based lessons learned in step 11 |  | 
Stewardship & Engagement
SMART Goal 2 Scoreboard

## Slide 22: Sample 4 Stewardship & Engagement

## Slide 23: Leadership, Outreach & Stewardship S.M.A.R.T. Goal 3
Measurably improve our stewardship and discipleship by developing and implementing an effective Leadership, Outreach, and Stewardship Programs (collectively, the “Discipleship Programs”) that will achieve the following “Discipleship Goals:”
(a) 100% of Parish Council members and candidates and ministry leaders will complete our Parish Leadership Program within 12 months and all PC members and Ministry leaders thereafter will do so before assuming their duties and responsibilities;
(b) a Welcoming Ministry Program which will actively engage 100% of visitors and invite them to participate in a comprehensive welcoming process within 10 months;
(c) a new Outreach Ministry Program will ensure at least 30 or more unaffiliated Orthodox or non-Orthodox join or re-join as stewards the parish each year beginning in 2024; and
(d) increase parish time, talents, and treasures stewardship by:
(i) within 34 months, increasing parish financial stewardship to consistently fund all operating expenses plus 10% or more of that parish approved budget to be expended on mission and community philanthropic outreach; and
(ii) Aggregate time and talent contributions by parishioners is increased by at least 10% over the starting baseline within 24 months.

## Slide 24: Leadership, Outreach & Stewardship Lags - Goal 3
LAG 1: Research the most effective leadership, outreach, and stewardship programs (the “Discipleship Programs”) within 4 months
LAG 2: Develop the most effective Discipleship Programs within 4 months
LAG 3: Recruit and train any needed parish training “Discipleship Ambassadors” within 2 months
LAG 4: Implement the Discipleship Programs to achieve all Discipleship Goals in not to exceed 24 months
LAG 5: Compile and assess the results of the Discipleship Programs and make necessary improvements within 2 months

## Slide 25: Leadership, Outreach & Stewardship Leads – Goal 3
LEAD 1:
  A: recruit team
  B: determine leadership , outreach, and stewardship key definitions, desired outcomes, and effectiveness metrics
  C: analyze the parish baseline on 1(B) key metrics and identify parish baselines and impediments to success
  D: identify at least 3 Leadership, 3 Outreach, and 3 Stewardship Programs to consider
LEAD 2:
  A: evaluate researched leadership , outreach, and stewardship for effectiveness against key definitions, performance metrics and parish baselines
  B: Modify all researched or existing leadership, outreach, and stewardship programs (the “Discipleship Programs”) for utilization at Holy Trinity to meet Discipleship Goals
  C: finalize parish Discipleship Programs and establish quarterly and/or monthly performance benchmarks to assess progress toward all respective Discipleship Goals
LEAD 3:
  A: identify numbers and names of Discipleship “Ambassadors” to help deliver Discipleship Programs
  B: develop Discipleship Ambassadors training programs
  C: train the Discipleship Ambassadors
LEAD 4:
  A: implement Discipleship Programs based on determined monthly and quarterly performance benchmarks to achieve all respective Discipleship Goals
  B: continue Ambassadors’ follow-up until all Discipleship Goals are achieved
LEAD 5:
  A: obtain qualitative and quantitative data from Discipleship Programs effectiveness
  B: analyze all data and finalize Discipleship Programs assessment and make all necessary improvements

## Slide 26
Key Actions Necessary To Achieve Strategic Goal 3 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 1: Research the most effective stewardship, and ministry and liturgical engagement programs (the “Discipleship Programs”) within 4 months |  |  | 
1. Form SMART Goal Team 3 (“Discipleship Ministry Team 3”). | Strategic Planning Team and Goal co-Captains | 1 month after Start Date | Discipleship Ministry Team 3 members agree to serve
2. Determine leadership, outreach, and stewardship engagement key definitions and effectiveness metrics. | Discipleship Ministry Team 3 | 2 month after step 1 | Discipleship definitions and metrics determined
3. Research and analyze the parish baselines on step 2 key metrics and survey or otherwise research and identify parish impediments to success on those key leadership, outreach, and stewardship effectiveness metrics success | Discipleship Ministry Team 3 | 1 months after step 2 | Parish baselines and parish impediments are finalized
4. Identify and research at least 3 Leadership, 3 Outreach, and 3 Stewardship Programs from both inside and outside the Orthodox ecosystem to evaluate and consider. | Discipleship Ministry Team 3 | Simultaneous with steps 2 & 3 | At least 3 Leadership, 3 Outreach, and 3 Stewardship Discipleship Programs examined
Leadership, Outreach & Stewardship
S.M.A.R.T. Goal 3

## Slide 27
Key Actions Necessary To Achieve Strategic Goal 3 | Responsible Party | Deadline Timetable |  | Completion Confirmation Test
LAG 2: Develop the most effective Discipleship Programs within 4 months |  |  |  | 
5. Evaluate researched leadership, outreach, and stewardship programs for effectiveness against key performance metrics and parish baselines based on criteria of effectiveness determined in step 2. | Discipleship Ministry Team 3 | 2 months after step 4 | Evaluation of alternative Leadership, Outreach, and Stewardship Discipleship programs is completed | Evaluation of alternative Stewardship, Outreach & Evangelism, and Leadership Discipleship programs is completed
6. Modify researched or existing Discipleship Programs for utilization at Holy Trinity and create and finalize parish Discipleship Programs and establish quarterly and/or monthly performance benchmarks to achieve all respective established Discipleship Goals. | Discipleship Ministry Team 3 | 2 months after step 5 | Discipleship Programs are finalized | Discipleship Programs are finalized
LAG 3: Recruit and train the parish Discipleship Ambassadors within 2 months |  |  |  | 
7. Identify and recruit the “Discipleship Ambassadors” who can implement the various Discipleship Programs. | Discipleship Ministry Team 3 | 1 month after step 6 | Discipleship Ambassadors are recruited | Discipleship Ambassadors are recruited
8. Develop Discipleship Ambassadors training program and train the Discipleship Ambassadors selected in step 7. | Discipleship Ministry Team 3 | 1 month after step 7 | Discipleship Ambassadors are trained | Discipleship Ambassadors are trained
Leadership, Outreach & Stewardship
S.M.A.R.T. Goal 3

## Slide 28
Key Actions Necessary To Achieve Strategic Goal 3 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 4: Implement the Engagement Programs to achieve the targeted goals within 24 months |  |  | 
9. Implement Discipleship Programs based on monthly and/or quarterly performance benchmarks determined in step 6 with continual Ambassador follow-up until all Discipleship Goals are achieved. | Discipleship Ambassadors | 24 months after step 8 | Established quarterly and/or monthly Discipleship Goals are achieved
LAG 5: Compile and assess the results of the Parish Discipleship Programs and make necessary improvements within 2 months |  |  | 
10. Obtain and compile qualitative and quantitative data from Discipleship Programs and compile as to the effectiveness and success (based on criteria established in step 2) and areas for improvement. | Discipleship Ambassadors and Discipleship Ministry Team 3 | 1 month after step 9 | Discipleship Programs assessments are completed
11. Finalize and deliver improvements to Discipleship Programs assessment analysis report, and make all refinements necessary to make those Ministries more effective based on information identified in step 10, and revise and improve them accordingly. | Discipleship Ambassadors and Discipleship Ministry Team 3 | 1 month after step 10 | Discipleship Programs implementation analysis is completed, and Discipleship Programs are refined accordingly
Leadership, Outreach & Stewardship
S.M.A.R.T. Goal 3

## Slide 29
Lead Measure Action | Deadline Date | Status: Percent Complete and Date
1. Form Discipleship Ministry Team 1 |  | 
2. Develop definitions and effectiveness metrics |  | 
3. Analyze parish baselines and success impediments |  | 
4. Research Discipleship Programs |  | 
5. Evaluate Discipleship Programs |  | 
6. Finalize Discipleship Programs |  | 
7. Identify and recruit Discipleship Ambassadors |  | 
8. Train Discipleship Ambassadors |  | 
9. Implement Discipleship Programs and manage to interim quarterly and monthly targets to achieve all Discipleship Goals |  | 
10. Obtain Data from Discipleship Programs Implementation |  | 
11. Improve Discipleship Programs based lessons learned in step 10 |  | 
Leadership, Outreach & Stewardship
Goal 3 Scoreboard

## Slide 30: Sample 5 Stewardship & Engagement

## Slide 31: Stewardship & Engagement Wildly Important Goal 1
Develop and implement effective Stewardship, Ministry, and Liturgical Engagement Programs (collectively, the “Engagement Programs”) that within 36 months will achieve the following “Engagement Targets”:
Increase liturgical engagement by 50% or more;
Increase ministries engagement by 50% or more;
Increase the parishioner financial stewardship so that all operating expenses are paid through stewardship.

## Slide 32: Prelim Lag Measures WIG 1
LAG 1: Research the most effective stewardship, ministry, and liturgical engagement programs (the “Engagement Programs”) within 4 months
LAG 2: Develop the most effective Engagement Programs within 4 months
LAG 3: Recruit and train the parish “Engagement Ambassadors” within 2 months
LAG 4: Implement the Engagement Programs to achieve the Engagement Targets within 24 months
LAG 5: Compile and assess the results of the Engagement Programs and make necessary improvements within 2 months
Ministries WIG 1:
Develop and implement effective Stewardship, Ministry, and Liturgical Engagement Programs (the “Engagement Programs”) that within 36 months will achieve the following “Engagement Targets”:
Increase liturgical engagement by 50% or more;
Increase ministries engagement by 50% or more;
Increase the parishioner financial stewardship so that all operating expenses are paid through stewardship.

## Slide 33: Prelim Lead Measures WIG 1
LEAD 1:
  A: recruit team
  B: determine stewardship , ministry, and liturgical engagement key definitions and effectiveness metrics
  C: analyze the parish baseline on those key effectiveness metrics and identify parish impediments to success
  D: identify at least 5 Stewardship and 5 Ministry and Liturgical Engagement Programs to consider
LEAD 2:
  A: evaluate researched Stewardship, Ministry and Liturgical Engagement programs for effectiveness against key performance metrics and parish baselines
  B: modify Stewardship, Ministry and Liturgical “Engagement “Programs” for utilization at St Demetrios
  C: finalize parish Engagement Programs and establish quarterly and/or monthly performance benchmarks
LEAD 3:
  A: identify numbers and names of Engagement Programs Engagement Ambassadors
  B: develop Engagement Ambassadors training programs
  C: train the Engagement Ambassadors
LEAD 4:
  A: implement Engagement Programs based on determined monthly and quarterly performance benchmarks
  B: continue Ambassadors’ follow-up with parishioners until Engagement Targets are achieved
LEAD 5:
  A: obtain qualitative and quantitative data from Engagement Programs effectiveness
  B: analyze all data and finalize Engagement Programs assessment and make all necessary improvements
LAG 1: Research the most effective stewardship, ministry and liturgical engagement programs (the “Engagement Programs”) within 4 months
LAG 2: Develop the most effective Engagement Programs within 4 months
LAG 3: Recruit and train the parish Engagement Ambassadors within 2 months
LAG 4: Implement the Engagement Programs to achieve the Engagement Targets within 24 months
LAG 5: Compile and assess the results of the Engagement Programs and make necessary improvements within 2 months

## Slide 34: Stewardship & Engagement Wildly Important Goal 1 Action Plan
Key Actions Necessary To Achieve Strategic WIG 1 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 1: Research the most effective stewardship, and ministry and liturgical engagement programs (the “Engagement Programs”) within 4 months |  |  | 
1. Form Parish Wildly Important Goal Team 1 (“Engagement Ministry Team 1”). | Strategic Planning Team and Goal co-Captains | 1 month after Start Date | Engagement Ministry Team 1 members agree to serve
2. Determine stewardship and ministry and liturgical engagement key definitions and effectiveness metrics. | Engagement Ministry Team 1 | 2 month after step 1 | Engagement definitions and metrics determined
3. Analyze the parish baseline on those key stewardship and engagement effectiveness metrics and survey/research parish impediments to achieving increased stewardship and ministry and liturgical engagement success | Engagement Ministry Team 1 | 1 months after step 2 | Parish baselines and parish impediments are finalized
4. ID at least 5 Stewardship and 5 Ministry and Liturgical Engagement Programs to consider from both inside and outside the Orthodox ecosystem. | Engagement Ministry Team 1 | Simultaneous with steps 2 & 3 | At least 5 Stewardship and 5 Ministry and Liturgical Engagement Programs examined

## Slide 35: Stewardship & Engagement Wildly Important Goal 1 Action Plan
Key Actions Necessary To Achieve Strategic WIG 1 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 2: Develop the most effective Engagement Programs within 4 months |  |  | 
5. Evaluate researched Stewardship, Ministry and Liturgical Engagement programs for effectiveness against key performance metrics and parish baselines based on criteria of effectiveness determined in step 2. | Engagement Ministry Team 1 | 2 months after step 4 | Evaluation of alternative Stewardship, Ministry and Liturgical Engagement programs is completed
6. Modify Engagement Programs for utilization at St. Demetrios and finalize parish Engagement Programs and establish quarterly and/or monthly performance benchmarks. | Engagement Ministry Team 1 | 2 months after step 5 | Engagement Programs are finalized
LAG 3: Recruit and train the parish Engagement Ambassadors within 2 months |  |  | 
7. Identify and recruit the “Engagement Ambassadors” who can implement the Engagement Programs. | Engagement Ministry Team 1 | 1 month after step 6 | Engagement Ambassadors are recruited
8. Develop Engagement Ambassadors training program and train the Engagement Ambassadors selected in step 7. | Engagement Ministry Team 1 | 1 month after step 7 | Engagement Ambassadors are trained

## Slide 36
Key Actions Necessary To Achieve Strategic WIG 1 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 4: Implement the Engagement Programs to achieve the targeted goals within 24 months |  |  | 
9. Implement Engagement Programs based on monthly and/or quarterly performance benchmarks determined in step 6 with continual Ambassador follow-up with parishioners until Engagement Targets are achieved. | Engagement Ambassadors | 24 months after step 8 | Established quarterly and/or monthly Engagement Targets are achieved
LAG 5: Compile and assess the results of the Parish Engagement Programs and make necessary improvements within 2 months |  |  | 
10. Obtain and compile qualitative and quantitative data from Engagement Programs and compile as to the effectiveness and success (based on criteria established in step 2) and areas for improvement. | Engagement Ambassadors and Engagement Ministry Team 1 | 1 month after step 9 | Engagement Programs assessments are completed
11. Finalize and deliver improvements to Engagement Programs assessment analysis report, and make all refinements necessary to make those Ministries more effective based on information identified in step 10, and revise and improve them accordingly. | Engagement Ambassadors and Engagement Ministry Team 1 | 1 month after step 10 | Engagement Programs implementation analysis is completed, and Engagement Programs are refined accordingly
Stewardship & Engagement Wildly Important Goal 1 Action Plan

## Slide 37: Stewardship & Engagement WIG 1 Compelling Scoreboard
Lead Measure Action | Deadline Date | Status: Percent Complete and Date
1. Form Engagement Ministry Team 1 | 1 month ___-21 | 
2. Develop definitions and effectiveness metrics | 2 months ___-21 | 
3. Analyze parish baselines and engagement success impediments | 1 month ___-21 | 
4. Research Engagement Programs | 1 month ____-21 | 
5. Evaluate Engagement Programs | 2 months ____-22 | 
6. Finalize Engagement Programs | 2 months ____-22 | 
7. Identify and recruit Engagement Ambassadors | 1 month _____-22 | 
8. Train Engagement Ambassadors | 1 month _____-22 | 
9. Implement Engagement Programs and manage to interim quarterly and monthly targets | 24 months ___-24 | 
10. Obtain Data from Engagement Programs Implementation | 1 month_____-24 | 
11. Improve Engagement Programs based lessons learned in step 10 | 1 month ____-24 | 

## Slide 38: Sample 6 Stewardship & Engagement

## Slide 39: Parishioner Engagement & Spiritual Growth Wildly Important Goal 3
Develop and implement within 36 months effective Parishioner Engagement & Spiritual Growth Programs (collectively, the “Engagement Programs”) that will achieve the following “Engagement Targets”:
Increase ministries engagement by at least 50%;
Increase the parishioner financial stewardship so that:
all parish operating expenses (plus increases in funding for parish-chosen external charities and philanthropies that equal at least 10% of the other operating expenses) are paid through parishioner stewardship; and
the median annual stewardship contribution from parishioners increases by at least 75%;
(c) Actively engage at least 50% of parishioners in a religious education and spiritual engagement program.

## Slide 40
LAG 1: Research the most effective stewardship and ministry engagement, and spiritual growth programs (the “Engagement Programs”) within 4 months
LAG 2: Develop the most effective Engagement Programs within 4 months
LAG 3: Recruit and train the parish “Engagement Ambassadors” within 2 months
LAG 4: Implement the Engagement Programs to achieve the Engagement Targets within 24 months
LAG 5: Compile and assess the results of the Engagement Programs and make necessary improvements within 2 months
WIG 3:
Develop and implement within 36 months effective Parishioner Engagement & Spiritual Growth Programs (collectively, the “Engagement Programs”) that will achieve the following “Engagement Targets”:
Increase ministries engagement by at least 50%;
Increase the parishioner financial stewardship so that:
all parish operating expenses (plus increases in funding for parish-chosen external charities and philanthropies to equal at least 10% of the other operating expenses) are paid through parishioner stewardship; and
the median annual stewardship contribution from parishioners will increase by at least 75%;
(c) Actively engage at least 50% of parishioners in a religious education and spiritual engagement program.
Parishioner Engagement & Spiritual Growth Lag Measures WIG 3

## Slide 41
LEAD 1:
  A: recruit team
  B: determine stewardship, ministry engagement, and spiritual engagement key definitions and effectiveness metrics
  C: analyze the parish baseline on those key effectiveness metrics and identify parish impediments to success
  D: identify at least 5 stewardship/ministry engagement and 5 spiritual growth programs to consider
LEAD 2:
  A: evaluate researched stewardship, ministry engagement, and spiritual engagement programs for effectiveness against key performance metrics and parish baselines
  B: modify stewardship, ministry engagement and spiritual engagement programs (collectively, the ”Engagement Programs”) for utilization at St Nicholas
  C: finalize parish Engagement Programs and establish quarterly and/or monthly performance benchmarks
LEAD 3:
  A: identify numbers and names of Engagement Programs and Engagement Ambassadors to deliver Engagement Programs
  B: develop Engagement Ambassadors training programs
  C: train the Engagement Ambassadors
LEAD 4:
  A: implement Engagement Programs based on determined monthly and quarterly performance benchmarks
  B: continue Engagement Ambassadors’ follow-up with parishioners until Engagement Targets are achieved
LEAD 5:
  A: obtain qualitative and quantitative data from Engagement Programs effectiveness
  B: analyze all data and finalize Engagement Programs assessment and make all necessary improvements
LAG 1: Research the most effective stewardship and ministry engagement, and spiritual growth programs (the “Engagement Programs”) within 4 months
LAG 2: Develop the most effective Engagement Programs within 4 months
LAG 3: Recruit and train the parish “Engagement Ambassadors” within 2 months
LAG 4: Implement the Engagement Programs to achieve the Engagement Targets within 24 months
LAG 5: Compile and assess the results of the Engagement Programs and make necessary improvements within 2 months
Parishioner Engagement & Spiritual Growth Lead Measures WIG 3

## Slide 42: Parishioner Engagement & Spiritual Growth Wildly Important Goal 3 Action Plan
Key Actions Necessary To Achieve Strategic WIG 3 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 1: Research the most effective stewardship, and ministry and spiritual engagement programs (the “Engagement Programs”) within 4 months |  |  | 
1. Form Parishioner Engagement & Spiritual Growth Wildly Important Goal Team 3 (“Engagement Programs Team 3”). | Strategic Planning Team and Goal co-Captains | 1 month after Start Date | Engagement Programs Ministry Team 3 members agree to serve
2. Determine stewardship and ministry and spiritual engagement key definitions and effectiveness metrics. | Engagement Programs Ministry Team 3 | 2 month after step 1 | Engagement definitions and metrics determined
3. Analyze the parish baseline on those key stewardship, ministry and spiritual engagement effectiveness metrics and survey/research parish impediments to achieving increased stewardship and ministry and spiritual engagement success. | Engagement Programs Ministry Team 3 | 1 months after step 2 | Parish baselines and parish impediments determination are finalized
4. Identify at least 5 stewardship/ ministry engagement, and 5 spiritual growth programs, to consider from both inside and outside the Orthodox ecosystem. | Engagement Programs Ministry Team 3 | Simultaneous with steps 2 & 3 | At least 5 stewardship /ministry engagement, and 5 spiritual growth programs are examined

## Slide 43: Parishioner Engagement & Spiritual Growth Wildly Important Goal 3 Action Plan
Key Actions Necessary To Achieve Strategic WIG 3 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 2: Develop the most effective Engagement Programs within 4 months |  |  | 
5. Evaluate researched stewardship/ ministry engagement and spiritual growth programs for effectiveness against key performance metrics and parish baselines based on criteria of effectiveness determined in step 2. | Engagement Programs Ministry Team 3 | 2 months after step 4 | Evaluation of alternative stewardship, ministry engagement, and spiritual engagement programs is completed
6. Modify or develop stewardship / ministry engagement and spiritual growth programs (collectively, the “Engagement Programs”) for utilization at St. Nicholas and finalize Engagement Programs and establish monthly performance benchmarks. | Engagement Programs Ministry Team 3 | 2 months after step 5 | Engagement Programs are finalized, and monthly performance benchmarks are determined
LAG 3: Recruit and train the parish Engagement Ambassadors within 2 months |  |  | 
7. Identify and recruit the “Engagement Ambassadors” who can implement the Engagement Programs. | Engagement Programs Ministry Team 3 | 1 month after step 6 | Engagement Ambassadors are recruited
8. Develop Engagement Ambassadors training program and train the Engagement Ambassadors selected in step 7. | Engagement Programs Ministry Team 3 | 1 month after step 7 | Engagement Ambassadors are trained

## Slide 44: Parishioner Engagement & Spiritual Growth Wildly Important Goal 3 Action Plan
Key Actions Necessary To Achieve Strategic WIG 3 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 4: Implement the Engagement Programs to achieve the Engagement Targets within 24 months |  |  | 
9. Implement Engagement Programs to achieve the Engagement Targets. | Engagement Ambassadors | 24 months after step 8 | Engagement Programs are fully launched
10. Track and report on monthly performance benchmarks determined in step 6 and continue Engagement Ambassadors’ follow-up with parishioners until Engagement Targets are achieved | Engagement Ambassadors | Contemporaneous with step 9 | Established monthly Engagement Targets are achieved
LAG 5: Compile and assess the results of the Parish Engagement Programs and make necessary improvements within 2 months |  |  | 
11. Obtain and compile qualitative and quantitative data from Engagement Programs and compile as to the effectiveness and success (based on criteria established in step 2) and identify areas for improvement. | Engagement Ambassadors and Engagement Ministry Team 3 | 1 month after step 10 | Engagement Programs assessments are completed
12. Finalize and deliver Engagement Programs assessment analysis report, and make all refinements necessary to make the Engagement Ministries more effective based on information identified in step 11. | Engagement Ambassadors and Engagement Ministry Team 3 | 1 month after step 11 | Engagement Programs analysis is completed, and Engagement Programs are refined accordingly

## Slide 45
Lead Measure Action | Deadline Date | Status: Percent Complete and Date
1. Form Engagement Ministry Team 3 | 1 month ___-22 | 
2. Develop definitions and effectiveness metrics | 2 months ___-22 | 
3. Analyze parish baselines and engagement success impediments | 1 month ___-22 | 
4. Research Engagement Programs | together with 2 and 3 month ____-22 | 
5. Evaluate Engagement Programs | 2 months ____-22 | 
6. Finalize Engagement Programs | 2 months ____-22 | 
7. Identify and recruit Engagement Ambassadors | 1 month _____-22 | 
8. Train Engagement Ambassadors | 1 month _____-22 | 
9. Implement Engagement Programs and manage to interim monthly targets | 24 months ___-24 | 
10. Track performance Data from Engagement Programs Implementation | Simultaneous with step 9 | 
11. Obtain qualitative and quantitative assessment data from Engagement Programs | 1 month_____-24 | 
12. Improve Engagement Programs based lessons learned in step 11 | 1 month ____-24 | 
Parishioner Engagement & Spiritual Growth Wildly Important Goal 3
Compelling Scoreboard

## Slide 46: Sample 7 Stewardship & Engagement

## Slide 47: Stewardship & Engagement Wildly Important Goal 1
Develop and implement effective youth and adult “Stewardship & Ministry Engagement Programs,” gain membership growth, and enhance our financial position so that within 36 months, we will achieve the following “Engagement Targets”:
(a) Increase ministries engagement by 50% or more across each age demographic;
(b) Net increase of 30 or more new steward families per year; and
(c) Increase parish stewardship financial giving to fund 100% of the parish approved budget (including parish approved ministry expenses); provided that 10% or more of that parish approved budget is to be spent on community philanthropic outreach.

## Slide 48: Stewardship & Engagement WIG 1 Lag Measures_
LAG 1: Research the most effective youth and adult Stewardship & Ministry Engagement Programs within 4 months
LAG 2: Develop the most effective Stewardship & Ministry Engagement Programs within 4 months
LAG 3: Recruit and train the parish “Engagement Champions” within 2 months
LAG 4: Implement the Stewardship & Ministry Engagement Programs to achieve the “Engagement Targets” within 24 months
LAG 5: Compile and assess the results of the Stewardship & Ministry Engagement Programs and make necessary improvements within 2 months
Stewardship & Engagement WIG 1:
Develop and implement effective youth and adult “Stewardship & Ministry Engagement Programs,” gain membership growth, and enhance our financial position so that within 36 months, we will achieve the following “Engagement Targets”:
(a) Increase ministries engagement by 50% or more across each age demographic;
(b) Net increase of 30 or more new steward families per year; and
(c) Increase parish stewardship financial giving to fund 100% of the parish approved budget (including parish approved ministry expenses); provided that 10% or more of that parish approved budget is to be spent on community philanthropic outreach.

## Slide 49: Stewardship & Engagement WIG 1 Lead Measures
LEAD 1:
  A: recruit team
  B: determine stewardship and ministry engagement key definitions and effectiveness metrics for each age demographic of youth and adults
  C: analyze the parish baseline on those key effectiveness metrics and identify parish impediments to success
  D: identify effective Stewardship & Ministry Engagement Programs to consider
LEAD 2:
  A: evaluate researched stewardship &ministry engagement programs for effectiveness against key performance metrics and parish baselines
  B: modify and/or develop Stewardship & Ministry Engagement Programs for implementation at Holy Trinity
  C: finalize parish Stewardship & Engagement Programs and establish quarterly and/or monthly performance benchmarks
LEAD 3:
  A: define Engagement Champions role and responsibilities
  B: identify numbers and names of Engagement Champions
  C: develop Engagement Champions training programs
  D: train the Engagement Champions
LEAD 4:
  A: implement Stewardship & Ministry Engagement Programs based on determined monthly and quarterly performance benchmarks
  B: continue Engagement Champions’ follow-up with parishioners until Engagement Targets are achieved
LEAD 5:
  A: obtain qualitative and quantitative data from Stewardship & Engagement Programs effectiveness
  B: analyze all data and finalize Stewardship & Engagement Programs assessment and make all necessary improvements
LAG 1: Research the most effective youth and adult stewardship and Stewardship & Ministry Engagement Programs within 4 months
LAG 2: Develop the most effective Stewardship & Ministry Engagement Programs within 4 months
LAG 3: Recruit and train the parish “Engagement Champions” within 2 months
LAG 4: Implement the Stewardship & Ministry Engagement Programs to achieve the Engagement Targets within 24 months
LAG 5: Compile and assess the results of the Stewardship & Ministry Engagement Programs and make necessary improvements within 2 months

## Slide 50: Stewardship & Engagement Wildly Important Goal 1 Action Plan
Key Actions Necessary To Achieve Strategic WIG 1 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 1: Research the most effective stewardship and ministry Engagement Programs within 4 months |  |  | 
1. Form Stewardship & Ministry Engagement Team 1 (“S&ME Team 1”). | Strategic Planning Team and Goal co-Captains | 1 month after Start Date | S&ME Team 1 members agree to serve
2. Determine stewardship and ministry engagement key definitions of engagement success and effectiveness metrics for each age demographic of youth and adults. | S&ME Team 1 | 2 month after step 1 | Key stewardship and ministry definitions and key effectiveness metrics are determined
3. Analyze the parish baseline on those key effectiveness metrics and identify parish impediments to success. | S&ME Team 1 | 1 month after step 2 | Parish baseline and impediments have been determined.
4. Identify successful Stewardship & Ministry Engagement Programs to consider 5 or more Orthodox and 5 or more non-Orthodox programs. | S&ME Team 1 | Simultaneously during step 2 and 3 | Targeted number of programs have been identified

## Slide 51: Stewardship & Engagement Wildly Important Goal 1 Action Plan
Key Actions Necessary To Achieve Strategic WIG 1 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 2:_Develop the most effective Engagement Programs within 4 months |  |  | 
5. Evaluate researched Stewardship & Ministry Engagement programs for effectiveness against definitions of engagement success and effectiveness metrics determined in step 2. | S&ME Team 1 | 2 month after step 4 | Stewardship & Ministry Engagement programs effectiveness evaluation completed
6. Create or modify youth and adult Stewardship & Ministry Engagement Programs for implementation at Holy Trinity (the “Stewardship & Engagement Programs”) and establish quarterly and/or monthly Stewardship & Engagement Programs performance benchmarks in order to achieve Engagement Targets. | S&ME Team 1 | 2 month after step 5 | Stewardship & Ministry Engagement Programs have been developed and quarterly or monthly effectiveness measurement benchmarks have been determined
LAG 3:_Recruit and train the parish Engagement Champions within 2 months |  |  | 
7. Define roles and responsibilities for team to implement the Stewardship & Ministry Engagement Programs (the “Engagement Champions”) and identify numbers and names of Engagement Champions. | S&ME Team 1 | 1 month after step 6 | Engagement Champions are identified along with roles and responsibilities

## Slide 52: Stewardship & Engagement WIG 1 Action Plan
Key Actions Necessary To Achieve Strategic WIG 1 | Responsible Party | Deadline Timetable | Completion Confirmation Test
8. Develop Engagement Champions training programs to teach them how to implement the Stewardship & Ministry Engagement Programs and train Engagement Champions. | S&ME Team 1 | 1 month after step 7 | Stewardship & Ministry Engagement Programs Training plan/manual and training completed
LAG 4:_Implement the Stewardship & Ministry Engagement Programs to achieve the Engagement Targets within 24 months |  |  | 
9. Implement Stewardship & Ministry Engagement Programs based on determined monthly and quarterly performance benchmarks in order to fully achieve the Engagement Targets. | Engagement Champions | 24 month after step 8 | Stewardship & Ministry Engagement Programs are implemented to achieve or exceed the Engagement Targets
10. Ongoing monthly/quarterly reviews of results of Stewardship & Ministry Engagement Programs with Engagement Champions. | Engagement Champions | Monthly during 24 months of implementation | Stewardship & Ministry Engagement Programs assessments are compiled

## Slide 53: Stewardship & Engagement WIG 1 Action Plan
Key Actions Necessary To Achieve Strategic WIG 1 | Responsible Party | Deadline Timetable | Completion Confirmation Test
LAG 5:_Compile and assess the results of the Stewardship & Ministry Engagement Programs and make necessary improvements within 2 months |  |  | 
11. Obtain and analyze qualitative and quantitative data from Stewardship & Ministry Engagement Programs effectiveness (based on criteria established in step 2) and make all necessary program improvements. | Engagement Champions and S&ME Team 1 | 2 month after step 10 | Review data and make necessary changes to Stewardship & Ministry Engagement Programs

## Slide 54
Lead Measure Action | Deadline Date | Status: Percent Complete and Date
1. Form Stewardship & Ministry Engagement Ministry Team 1 | 1 month ___-21 | 
2. Develop definitions and effectiveness metrics | 2 months __-21 | 
3. Analyze parish baselines and engagement success impediments | 1 months __-22 | 
4. Research Stewardship & Ministry Engagement Programs | 1 month __-22 | 
5. Evaluate Stewardship & Ministry Engagement Programs | 2 months __-22 | 
6. Finalize Stewardship & Ministry Engagement Programs | 3 months __-22 | 
7. Identify and recruit Engagement Champions | 1 month ___-22 | 
8. Train Engagement Champions | 2 months ___-22 | 
9. Implement Stewardship & Ministry Engagement Programs and manage to interim quarterly and monthly targets | 12 months __-23 | 
10. Obtain Data from Stewardship & Ministry Engagement Programs Implementation | 1 month___-24 | 
11. Improve Stewardship & Ministry Engagement Programs based lessons learned in step 10 and revamp | 2 months ___-24 | 
Stewardship & Engagement
WIG 1 Compelling Scoreboard